## TASK
task_code | status_code | wbs_id | task_name | target_start_date | target_end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Planned Start | (*)Planned Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Delete This Row
A4380 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | MAN: Insulation | 2025-12-02 00:30 | 2026-04-27 23:30 |  |  | 146 | 0
A4390 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | INSP: Insulation | 2025-02-26 00:30 | 2026-05-11 23:30 |  |  | 434 | 0
A4400 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DCC.a: Insulation | 2025-02-26 00:30 | 2026-05-14 23:30 |  |  | 437 | 0
A4410 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DCC.r: Insulation | 2025-02-26 00:30 | 2026-05-18 23:30 |  |  | 441 | 0
A4420 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | LT: Insulation | 2025-02-26 00:30 | 2026-06-08 23:30 |  |  | 462 | 0
A4430 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Heat insulation material ( for dust hoppers of ESP) | 2026-06-09 00:30 | 2026-06-24 23:30 |  |  | 16 | 0
A4440 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Sound insulation (for secondary ID fan) | 2026-06-09 00:30 | 2026-06-24 23:30 |  |  | 16 | 0
A4450 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Sound insulation (for MHS booster fan) | 2026-06-09 00:30 | 2026-06-24 23:30 |  |  | 16 | 0
A4460 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | BE.s: Misc. electric hoists | 2025-06-11 00:30 | 2025-07-09 23:30 |  |  | 29 | 0
A4470 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | BE.a: Misc. electric hoists | 2025-02-26 00:30 | 2025-07-23 23:30 |  |  | 146 | 0
A4480 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DE.s: Misc. electric hoists | 2025-09-30 00:30 | 2025-11-27 23:30 |  |  | 57 | 0
A4490 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DE.a/i: Misc. electric hoists | 2025-02-26 00:30 | 2025-12-11 23:30 |  |  | 284 | 0
A4500 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | MAN: Misc. electric hoists | 2025-11-14 00:30 | 2026-03-10 23:30 |  |  | 116 | 0
A4510 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | INSP: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-24 23:30 |  |  | 386 | 0
A4520 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DCC.a: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-27 23:30 |  |  | 389 | 0
A4530 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DCC.r: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-31 23:30 |  |  | 393 | 0
A4540 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | LT: Misc. electric hoists | 2025-02-26 00:30 | 2026-04-21 23:30 |  |  | 414 | 0
A4550 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric hoist (for transformer rectifier of ESP) | 2025-02-26 00:30 | 2026-04-21 23:30 |  |  | 414 | 0
A4560 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric hoist | 2025-02-26 00:30 | 2026-04-21 23:30 |  |  | 414 | 0
A4570 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric Hoist for Secondary Dedusting Electrical Room | 2025-02-26 00:30 | 2026-04-21 23:30 |  |  | 414 | 0
A1810 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | INSP: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-12 23:30 |  |  | 374 | 0
A1820 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | DCC.a: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-15 23:30 |  |  | 377 | 0
A1830 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | DCC.r: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-18 23:30 |  |  | 380 | 0
A1840 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | LT: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-04-08 23:30 |  |  | 401 | 0
A1900 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.7 | AoS: Dog house unit drive | 2025-02-26 00:30 | 2026-04-08 23:30 |  |  | 401 | 0
A1760 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | BE.s: Dog house unit drive | 2025-04-16 00:30 | 2025-06-25 23:30 |  |  | 70 | 0
A1770 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | BE.a: Dog house unit drive | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A1780 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | DE.s: Dog house unit drive | 2025-08-18 00:30 | 2025-11-14 23:30 |  |  | 87 | 0
A1790 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | DE.a/i: Dog house unit drive | 2025-02-26 00:30 | 2025-11-28 23:30 |  |  | 271 | 0
A1800 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | MAN: Dog house unit drive (Converter-1) | 2025-10-23 00:30 | 2026-02-26 23:30 |  |  | 126 | 0
A4580 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | BE.s: Fluid and utility facilities | 2025-05-13 00:30 | 2025-07-10 23:30 |  |  | 59 | 0
A4590 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | BE.a: Fluid and utility facilities | 2025-02-26 00:30 | 2025-07-24 23:30 |  |  | 147 | 0
A4600 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DE.s: Fluid and utility facilities | 2025-07-25 00:30 | 2025-12-20 23:30 |  |  | 146 | 0
A4610 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DE.a/i: Fluid and utility facilities | 2025-02-26 00:30 | 2026-01-04 23:30 |  |  | 307 | 0
A4620 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | MAN: Fluid and utility facilities | 2025-11-02 00:30 | 2026-03-13 23:30 |  |  | 131 | 0
A4630 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | INSP: Fluid and utility facilities | 2025-02-26 00:30 | 2026-03-27 23:30 |  |  | 389 | 0
A4640 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DCC.a: Fluid and utility facilities | 2025-02-26 00:30 | 2026-03-30 23:30 |  |  | 392 | 0
A4650 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DCC.r: Fluid and utility facilities | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A4660 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | LT: Fluid and utility facilities | 2025-02-26 00:30 | 2026-04-24 23:30 |  |  | 417 | 0
A4670 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17.1.2.2.4.17.10 | AoS: Interconnecting piping - fire water | 2025-02-26 00:30 | 2026-04-24 23:30 |  |  | 417 | 0
A4680 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17.1.2.2.4.17.10 | AoS: Interconnecting piping - nitrogen | 2025-02-26 00:30 | 2026-04-24 23:30 |  |  | 417 | 0
A4710 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | BE.s: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-06-27 23:30 |  |  | 120 | 0
A4720 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | BE.a: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-07-11 23:30 |  |  | 134 | 0
A4730 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DE.s: General scope for buildings and foundations | 2025-03-29 00:30 | 2025-11-21 23:30 |  |  | 234 | 0
A4740 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DE.a/i: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-12-05 23:30 |  |  | 278 | 0
A4750 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | MAN: General scope for buildings and foundations | 2025-06-13 00:30 | 2026-04-20 23:30 |  |  | 308 | 0
A4760 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | INSP: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-04 23:30 |  |  | 427 | 0
A4770 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DCC.a: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-07 23:30 |  |  | 430 | 0
A4780 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DCC.r: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-11 23:30 |  |  | 434 | 0
A4790 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | LT: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4800 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Anchor boxes/bolts for equipment directly placed in concrete | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4810 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Equipment base frames incl. anchor bolts | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4820 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Anchors for steel structure | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4830 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Retaining bars, weld-on plates; edge protection as well as running rails for transformers; wall penetrations and pi | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4840 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Concrete covers for openings | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4850 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Steel covers for openings | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4860 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Earthwork/ cable protection measures related to temporary site facilities | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4870 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Lightning protection and earthing | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4880 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Conduits and conduit templates including all connections placed in concrete or ground, as well as conduit closures | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4890 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Doors and windows | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4900 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Temporary site fencing incl. gates, barriers, repair and disassembly | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A4910 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | BE.s: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-04-30 23:30 |  |  | 63 | 0
A4920 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | BE.a: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-05-16 23:30 |  |  | 78 | 0
A4930 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | DE.s: Secondary dedusting E-building | 2025-07-16 00:30 | 2025-11-16 23:30 |  |  | 121 | 0
A4940 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | DE.a/i: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-11-30 23:30 |  |  | 273 | 0
A4950 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | BE.s: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-02-26 00:30 | 2025-07-13 23:30 |  |  | 136 | 0
A4960 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | BE.a: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-02-26 00:30 | 2025-07-27 23:30 |  |  | 150 | 0
A4970 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | DE.s: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-07-28 00:30 | 2025-12-22 23:30 |  |  | 144 | 0
A4980 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | DE.a/i: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Second | 2025-02-26 00:30 | 2026-01-05 23:30 |  |  | 308 | 0
A4990 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | BE.s: Secondary ID fan foundation | 2025-04-16 00:30 | 2025-05-30 23:30 |  |  | 44 | 0
A5000 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | BE.a: Secondary ID fan foundation | 2025-02-26 00:30 | 2025-06-13 23:30 |  |  | 106 | 0
A5010 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | DE.s: Secondary ID fan foundation | 2025-06-18 00:30 | 2025-08-20 23:30 |  |  | 63 | 0
A5020 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | DE.a/i: Secondary ID fan foundation | 2025-02-26 00:30 | 2025-09-03 23:30 |  |  | 187 | 0
A5030 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | BE.s: Secondary ID fan rain protection foundation | 2025-04-16 00:30 | 2025-05-30 23:30 |  |  | 44 | 0
A5040 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | BE.a: Secondary ID fan rain protection foundation | 2025-02-26 00:30 | 2025-06-13 23:30 |  |  | 106 | 0
A5050 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | DE.s: Secondary ID fan rain protection foundation | 2025-06-14 00:30 | 2025-08-20 23:30 |  |  | 67 | 0
A5060 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | DE.a/i: Secondary ID fan rain protection foundation | 2025-02-26 00:30 | 2025-09-03 23:30 |  |  | 187 | 0
A5070 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | BE.s: Secondary stack foundation | 2025-04-25 00:30 | 2025-06-08 23:30 |  |  | 44 | 0
A5080 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | BE.a: Secondary stack foundation | 2025-02-26 00:30 | 2025-06-22 23:30 |  |  | 115 | 0
A5090 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | DE.s: Secondary stack foundation | 2025-06-23 00:30 | 2025-09-20 23:30 |  |  | 89 | 0
A5100 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | DE.a/i: Secondary stack foundation | 2025-02-26 00:30 | 2025-10-08 23:30 |  |  | 221 | 0
A5110 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | BE.s: Dry ESP support foundation | 2025-04-25 00:30 | 2025-06-08 23:30 |  |  | 44 | 0
A5120 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | BE.a: Dry ESP support foundation | 2025-02-26 00:30 | 2025-06-22 23:30 |  |  | 115 | 0
A5130 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | DE.s: Dry ESP support foundation | 2025-06-23 00:30 | 2025-09-20 23:30 |  |  | 89 | 0
A5140 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | DE.a/i: Dry ESP support foundation | 2025-02-26 00:30 | 2025-10-08 23:30 |  |  | 221 | 0
A5150 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | BE.s: Foundation for dust disposal system | 2025-04-27 00:30 | 2025-06-10 23:30 |  |  | 44 | 0
A5160 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | BE.a: Foundation for dust disposal system | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A5170 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | DE.s: Foundation for dust disposal system | 2025-07-11 00:30 | 2025-09-21 23:30 |  |  | 72 | 0
A5180 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | DE.a/i: Foundation for dust disposal system | 2025-02-26 00:30 | 2025-10-09 23:30 |  |  | 222 | 0
A5190 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | BE.s: Duct support structure foundation | 2025-04-27 00:30 | 2025-06-25 23:30 |  |  | 59 | 0
A5200 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | BE.a: Duct support structure foundation | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A5210 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | DE.s: Duct support structure foundation | 2025-07-10 00:30 | 2025-10-07 23:30 |  |  | 88 | 0
A5220 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | DE.a/i: Duct support structure foundation | 2025-02-26 00:30 | 2025-10-26 23:30 |  |  | 238 | 0
A5230 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | BE.s: Cable rack foundations/trench/conduit banks | 2025-04-25 00:30 | 2025-06-23 23:30 |  |  | 59 | 0
A5240 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | BE.a: Cable rack foundations/trench/conduit banks | 2025-02-26 00:30 | 2025-07-07 23:30 |  |  | 130 | 0
A5250 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | DE.s: Cable rack foundations/trench/conduit banks | 2025-07-08 00:30 | 2026-01-03 23:30 |  |  | 176 | 0
A5260 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | DE.a/i: Cable rack foundations/trench/conduit banks | 2025-02-26 00:30 | 2026-01-17 23:30 |  |  | 320 | 0
A5270 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | BE.s: Cable support structures | 2025-04-27 00:30 | 2025-06-25 23:30 |  |  | 59 | 0
A5280 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | BE.a: Cable support structures | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A5290 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DE.s: Cable support structures | 2025-07-10 00:30 | 2025-10-07 23:30 |  |  | 88 | 0
A5300 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DE.a/i: Cable support structures | 2025-02-26 00:30 | 2025-10-26 23:30 |  |  | 238 | 0
A5310 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | MAN: Cable support structures | 2025-09-11 00:30 | 2026-03-04 23:30 |  |  | 172 | 0
A5320 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | INSP: Cable support structures | 2025-02-26 00:30 | 2026-03-18 23:30 |  |  | 380 | 0
A5330 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DCC.a: Cable support structures | 2025-02-26 00:30 | 2026-03-21 23:30 |  |  | 383 | 0
A5340 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DCC.r: Cable support structures | 2025-02-26 00:30 | 2026-03-25 23:30 |  |  | 387 | 0
A5350 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | LT: Cable support structures | 2025-02-26 00:30 | 2026-04-15 23:30 |  |  | 408 | 0
A5360 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | AoS: Cable support structures | 2025-02-26 00:30 | 2026-04-15 23:30 |  |  | 408 | 0
A5370 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | BE.s: HVAC | 2025-04-16 00:30 | 2025-06-15 23:30 |  |  | 60 | 0
A5380 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | BE.a: HVAC | 2025-02-26 00:30 | 2025-06-29 23:30 |  |  | 122 | 0
A5390 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DE.s: HVAC | 2025-08-29 00:30 | 2025-11-10 23:30 |  |  | 72 | 0
A5400 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DE.a/i: HVAC | 2025-02-26 00:30 | 2025-11-24 23:30 |  |  | 267 | 0
A5410 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | MAN: HVAC | 2025-11-01 00:30 | 2026-01-26 23:30 |  |  | 86 | 0
A5420 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | INSP: HVAC | 2025-02-26 00:30 | 2026-02-09 23:30 |  |  | 343 | 0
A5430 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DCC.a: HVAC | 2025-02-26 00:30 | 2026-02-12 23:30 |  |  | 346 | 0
A5440 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DCC.r: HVAC | 2025-02-26 00:30 | 2026-02-16 23:30 |  |  | 350 | 0
A5450 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | LT: HVAC | 2025-02-26 00:30 | 2026-03-09 23:30 |  |  | 371 | 0
A5460 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: Equipment for HVAC system excl. natural ventilation | 2025-06-26 00:30 | 2026-03-09 23:30 |  |  | 253 | 0
A5470 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: Power supply, electrical distribution and cabling for HVAC system | 2025-06-26 00:30 | 2026-03-09 23:30 |  |  | 253 | 0
A5480 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: FRP cooling tower pumps (1W+1S) | 2025-06-26 00:30 | 2026-03-09 23:30 |  |  | 253 | 0
A5490 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: FRP cooling tower (NW+NS) | 2025-06-26 00:30 | 2026-03-09 23:30 |  |  | 253 | 0
A5500 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | BE.s: Fire detection, fire fighting and fire protection systems | 2025-04-27 00:30 | 2025-06-10 23:30 |  |  | 44 | 0
A5510 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | BE.a: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A5520 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DE.s: Fire detection, fire fighting and fire protection systems | 2025-08-02 00:30 | 2025-10-15 23:30 |  |  | 73 | 0
A5530 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DE.a/i: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2025-11-03 23:30 |  |  | 246 | 0
A5540 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | MAN: Fire detection, fire fighting and fire protection systems | 2025-10-14 00:30 | 2026-02-27 23:30 |  |  | 135 | 0
A5550 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | INSP: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-13 23:30 |  |  | 375 | 0
A5560 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DCC.a: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-16 23:30 |  |  | 378 | 0
A5570 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DCC.r: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-20 23:30 |  |  | 382 | 0
A5580 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | LT: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-04-10 23:30 |  |  | 403 | 0
A5590 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire Protection System | 2025-06-28 00:30 | 2026-04-10 23:30 |  |  | 283 | 0
A5600 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire alarm systems | 2025-06-28 00:30 | 2026-04-10 23:30 |  |  | 283 | 0
A5610 | Not Started | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire-extinguishing systems and devices | 2025-06-28 00:30 | 2026-04-10 23:30 |  |  | 283 | 0
A2630 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Chain Conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2640 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Motor for conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2650 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2660 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.2 | AoS: Rotary valve | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A3030 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | AoS: Pug mill assembly | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A3020 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | LT: Pug mill assembly | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2980 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | MAN: Pug mill assembly | 2025-09-21 00:30 | 2026-02-05 23:30 |  |  | 135 | 0
A2990 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | INSP: Pug mill assembly | 2025-02-26 00:30 | 2026-02-19 23:30 |  |  | 353 | 0
A3000 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DCC.a: Pug mill assembly | 2025-02-26 00:30 | 2026-02-22 23:30 |  |  | 356 | 0
A3010 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DCC.r: Pug mill assembly | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A2940 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | BE.s: Pug mill assembly | 2025-04-28 00:30 | 2025-06-26 23:30 |  |  | 59 | 0
A2950 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | BE.a: Pug mill assembly | 2025-02-26 00:30 | 2025-07-10 23:30 |  |  | 133 | 0
A2960 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DE.s: Pug mill assembly | 2025-07-11 00:30 | 2025-10-08 23:30 |  |  | 88 | 0
A2970 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DE.a/i: Pug mill assembly | 2025-02-26 00:30 | 2025-10-27 23:30 |  |  | 239 | 0
A5620 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | BE.s: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-05-13 23:30 |  |  | 75 | 0
A5630 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | BE.a: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-05-27 23:30 |  |  | 89 | 0
A5640 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DE.s: HMI Hardware and System Software | 2025-10-06 00:30 | 2025-11-30 23:30 |  |  | 55 | 0
A5650 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DE.a/i: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-12-14 23:30 |  |  | 287 | 0
A5660 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | MAN: HMI Hardware and System Software | 2025-12-06 00:30 | 2026-02-13 23:30 |  |  | 69 | 0
A5670 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | INSP: HMI Hardware and System Software | 2026-02-14 00:30 | 2026-02-27 23:30 |  |  | 14 | 0
A5680 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DCC.a: HMI Hardware and System Software | 2026-02-28 00:30 | 2026-03-02 23:30 |  |  | 3 | 0
A5690 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DCC.r: HMI Hardware and System Software | 2026-03-03 00:30 | 2026-03-06 23:30 |  |  | 4 | 0
A5700 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | LT: HMI Hardware and System Software | 2025-02-26 00:30 | 2026-03-27 23:30 |  |  | 389 | 0
A5710 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at New ECR room for ESP - Hardware | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5720 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at New ECR room for ESP - System Software | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5730 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at Converter Control room - Hardware | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5740 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at Converter Control room - System Software | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5750 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: A4 B/W Laser Printer | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5760 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: Computer furniture (3 Computer table, 3 chairs , 1 Printer Table, 2 steel almirah) | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A5770 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | BE.s: Control Desks and Control Boxes | 2025-05-28 00:30 | 2025-07-10 23:30 |  |  | 44 | 0
A5780 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | BE.a: Control Desks and Control Boxes | 2025-02-26 00:30 | 2025-07-24 23:30 |  |  | 147 | 0
A5790 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DE.s: Control Desks and Control Boxes | 2025-09-02 00:30 | 2025-10-30 23:30 |  |  | 57 | 0
A5800 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DE.a/i: Control Desks and Control Boxes | 2025-02-26 00:30 | 2025-11-13 23:30 |  |  | 256 | 0
A5810 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | MAN: Control Desks and Control Boxes | 2025-11-03 00:30 | 2026-02-12 23:30 |  |  | 101 | 0
A5820 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | INSP: Control Desks and Control Boxes | 2026-02-13 00:30 | 2026-02-26 23:30 |  |  | 14 | 0
A5830 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DCC.a: Control Desks and Control Boxes | 2026-02-27 00:30 | 2026-03-01 23:30 |  |  | 3 | 0
A5840 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DCC.r: Control Desks and Control Boxes | 2026-03-02 00:30 | 2026-03-05 23:30 |  |  | 4 | 0
A5850 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | LT: Control Desks and Control Boxes | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A5860 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2.1.2.2.6.2.10 | AoS: Operator Desk at new ECR Building | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A5870 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2.1.2.2.6.2.10 | AoS: Local Control Boxes for ESP area | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A5880 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | BE.s: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-05-13 23:30 |  |  | 75 | 0
A5890 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | BE.a: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-05-27 23:30 |  |  | 89 | 0
A5900 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DE.s: PCS Hardware and System Software | 2025-07-05 00:30 | 2025-09-15 23:30 |  |  | 72 | 0
A5910 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DE.a/i: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-09-29 23:30 |  |  | 213 | 0
A5920 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | MAN: PCS Hardware and System Software | 2025-09-04 00:30 | 2026-02-17 23:30 |  |  | 164 | 0
A5930 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | INSP: PCS Hardware and System Software | 2026-02-18 00:30 | 2026-03-03 23:30 |  |  | 14 | 0
A5940 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DCC.a: PCS Hardware and System Software | 2026-03-04 00:30 | 2026-03-06 23:30 |  |  | 3 | 0
A5950 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DCC.r: PCS Hardware and System Software | 2026-03-07 00:30 | 2026-03-10 23:30 |  |  | 4 | 0
A5960 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | LT: PCS Hardware and System Software | 2025-02-26 00:30 | 2026-03-31 23:30 |  |  | 393 | 0
A5970 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: PLC (CPU) for ESP | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A5980 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: RIOs for ESP & ID Fans | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A5990 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Remote Ios for Doghouse & Dampers for Converters # 1 & 2 | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6000 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: RIO (with Panel AC) for Suction Damper of Mixer-II | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6010 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Laptop based Programming Station - Hardware | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6020 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Laptop based Programming Station - System Software | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6030 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: HMI development cum Engineering station at New ECR room for ESP - Hardware | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6040 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: HMI development cum Engineering station at New ECR room for ESP - System Software | 2026-04-01 00:30 | 2026-04-01 00:30 |  |  | 0 | 0
A6050 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | BE.s: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A6060 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | BE.a: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A6070 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DE.s: Electrical Field Devices, Sensors | 2025-08-02 00:30 | 2025-09-30 23:30 |  |  | 59 | 0
A6080 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DE.a/i: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-10-18 23:30 |  |  | 231 | 0
A6090 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | MAN: Electrical Field Devices, Sensors | 2025-10-05 00:30 | 2026-02-18 23:30 |  |  | 135 | 0
A6100 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | INSP: Electrical Field Devices, Sensors | 2026-02-19 00:30 | 2026-02-26 23:30 |  |  | 8 | 0
A6110 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DCC.a: Electrical Field Devices, Sensors | 2026-02-27 00:30 | 2026-03-01 23:30 |  |  | 3 | 0
A6120 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DCC.r: Electrical Field Devices, Sensors | 2026-03-02 00:30 | 2026-03-05 23:30 |  |  | 4 | 0
A6130 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | LT: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A6140 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4.1.2.2.6.4.10 | AoS: Electrical Field devices, Sensors for Seller supplied system | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6150 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | BE.s: Network | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A6160 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | BE.a: Network | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A6170 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DE.s: Network | 2025-09-02 00:30 | 2025-10-30 23:30 |  |  | 57 | 0
A6180 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DE.a/i: Network | 2025-02-26 00:30 | 2025-11-13 23:30 |  |  | 256 | 0
A6190 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | MAN: Network | 2025-11-03 00:30 | 2026-02-12 23:30 |  |  | 101 | 0
A6200 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | INSP: Network | 2026-02-13 00:30 | 2026-02-26 23:30 |  |  | 14 | 0
A6210 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DCC.a: Network | 2026-02-27 00:30 | 2026-03-01 23:30 |  |  | 3 | 0
A6220 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DCC.r: Network | 2026-03-02 00:30 | 2026-03-05 23:30 |  |  | 4 | 0
A6230 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | LT: Network | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A6240 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Switches (Layer 2) including accessories | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6250 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Switches (Layer 3) including accessories | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6260 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Hardware Firewall | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6270 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Components (Passive) | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6280 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | BE.s: HMI Functions | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A6290 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | BE.a: HMI Functions | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A6300 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DE.s: HMI Functions | 2025-08-18 00:30 | 2025-10-15 23:30 |  |  | 58 | 0
A6310 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DE.a/i: HMI Functions | 2025-02-26 00:30 | 2025-11-03 23:30 |  |  | 246 | 0
A6320 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | MAN: HMI Functions | 2025-10-19 00:30 | 2026-02-17 23:30 |  |  | 120 | 0
A6330 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | INSP: HMI Functions | 2026-02-18 00:30 | 2026-02-25 23:30 |  |  | 8 | 0
A6340 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DCC.a: HMI Functions | 2026-02-26 00:30 | 2026-02-28 23:30 |  |  | 3 | 0
A6350 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DCC.r: HMI Functions | 2026-03-01 00:30 | 2026-03-04 23:30 |  |  | 4 | 0
A6360 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | LT: HMI Functions | 2025-02-26 00:30 | 2026-03-25 23:30 |  |  | 387 | 0
A6370 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6.1.2.2.6.6.10 | AoS: HMI (Human Machine Interface) Application Software for Secondary Dedusting system | 2026-03-26 00:30 | 2026-03-26 00:30 |  |  | 0 | 0
A6380 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | BE.s: Process Control Functions | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A6390 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | BE.a: Process Control Functions | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A6400 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DE.s: Process Control Functions | 2025-07-11 00:30 | 2025-11-07 23:30 |  |  | 117 | 0
A6410 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DE.a/i: Process Control Functions | 2025-02-26 00:30 | 2025-11-21 23:30 |  |  | 264 | 0
A6420 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | MAN: Process Control Functions | 2025-11-22 00:30 | 2026-02-23 23:30 |  |  | 93 | 0
A6430 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | INSP: Process Control Functions | 2026-02-24 00:30 | 2026-03-09 23:30 |  |  | 14 | 0
A6440 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DCC.a: Process Control Functions | 2026-03-10 00:30 | 2026-03-12 23:30 |  |  | 3 | 0
A6450 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DCC.r: Process Control Functions | 2026-03-13 00:30 | 2026-03-16 23:30 |  |  | 4 | 0
A6460 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | LT: Process Control Functions | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A6470 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7.1.2.2.6.7.10 | AoS: Process Control Application Software for Secondary Dedusting system | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6480 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | BE.s: Instrumentation | 2025-02-26 00:30 | 2025-05-31 23:30 |  |  | 93 | 0
A6490 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | BE.a: Instrumentation | 2025-02-26 00:30 | 2025-06-14 23:30 |  |  | 107 | 0
A6500 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DE.s: Instrumentation | 2025-08-23 00:30 | 2025-10-20 23:30 |  |  | 58 | 0
A6510 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DE.a/i: Instrumentation | 2025-02-26 00:30 | 2025-11-08 23:30 |  |  | 251 | 0
A6520 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | MAN: Instrumentation | 2025-10-10 00:30 | 2026-02-08 23:30 |  |  | 120 | 0
A6530 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | INSP: Instrumentation | 2026-02-09 00:30 | 2026-02-16 23:30 |  |  | 8 | 0
A6540 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DCC.a: Instrumentation | 2026-02-17 00:30 | 2026-02-19 23:30 |  |  | 3 | 0
A6550 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DCC.r: Instrumentation | 2026-02-20 00:30 | 2026-02-23 23:30 |  |  | 4 | 0
A6560 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | LT: Instrumentation | 2025-02-26 00:30 | 2026-03-16 23:30 |  |  | 378 | 0
A6570 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8.1.2.2.6.8.10 | AoS: Instruments including accessories | 2026-03-17 00:30 | 2026-03-17 00:30 |  |  | 0 | 0
A6580 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | BE.s: Control Valves | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A6590 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | BE.a: Control Valves | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A6600 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DE.s: Control Valves | 2025-07-19 00:30 | 2025-09-01 23:30 |  |  | 44 | 0
A6610 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DE.a/i: Control Valves | 2025-02-26 00:30 | 2025-09-15 23:30 |  |  | 199 | 0
A6620 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | MAN: Control Valves | 2025-09-17 00:30 | 2026-02-13 23:30 |  |  | 147 | 0
A6630 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | INSP: Control Valves | 2026-02-14 00:30 | 2026-02-27 23:30 |  |  | 14 | 0
A6640 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DCC.a: Control Valves | 2026-02-28 00:30 | 2026-03-02 23:30 |  |  | 3 | 0
A6650 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DCC.r: Control Valves | 2026-03-03 00:30 | 2026-03-06 23:30 |  |  | 4 | 0
A6660 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | LT: Control Valves | 2025-02-26 00:30 | 2026-03-27 23:30 |  |  | 389 | 0
A6670 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9.1.2.2.6.9.10 | AoS: Control Valves | 2026-03-28 00:30 | 2026-03-28 00:30 |  |  | 0 | 0
A6680 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | BE.s: Analysis System | 2025-02-26 00:30 | 2025-06-01 23:30 |  |  | 94 | 0
A6690 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | BE.a: Analysis System | 2025-02-26 00:30 | 2025-06-15 23:30 |  |  | 108 | 0
A6700 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DE.s: Analysis System | 2025-07-24 00:30 | 2025-09-21 23:30 |  |  | 59 | 0
A6710 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DE.a/i: Analysis System | 2025-02-26 00:30 | 2025-10-09 23:30 |  |  | 222 | 0
A6720 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | MAN: Analysis System | 2025-10-05 00:30 | 2026-02-18 23:30 |  |  | 135 | 0
A6730 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | INSP: Analysis System | 2026-02-19 00:30 | 2026-02-26 23:30 |  |  | 8 | 0
A6740 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DCC.a: Analysis System | 2026-02-27 00:30 | 2026-03-01 23:30 |  |  | 3 | 0
A6750 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DCC.r: Analysis System | 2026-03-02 00:30 | 2026-03-05 23:30 |  |  | 4 | 0
A6760 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | LT: Analysis System | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A6770 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10.1.2.2.6.10.10 | AoS: Dust concentration measurement in Secondary dedusting stack (common for all units) | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6780 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | BE.s: Vibration Monitoring System | 2025-02-26 00:30 | 2025-06-01 23:30 |  |  | 94 | 0
A6790 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | BE.a: Vibration Monitoring System | 2025-02-26 00:30 | 2025-06-15 23:30 |  |  | 108 | 0
A6800 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DE.s: Vibration Monitoring System | 2025-07-24 00:30 | 2025-09-21 23:30 |  |  | 59 | 0
A6810 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DE.a/i: Vibration Monitoring System | 2025-02-26 00:30 | 2025-10-09 23:30 |  |  | 222 | 0
A6820 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | MAN: Vibration Monitoring System | 2025-10-05 00:30 | 2026-02-18 23:30 |  |  | 135 | 0
A6830 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | INSP: Vibration Monitoring System | 2026-02-19 00:30 | 2026-02-26 23:30 |  |  | 8 | 0
A6840 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DCC.a: Vibration Monitoring System | 2026-02-27 00:30 | 2026-03-01 23:30 |  |  | 3 | 0
A6850 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DCC.r: Vibration Monitoring System | 2026-03-02 00:30 | 2026-03-05 23:30 |  |  | 4 | 0
A6860 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | LT: Vibration Monitoring System | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A6870 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11.1.2.2.6.11.10 | AoS: Vibration Monitoring System for Secondary dedusting ID Fan | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6880 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11.1.2.2.6.11.10 | AoS: Vibration Monitoring System for Secondary dedusting ID Fan Motor | 2026-03-27 00:30 | 2026-03-27 00:30 |  |  | 0 | 0
A6890 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | BE.s: MV drives | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A6900 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | BE.a: MV drives | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A6910 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DE.s: MV drives | 2025-07-18 00:30 | 2025-09-15 23:30 |  |  | 59 | 0
A6920 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DE.a/i: MV drives | 2025-02-26 00:30 | 2025-09-29 23:30 |  |  | 213 | 0
A6930 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | MAN: MV drives | 2025-09-17 00:30 | 2026-02-14 23:30 |  |  | 148 | 0
A6940 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | INSP: MV drives | 2026-02-15 00:30 | 2026-02-28 23:30 |  |  | 14 | 0
A6950 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DCC.a: MV drives | 2026-03-01 00:30 | 2026-03-03 23:30 |  |  | 3 | 0
A6960 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DCC.r: MV drives | 2026-03-04 00:30 | 2026-03-07 23:30 |  |  | 4 | 0
A6970 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | LT: MV drives | 2025-02-26 00:30 | 2026-03-28 23:30 |  |  | 390 | 0
A6980 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1.1.2.2.6.12.1.10 | AoS: MV VVVF Drive for Secondary Deusting ID Fan | 2026-03-29 00:30 | 2026-03-29 00:30 |  |  | 0 | 0
A6990 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | BE.s: MV motors | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A7000 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | BE.a: MV motors | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A7010 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DE.s: MV motors | 2025-07-18 00:30 | 2025-09-15 23:30 |  |  | 59 | 0
A7020 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DE.a/i: MV motors | 2025-02-26 00:30 | 2025-09-29 23:30 |  |  | 213 | 0
A7030 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | MAN: MV motors | 2025-09-17 00:30 | 2026-02-14 23:30 |  |  | 148 | 0
A7040 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | INSP: MV motors | 2026-02-15 00:30 | 2026-02-28 23:30 |  |  | 14 | 0
A7050 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DCC.a: MV motors | 2026-03-01 00:30 | 2026-03-03 23:30 |  |  | 3 | 0
A7060 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DCC.r: MV motors | 2026-03-04 00:30 | 2026-03-07 23:30 |  |  | 4 | 0
A7070 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | LT: MV motors | 2025-02-26 00:30 | 2026-03-28 23:30 |  |  | 390 | 0
A7080 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2.1.2.2.6.12.2.10 | AoS: MV Motor for Secondary Deusting ID Fan | 2026-03-29 00:30 | 2026-03-29 00:30 |  |  | 0 | 0
A7090 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | BE.s: Variable speed motors | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A7100 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | BE.a: Variable speed motors | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A7110 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DE.s: Variable speed motors | 2025-07-18 00:30 | 2025-09-30 23:30 |  |  | 74 | 0
A7120 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DE.a/i: Variable speed motors | 2025-02-26 00:30 | 2025-10-18 23:30 |  |  | 231 | 0
A7130 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | MAN: Variable speed motors | 2025-09-18 00:30 | 2026-02-17 23:30 |  |  | 150 | 0
A7140 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | INSP: Variable speed motors | 2026-02-18 00:30 | 2026-02-25 23:30 |  |  | 8 | 0
A7150 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DCC.a: Variable speed motors | 2026-02-26 00:30 | 2026-02-28 23:30 |  |  | 3 | 0
A7160 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DCC.r: Variable speed motors | 2026-03-01 00:30 | 2026-03-04 23:30 |  |  | 4 | 0
A7170 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | LT: Variable speed motors | 2025-02-26 00:30 | 2026-03-25 23:30 |  |  | 387 | 0
A7180 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1.1.2.2.6.13.1.10 | AoS: Low Voltage Variable Speed Motors | 2026-03-26 00:30 | 2026-03-26 00:30 |  |  | 0 | 0
A7190 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | BE.s: Motor starter panels | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A7200 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | BE.a: Motor starter panels | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A7210 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DE.s: Motor starter panels | 2025-07-18 00:30 | 2025-09-15 23:30 |  |  | 59 | 0
A7220 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DE.a/i: Motor starter panels | 2025-02-26 00:30 | 2025-09-29 23:30 |  |  | 213 | 0
A7230 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | MAN: Motor starter panels | 2025-09-12 00:30 | 2026-01-23 23:30 |  |  | 131 | 0
A7240 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | INSP: Motor starter panels | 2026-01-24 00:30 | 2026-02-06 23:30 |  |  | 14 | 0
A7250 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DCC.a: Motor starter panels | 2026-02-07 00:30 | 2026-02-09 23:30 |  |  | 3 | 0
A7260 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DCC.r: Motor starter panels | 2026-02-10 00:30 | 2026-02-13 23:30 |  |  | 4 | 0
A7270 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | LT: Motor starter panels | 2025-02-26 00:30 | 2026-03-06 23:30 |  |  | 368 | 0
A7280 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: Motor Control Center (MCC) for ESP | 2026-03-07 00:30 | 2026-03-07 00:30 |  |  | 0 | 0
A7290 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: MCC for Doghouse & Dampers for Converters # 1 | 2026-03-07 00:30 | 2026-03-07 00:30 |  |  | 0 | 0
A7300 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: MCC for Doghouse & Dampers for Converters # 2 | 2026-03-07 00:30 | 2026-03-07 00:30 |  |  | 0 | 0
A7310 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: Standalone Soft-starter panel for MHS Booster Fan | 2026-03-07 00:30 | 2026-03-07 00:30 |  |  | 0 | 0
A7320 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | BE.s: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-05-11 23:30 |  |  | 73 | 0
A7330 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | BE.a: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-05-25 23:30 |  |  | 87 | 0
A7340 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DE.s: Medium Voltage Distribution Board | 2025-07-10 00:30 | 2025-09-07 23:30 |  |  | 59 | 0
A7350 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DE.a/i: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-09-21 23:30 |  |  | 205 | 0
A7360 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | MAN: Medium Voltage Distribution Board | 2025-09-03 00:30 | 2026-01-14 23:30 |  |  | 131 | 0
A7370 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | INSP: Medium Voltage Distribution Board | 2026-01-15 00:30 | 2026-01-28 23:30 |  |  | 14 | 0
A7380 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DCC.a: Medium Voltage Distribution Board | 2026-01-29 00:30 | 2026-01-31 23:30 |  |  | 3 | 0
A7390 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DCC.r: Medium Voltage Distribution Board | 2026-02-01 00:30 | 2026-02-04 23:30 |  |  | 4 | 0
A7400 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | LT: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2026-02-25 23:30 |  |  | 359 | 0
A7410 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: 11kV Isolator (VCB without protection), | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7420 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: Retrofitting job in existing 11 kV HT Boards at 15 RP | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7430 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: Retrofitting job in existing 11 kV HT Boards at MSDS-VI | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7440 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: One Laptop, licensed software along with communication cable for programming and testing the numerical relay. | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7450 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | BE.s: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-05-11 23:30 |  |  | 73 | 0
A7460 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | BE.a: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-05-25 23:30 |  |  | 87 | 0
A7470 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DE.s: Low Voltage Distribution (Load center) | 2025-07-10 00:30 | 2025-09-07 23:30 |  |  | 59 | 0
A7480 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DE.a/i: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-09-21 23:30 |  |  | 205 | 0
A7490 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | MAN: Low Voltage Distribution (Load center) | 2025-09-03 00:30 | 2026-01-14 23:30 |  |  | 131 | 0
A7500 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | INSP: Low Voltage Distribution (Load center) | 2026-01-15 00:30 | 2026-01-28 23:30 |  |  | 14 | 0
A7510 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DCC.a: Low Voltage Distribution (Load center) | 2026-01-29 00:30 | 2026-01-31 23:30 |  |  | 3 | 0
A7520 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DCC.r: Low Voltage Distribution (Load center) | 2026-02-01 00:30 | 2026-02-04 23:30 |  |  | 4 | 0
A7530 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | LT: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2026-02-25 23:30 |  |  | 359 | 0
A7540 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16.1.2.2.6.16.10 | AoS: Modification in existing 3x800A and 6x 630A feeders of LT Substation-1, if any | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7550 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16.1.2.2.6.16.10 | AoS: Power Distribution Board (PDB: Aux) | 2026-02-26 00:30 | 2026-02-26 00:30 |  |  | 0 | 0
A7560 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | BE.s: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A7570 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | BE.a: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A7580 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DE.s: Automation Power Supply Systems | 2025-08-02 00:30 | 2025-09-30 23:30 |  |  | 59 | 0
A7590 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DE.a/i: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-10-18 23:30 |  |  | 231 | 0
A7600 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | MAN: Automation Power Supply Systems | 2025-10-04 00:30 | 2026-02-02 23:30 |  |  | 120 | 0
A7610 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | INSP: Automation Power Supply Systems | 2026-02-03 00:30 | 2026-02-11 23:30 |  |  | 9 | 0
A7620 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DCC.a: Automation Power Supply Systems | 2026-02-12 00:30 | 2026-02-14 23:30 |  |  | 3 | 0
A7630 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DCC.r: Automation Power Supply Systems | 2026-02-15 00:30 | 2026-02-18 23:30 |  |  | 4 | 0
A7640 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | LT: Automation Power Supply Systems | 2025-02-26 00:30 | 2026-03-11 23:30 |  |  | 373 | 0
A7650 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17.1.2.2.6.17.10 | AoS: Uninterruptable Power Supply (UPS) & Main Distribution Board | 2026-03-12 00:30 | 2026-03-12 00:30 |  |  | 0 | 0
A7660 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17.1.2.2.6.17.10 | AoS: UPS Sub Distribution Board | 2026-03-12 00:30 | 2026-03-12 00:30 |  |  | 0 | 0
A7670 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | BE.s: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-05-24 23:30 |  |  | 86 | 0
A7680 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | BE.a: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-06-07 23:30 |  |  | 100 | 0
A7690 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DE.s: Power cables (HT&LT) | 2025-06-08 00:30 | 2025-10-10 23:30 |  |  | 123 | 0
A7700 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DE.a/i: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-10-29 23:30 |  |  | 241 | 0
A7710 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | MAN: Power cables (HT&LT) | 2025-08-09 00:30 | 2026-01-28 23:30 |  |  | 169 | 0
A7720 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | INSP: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-11 23:30 |  |  | 345 | 0
A7730 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DCC.a: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-14 23:30 |  |  | 348 | 0
A7740 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DCC.r: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-18 23:30 |  |  | 352 | 0
A7750 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | LT: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-03-11 23:30 |  |  | 373 | 0
A7760 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1.1.2.2.6.18.1.10 | AoS: Power cables (HT) | 2025-06-28 00:30 | 2026-03-11 23:30 |  |  | 253 | 0
A7770 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1.1.2.2.6.18.1.10 | AoS: Power cables (LT) | 2025-06-28 00:30 | 2026-03-11 23:30 |  |  | 253 | 0
A7780 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | BE.s: Other misc. cables | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A7790 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | BE.a: Other misc. cables | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A7800 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DE.s: Other misc. cables | 2025-07-30 00:30 | 2025-10-27 23:30 |  |  | 87 | 0
A7810 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DE.a/i: Other misc. cables | 2025-02-26 00:30 | 2025-11-10 23:30 |  |  | 253 | 0
A7820 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | MAN: Other misc. cables | 2025-09-29 00:30 | 2026-02-09 23:30 |  |  | 131 | 0
A7830 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | INSP: Other misc. cables | 2025-02-26 00:30 | 2026-02-23 23:30 |  |  | 357 | 0
A7840 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DCC.a: Other misc. cables | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A7850 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DCC.r: Other misc. cables | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A7860 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | LT: Other misc. cables | 2025-02-26 00:30 | 2026-03-23 23:30 |  |  | 385 | 0
A7870 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Control and Signal Cables | 2025-06-26 00:30 | 2026-03-23 23:30 |  |  | 267 | 0
A7880 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Automation & Networking Cable | 2025-06-26 00:30 | 2026-03-23 23:30 |  |  | 267 | 0
A7890 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Cables for ACVS, Illumination etc. | 2025-06-26 00:30 | 2026-03-23 23:30 |  |  | 267 | 0
A1750 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6.1.2.2.4.1.6.6 | AoS: Dog house door front side/ back side rail | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1690 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | MAN: Dog house unit (Converter-2) | 2025-11-20 00:30 | 2026-05-15 23:30 |  |  | 176 | 0
A1700 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | INSP: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-05-29 23:30 |  |  | 452 | 0
A1710 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | DCC.a: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-01 23:30 |  |  | 455 | 0
A1720 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | DCC.r: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-05 23:30 |  |  | 459 | 0
A1730 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | LT: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1740 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6.1.2.2.4.1.6.6 | AoS: Dog house unit | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1850 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | MAN: Dog house unit drive (Converter-2) | 2025-12-07 00:30 | 2026-04-12 23:30 |  |  | 126 | 0
A1860 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | INSP: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A1870 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | DCC.a: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-04-29 23:30 |  |  | 422 | 0
A1880 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | DCC.r: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-05-02 23:30 |  |  | 425 | 0
A1890 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | LT: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-05-23 23:30 |  |  | 446 | 0
A1910 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.8 | AoS: Dog house unit drive | 2026-05-24 00:30 | 2026-05-24 00:30 |  |  | 0 | 0
A2410 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Structure (for Weather Protection) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2330 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Rotary valve (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2340 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Expansion joints (at dust hoppers of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2350 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Dust hoppers (of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2360 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: HV Insulator system (of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2370 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Heating elements (for HV insulators of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2380 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Transformer rectifier (HFTR - 1 field, advance controller - all field) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2390 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Technological internals (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2400 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Weather protection over TR Bay | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2190 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | MAN: Square shape ESP unit (dry type) (Unit-2) | 2025-09-16 00:30 | 2026-04-08 23:30 |  |  | 202 | 0
A2200 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | INSP: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-22 23:30 |  |  | 415 | 0
A2210 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | DCC.a: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-25 23:30 |  |  | 418 | 0
A2220 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | DCC.r: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-29 23:30 |  |  | 422 | 0
A2230 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | LT: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2240 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Access (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2250 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Support structure (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2260 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Motorized Guillotine dampers (for inlet at each pass) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2270 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Motorized Guillotine dampers (for outlet at each pass) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2280 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Gas inlet and outlet cone (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2290 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Expansion joint (for duct of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2300 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Casing (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2310 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Heating elements (for dust hoppers of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A2320 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Manual slide gate (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 |  |  | 443 | 0
A3560 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6.1.2.2.4.10.6.6 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-05-22 23:30 |  |  | 327 | 0
A3570 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6.1.2.2.4.10.6.6 | AoS: ID fan | 2025-06-26 00:30 | 2026-05-22 23:30 |  |  | 327 | 0
A3440 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | MAN: ID fan station (Fan-2) | 2025-09-16 00:30 | 2026-02-09 23:30 |  |  | 144 | 0
A3450 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | INSP: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-02-23 23:30 |  |  | 357 | 0
A3460 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.a: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A3470 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.r: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A3480 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | LT: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-03-23 23:30 |  |  | 385 | 0
A3490 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.12 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-03-23 23:30 |  |  | 267 | 0
A3500 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.12 | AoS: ID fan | 2025-06-26 00:30 | 2026-03-23 23:30 |  |  | 267 | 0
A3510 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | MAN: ID fan station (Fan-3) | 2025-10-17 00:30 | 2026-04-10 23:30 |  |  | 174 | 0
A3520 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | INSP: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-04-24 23:30 |  |  | 417 | 0
A3530 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | DCC.a: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-04-27 23:30 |  |  | 420 | 0
A3540 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | DCC.r: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-05-01 23:30 |  |  | 424 | 0
A3550 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | LT: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-05-22 23:30 |  |  | 445 | 0
A3860 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of charging fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3850 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of charging fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3900 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of tapping fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3890 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of tapping fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A7900 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | BE.s: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-05-13 23:30 |  |  | 75 | 0
A7910 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | BE.a: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-05-27 23:30 |  |  | 89 | 0
A7920 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DE.s: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-08-11 00:30 | 2025-11-06 23:30 |  |  | 85 | 0
A7930 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DE.a/i: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-11-20 23:30 |  |  | 263 | 0
A7940 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | MAN: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-09-26 00:30 | 2026-01-20 23:30 |  |  | 114 | 0
A7950 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | INSP: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-03 23:30 |  |  | 337 | 0
A7960 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DCC.a: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-06 23:30 |  |  | 340 | 0
A7970 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DCC.r: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-10 23:30 |  |  | 344 | 0
A7980 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | LT: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-03-03 23:30 |  |  | 365 | 0
A7990 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | AoS: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-06-26 00:30 | 2026-03-03 23:30 |  |  | 247 | 0
A8000 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | BE.s: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A8010 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | BE.a: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A8020 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DE.s: Impulse tubes & fittings for Instruments | 2025-06-25 00:30 | 2025-08-23 23:30 |  |  | 59 | 0
A8030 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DE.a/i: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-09-06 23:30 |  |  | 190 | 0
A8040 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | MAN: Impulse tubes & fittings for Instruments | 2025-09-08 00:30 | 2026-01-04 23:30 |  |  | 116 | 0
A8050 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | INSP: Impulse tubes & fittings for Instruments | 2026-01-05 00:30 | 2026-01-18 23:30 |  |  | 14 | 0
A8060 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DCC.a: Impulse tubes & fittings for Instruments | 2026-01-19 00:30 | 2026-01-21 23:30 |  |  | 3 | 0
A8070 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DCC.r: Impulse tubes & fittings for Instruments | 2026-01-22 00:30 | 2026-01-25 23:30 |  |  | 4 | 0
A8080 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | LT: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2026-02-11 23:30 |  |  | 345 | 0
A8090 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | AoS: Impulse tubes & fittings for Instruments | 2026-02-12 00:30 | 2026-02-12 00:30 |  |  | 0 | 0
A8100 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | BE.s: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-05-11 23:30 |  |  | 73 | 0
A8110 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | BE.a: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-05-25 23:30 |  |  | 87 | 0
A8120 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DE.s: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-05-26 00:30 | 2025-10-23 23:30 |  |  | 148 | 0
A8130 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DE.a/i: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-11-06 23:30 |  |  | 249 | 0
A8140 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | MAN: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-07-10 00:30 | 2026-02-05 23:30 |  |  | 207 | 0
A8150 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | INSP: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-19 23:30 |  |  | 353 | 0
A8160 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DCC.a: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-22 23:30 |  |  | 356 | 0
A8170 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DCC.r: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A8180 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | LT: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A8190 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | AoS: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-06-26 00:30 | 2026-03-19 23:30 |  |  | 263 | 0
A8200 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | BE.s: Special tools | 2025-02-26 00:30 | 2025-07-10 23:30 |  |  | 133 | 0
A8210 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | BE.a: Special tools | 2025-02-26 00:30 | 2025-07-24 23:30 |  |  | 147 | 0
A8220 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DE.s: Special tools | 2025-10-19 00:30 | 2025-12-13 23:30 |  |  | 55 | 0
A8230 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DE.a/i: Special tools | 2025-02-26 00:30 | 2026-01-02 23:30 |  |  | 305 | 0
A8240 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | MAN: Special tools | 2026-01-03 00:30 | 2026-03-27 23:30 |  |  | 84 | 0
A8250 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | INSP: Special tools | 2026-03-28 00:30 | 2026-04-10 23:30 |  |  | 14 | 0
A8260 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DCC.a: Special tools | 2026-04-11 00:30 | 2026-04-13 23:30 |  |  | 3 | 0
A8270 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DCC.r: Special tools | 2026-04-14 00:30 | 2026-04-17 23:30 |  |  | 4 | 0
A8280 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | LT: Special tools | 2025-02-26 00:30 | 2026-05-08 23:30 |  |  | 431 | 0
A8290 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20.1.2.2.6.20.10 | AoS: Universal HART calibrator | 2026-05-09 00:30 | 2026-05-09 00:30 |  |  | 0 | 0
A8300 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | BE.s: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-06-10 23:30 |  |  | 103 | 0
A8310 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | BE.a: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-06-24 23:30 |  |  | 117 | 0
A8320 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DE.s: Lighting And Socket Systems incl. Cables | 2025-08-03 00:30 | 2025-10-01 23:30 |  |  | 59 | 0
A8330 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DE.a/i: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-10-19 23:30 |  |  | 232 | 0
A8340 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | MAN: Lighting And Socket Systems incl. Cables | 2025-09-19 00:30 | 2026-01-19 23:30 |  |  | 120 | 0
A8350 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | INSP: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-03 23:30 |  |  | 337 | 0
A8360 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DCC.a: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-06 23:30 |  |  | 340 | 0
A8370 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DCC.r: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-10 23:30 |  |  | 344 | 0
A8380 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | LT: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-03-03 23:30 |  |  | 365 | 0
A8390 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Room Lighting System | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8400 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Machine Lighting System | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8410 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Emergency Lighting Systems | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8420 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Outdoor/ Area Lighting Systems | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8430 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Standard Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8440 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Safety Extra-Low Voltage Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8450 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Welding Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8460 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Lighting Transformer | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8470 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: MLDB & SLDBs | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8480 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Welding Distribution Board (WDB) | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8490 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Aviation Lighting for Secondary Dedusting Stack | 2025-06-28 00:30 | 2026-03-03 23:30 |  |  | 245 | 0
A8500 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | BE.s: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2025-06-25 23:30 |  |  | 118 | 0
A8510 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | BE.a: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A8520 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DE.s: Industrial TV Systems (CCTV system) including cable | 2025-10-19 00:30 | 2025-12-15 23:30 |  |  | 57 | 0
A8530 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DE.a/i: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2026-01-04 23:30 |  |  | 307 | 0
A8540 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | MAN: Industrial TV Systems (CCTV system) including cable | 2025-12-06 00:30 | 2026-03-05 23:30 |  |  | 89 | 0
A8550 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | INSP: Industrial TV Systems (CCTV system) including cable | 2026-03-06 00:30 | 2026-03-13 23:30 |  |  | 8 | 0
A8560 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DCC.a: Industrial TV Systems (CCTV system) including cable | 2026-03-14 00:30 | 2026-03-16 23:30 |  |  | 3 | 0
A8570 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DCC.r: Industrial TV Systems (CCTV system) including cable | 2026-03-17 00:30 | 2026-03-20 23:30 |  |  | 4 | 0
A8580 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | LT: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2026-04-10 23:30 |  |  | 403 | 0
A8590 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | AoS: Industrial TV Systems (CCTV system) including cable | 2026-04-11 00:30 | 2026-04-11 00:30 |  |  | 0 | 0
A8600 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | BE.s: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2025-06-25 23:30 |  |  | 118 | 0
A8610 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | BE.a: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A8620 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DE.s: Plant Telephone Systems including cable | 2025-10-19 00:30 | 2025-12-15 23:30 |  |  | 57 | 0
A8630 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DE.a/i: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2026-01-04 23:30 |  |  | 307 | 0
A8640 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | MAN: Plant Telephone Systems including cable | 2025-12-06 00:30 | 2026-03-05 23:30 |  |  | 89 | 0
A8650 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | INSP: Plant Telephone Systems including cable | 2026-03-06 00:30 | 2026-03-13 23:30 |  |  | 8 | 0
A8660 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DCC.a: Plant Telephone Systems including cable | 2026-03-14 00:30 | 2026-03-16 23:30 |  |  | 3 | 0
A8670 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DCC.r: Plant Telephone Systems including cable | 2026-03-17 00:30 | 2026-03-20 23:30 |  |  | 4 | 0
A8680 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | LT: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2026-04-10 23:30 |  |  | 403 | 0
A8690 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | AoS: Plant Telephone Systems including cable | 2026-04-11 00:30 | 2026-04-11 00:30 |  |  | 0 | 0
A8700 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | BE.s: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-06-25 23:30 |  |  | 118 | 0
A8710 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | BE.a: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A8720 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DE.s: Power feeding of Heating-, Ventilation, Aircondition | 2025-08-30 00:30 | 2025-10-27 23:30 |  |  | 57 | 0
A8730 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DE.a/i: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-11-10 23:30 |  |  | 253 | 0
A8740 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | MAN: Power feeding of Heating-, Ventilation, Aircondition | 2025-10-15 00:30 | 2026-02-08 23:30 |  |  | 115 | 0
A8750 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | INSP: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-09 00:30 | 2026-02-22 23:30 |  |  | 14 | 0
A8760 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DCC.a: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-23 00:30 | 2026-02-25 23:30 |  |  | 3 | 0
A8770 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DCC.r: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-26 00:30 | 2026-03-01 23:30 |  |  | 4 | 0
A8780 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | LT: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2026-03-22 23:30 |  |  | 384 | 0
A8790 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | AoS: Power feeding of Heating-, Ventilation, Aircondition | 2026-03-23 00:30 | 2026-03-23 00:30 |  |  | 0 | 0
A8820 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Basic Engineering Submission | 2025-07-14 00:30 | 2025-07-14 00:30 |  |  | 0 | 0
A8830 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Basic Engineering Approval | 2025-07-28 00:30 | 2025-07-28 00:30 |  |  | 0 | 0
A8840 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Detailed Engineering Submission | 2026-02-13 00:30 | 2026-02-13 00:30 |  |  | 0 | 0
A8850 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Detailed Engineering Approval | 2026-03-04 00:30 | 2026-03-04 00:30 |  |  | 0 | 0
A8860 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Supply (Indigenous) | 2026-07-01 00:30 | 2026-07-01 00:30 |  |  | 0 | 0
A8870 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Supply (Perishable) | 2026-06-25 00:30 | 2026-06-25 00:30 |  |  | 0 | 0
A8880 | Not Started | BSL.1.3.1.2.3.1.2.3.1 | Construction power available | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A8890 | Not Started | BSL.1.3.1.2.3.1.2.3.1 | Construction water available | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A8900 | Not Started | BSL.1.3.1.2.3.1.2.3.1 | Drinking water available | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A8910 | Not Started | BSL.1.3.1.2.3.1.2.3.1 | Allocation of covered storage area | 2025-02-26 00:30 | 2025-06-25 23:30 |  |  | 118 | 0
A8920 | Not Started | BSL.1.3.1.2.3.1.2.3.1 | Space for Site office available | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A8930 | Not Started | BSL.1.3.1.2.3.1.2.3.2 | Permanent Power from Substation available | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A8940 | Not Started | BSL.1.3.1.2.3.1.2.3.2 | Make Up Water available at TOP (Flushing and Pressure Testing) | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A8950 | Not Started | BSL.1.3.1.2.3.1.2.3.2 | Availability of fire water for fire-fighting | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A8960 | Not Started | BSL.1.3.1.2.3.1.2.3.2 | Nitrogen available at TOP (For purging and instrumentation) | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A9010 | Not Started | BSL.1.3.1.2.3.1.2.3.4 | CW: Civil Works - Site mobilisation | 2025-02-26 00:30 | 2025-07-25 23:30 |  |  | 148 | 0
A9020 | Not Started | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Dry ESP, ID fan & clean gas stack foundations | 2025-07-26 00:30 | 2026-01-25 23:30 |  |  | 180 | 0
A9030 | Not Started | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Duct support structure foundation and other misc. foundations | 2025-03-29 00:30 | 2026-03-05 23:30 |  |  | 337 | 0
A9040 | Not Started | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Secondary ECR Building | 2025-08-31 00:30 | 2026-04-29 23:30 |  |  | 239 | 0
A9060 | Not Started | BSL.1.3.1.2.3.1.2.3.5 | ERE: Erection Works - Site mobilisation | 2025-02-26 00:30 | 2025-11-15 23:30 |  |  | 258 | 0
A9070 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Dry ESP (Pass # A) | 2025-11-16 00:30 | 2026-04-24 23:30 |  |  | 159 | 0
A9090 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary ID fan (Unit # 1) | 2026-03-24 00:30 | 2026-04-25 23:30 |  |  | 33 | 0
A9110 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Clean gas stack | 2025-11-16 00:30 | 2026-04-30 23:30 |  |  | 165 | 0
A9120 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Silo unit (incl. conveying) | 2025-11-21 00:30 | 2026-05-03 23:30 |  |  | 163 | 0
A9130 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary duct with support structure (Unit # 1) | 2025-11-18 00:30 | 2026-05-03 23:30 |  |  | 166 | 0
A9080 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Dry ESP (Pass # B) | 2025-11-21 00:30 | 2026-07-31 23:30 |  |  | 252 | 0
A9160 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Piping works (Unit # 1) | 2025-11-16 00:30 | 2026-05-26 23:30 |  |  | 191 | 0
A9180 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Pre-assembly works of dog house (Converter # 1) | 2025-11-16 00:30 | 2026-05-21 23:30 |  |  | 186 | 0
A9190 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Pre-assembly works of dog house (Converter # 2) | 2025-11-16 00:30 | 2026-08-22 23:30 |  |  | 279 | 0
A9150 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Other misc. works | 2025-11-19 00:30 | 2026-05-10 23:30 |  |  | 172 | 0
A9310 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ERE: Erection Works - Site mobilisation | 2025-02-26 00:30 | 2026-01-06 23:30 |  |  | 309 | 0
A9320 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ERE: Electrical and automation works of Unit # 1 | 2026-01-15 00:30 | 2026-04-30 23:30 |  |  | 106 | 0
A9340 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ERE: Electrical and automation works of Unit # 2 | 2026-01-07 00:30 | 2026-07-27 23:30 |  |  | 202 | 0
A9380 | Not Started | BSL.1.3.1.2.3.1.2.3.7 | Shutdown of converter # 1 for doghouse, charging and tapping duct erection (incl. mechanical, electrical and refractory | 2026-05-25 00:30 | 2026-06-26 23:30 |  |  | 33 | 0
A9440 | Not Started | BSL.1.3.1.2.3.1.2.3.9 | Shutdown of converter # 2 for doghouse, charging and tapping duct erection (incl. mechanical, electrical and refractory | 2026-08-31 00:30 | 2026-09-26 23:30 |  |  | 27 | 0
A9450 | Not Started | BSL.1.3.1.2.3.1.2.3.10 | Testing of equipment | 2026-05-03 00:30 | 2026-09-16 23:30 |  |  | 137 | 0
A9460 | Not Started | BSL.1.3.1.2.3.1.2.3.10 | Trial run of equipment | 2026-08-31 00:30 | 2026-10-02 23:30 |  |  | 33 | 0
A9470 | Not Started | BSL.1.3.1.2.3.1.2.3.10 | Hot commissioning (Unit-2) | 2026-10-03 00:30 | 2026-10-26 23:30 |  |  | 24 | 0
A9370 | Not Started | BSL.1.3.1.2.3.1.2.3.7 | Availiability of EOT crane for converter # 1 misc. shutdown activity | 2025-02-26 00:30 | 2026-05-24 23:30 |  |  | 447 | 0
A9430 | Not Started | BSL.1.3.1.2.3.1.2.3.9 | Availiability of EOT crane for converter # 2 misc. shutdown activity | 2025-02-26 00:30 | 2026-08-24 23:30 |  |  | 539 | 0
A8990 | Not Started | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Existing facilities (Major items- priority areas) | 2025-03-27 00:30 | 2025-05-28 17:01 |  |  | 62 | 0
A8970 | Not Started | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Site mobilisation | 2025-03-27 00:30 | 2025-03-27 00:30 |  |  | 0 | 0
A8980 | Not Started | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works: Clearance for dismantling & relocation of existing facilities | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A1430 | Not Started | BSL.1.1.2.2 | Testing of Equipment | 2025-02-26 00:30 | 2026-06-13 23:30 |  |  | 467 | 0
A9360 | Not Started | BSL.1.3.1.2.3.1.2.3.7 | Converter#1 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-05-24 23:30 |  |  | 447 | 0
A9420 | Not Started | BSL.1.3.1.2.3.1.2.3.9 | Converter#2 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-08-24 23:30 |  |  | 539 | 0
A1330 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Pre-assembly of Dog house before shutdown | 2025-02-26 00:30 | 2026-05-21 23:30 |  |  | 444 | 0
A1390 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Pre-assembly of Dog house before shutdown | 2025-02-26 00:30 | 2026-08-22 23:30 |  |  | 537 | 0
A9000 | Not Started | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Existing facilities (Non-priority areas & Doghouse) | 2025-05-28 17:01 | 2026-08-27 23:30 |  |  | 452 | 0
A9050 | Not Started | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Road & drain works | 2025-02-26 00:30 | 2026-07-26 23:30 |  |  | 510 | 0
A9490 | Completed | BSL.1.2 | Effective Date of Contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A9510 | Completed | BSL.1.2 | Kick off Meeting | 2025-03-18 00:30 | 2025-03-18 00:30 | 2025-03-18 08:00 | 2025-03-18 17:00 | 0 | 0
A9500 | Completed | BSL.1.2 | Signing of Contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A9520 | Completed | BSL.1.2 | PBG | 2025-03-28 00:30 | 2025-03-28 00:30 | 2025-03-13 08:00 | 2025-03-13 17:00 | 0 | 0
A9530 | Not Started | BSL.1.2 | Procurement Start | 2025-03-06 00:30 | 2025-03-25 23:30 |  |  | 19 | 0
A9540 | Not Started | BSL.1.2 | Completion of Procurement | 2026-06-29 06:30 | 2026-07-01 00:30 |  |  | 2 | 0
A9550 | Not Started | BSL.1.2 | Site Handover | 2025-03-27 00:30 | 2025-03-27 00:30 |  |  | 0 | 0
A9560 | Not Started | BSL.1.2 | Supply Start | 2025-10-18 00:30 | 2025-11-02 23:30 |  |  | 15 | 0
A9590 | Not Started | BSL.1.2 | Erection Completion | 2026-09-01 00:30 | 2026-09-01 00:30 |  |  | 0 | 0
A9600 | Not Started | BSL.1.2 | PAC | 2026-10-03 00:30 | 2026-10-03 00:30 |  |  | 0 | 0
A9610 | Not Started | BSL.1.2 | Commissioning |  | 2026-11-01 23:30 |  |  | 0 | 0
A9570 | Not Started | BSL.1.2 | Erection Start | 2025-11-22 00:30 | 2025-11-22 00:30 |  |  | 0 | 0
A9390 | Not Started | BSL.1.3.1.2.3.1.2.3.8 | Testing of equipment | 2026-05-03 00:30 | 2026-06-19 23:30 |  |  | 48 | 0
A9400 | Not Started | BSL.1.3.1.2.3.1.2.3.8 | Trial run of equipment | 2025-02-26 00:30 | 2026-07-02 23:30 |  |  | 486 | 0
A9410 | Not Started | BSL.1.3.1.2.3.1.2.3.8 | Hot commissioning (unit-1) | 2026-07-03 00:30 | 2026-07-03 00:30 |  |  | 0 | 0
A9100 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary ID fan (Unit # 2) | 2026-05-23 00:30 | 2026-07-23 23:30 |  |  | 62 | 0
A9140 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary duct with support structure (Unit # 2) | 2025-11-16 00:30 | 2026-07-27 23:30 |  |  | 253 | 0
A1500 | Not Started | BSL.1.1.2.5 | Testing of Equipment | 2025-02-26 00:30 | 2026-09-10 23:30 |  |  | 556 | 0
A1520 | Not Started | BSL.1.1.2.5 | Commissioning of Secondary emission control system (Unit-2) | 2026-09-27 00:30 | 2026-10-26 23:30 |  |  | 30 | 0
A1530 | Not Started | BSL.1.1.2.5 | Completion of Secondary emission control system (Unit-2) | 2026-10-27 00:30 | 2026-10-27 00:30 |  |  | 0 | 0
A1440 | Not Started | BSL.1.1.2.2 | Trial Run of Equipment | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1510 | Not Started | BSL.1.1.2.5 | Trial Run of Equipment | 2025-02-26 00:30 | 2026-09-26 23:30 |  |  | 572 | 0
A1250 | Not Started | BSL.1.1.2.6 | Dismantling of existing facilities (Non-priority areas & Doghouse) | 2025-07-26 11:30 | 2026-07-26 23:30 |  |  | 362 | 0
A1340 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of ESP # 2 | 2026-01-28 00:30 | 2026-08-24 23:30 |  |  | 209 | 0
A9170 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Piping works (Unit # 2) | 2025-11-21 00:30 | 2026-07-31 23:30 |  |  | 252 | 0
A9200 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Dry ESP (Pass # A) | 2025-02-26 00:30 | 2026-05-24 23:30 |  |  | 447 | 0
A9210 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Dry ESP (Pass # B) | 2025-02-26 00:30 | 2026-08-30 23:30 |  |  | 545 | 0
A9220 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary ID fan (Unit # 1) | 2025-02-26 00:30 | 2026-05-25 23:30 |  |  | 448 | 0
A9230 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary ID fan (Unit # 2) | 2025-02-26 00:30 | 2026-08-22 23:30 |  |  | 537 | 0
A9240 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Clean gas stack | 2025-02-26 00:30 | 2026-05-30 23:30 |  |  | 453 | 0
A9250 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Silo unit (incl. conveying) | 2025-02-26 00:30 | 2026-06-02 23:30 |  |  | 456 | 0
A9260 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary duct with support structure (Unit # 1) | 2025-02-26 00:30 | 2026-06-05 23:30 |  |  | 459 | 0
A9270 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary duct with support structure (Unit # 2) | 2025-02-26 00:30 | 2026-08-26 23:30 |  |  | 541 | 0
A9280 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Other misc. works | 2025-02-26 00:30 | 2026-06-11 23:30 |  |  | 465 | 0
A9290 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Piping works (Unit # 1) | 2025-02-26 00:30 | 2026-06-16 23:30 |  |  | 470 | 0
A9300 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Piping works (Unit # 2) | 2025-02-26 00:30 | 2026-08-30 23:30 |  |  | 545 | 0
A9330 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ALN: Electrical and automation works of Unit # 1 | 2025-02-26 00:30 | 2026-05-30 23:30 |  |  | 453 | 0
A9350 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ALN: Electrical and automation works of Unit # 2 | 2025-02-26 00:30 | 2026-08-26 23:30 |  |  | 541 | 0
A1560 | Not Started | BSL.1.3.1.2.2 | Layout submission | 2025-03-22 00:30 | 2025-04-01 23:30 |  |  | 11 | 0
A1570 | Not Started | BSL.1.3.1.2.2 | Approval of Layout | 2025-04-02 00:30 | 2025-04-15 23:30 |  |  | 14 | 0
A9580 | Not Started | BSL.1.2 | Supply Finish | 2026-06-29 06:30 | 2026-07-01 00:30 |  |  | 2 | 0
A8800 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.24 | DE.s: Functional Description - Secondary dedusting | 2025-02-26 00:30 | 2026-01-31 23:30 |  |  | 334 | 0
A8810 | Not Started | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.24 | DE.a/i: Functional Description - Secondary dedusting | 2025-02-26 00:30 | 2026-02-14 23:30 |  |  | 348 | 0
A4690 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.18 | DE.s: Operation & Maintenance manual | 2025-02-26 00:30 | 2026-02-12 23:30 |  |  | 346 | 0
A4700 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.18 | DE.a/i: Operation & Maintenance manual | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A1010 | Completed | BSL.1.1 | Effective date of contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A1200 | Not Started | BSL.1.1.2.1 | Work Front Handover including Construction power & water | 2025-03-27 00:30 | 2025-03-27 00:30 |  |  | 0 | 0
A1180 | Not Started | BSL.1.1.2.1 | Allocation of Work Front Office Area | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A1190 | Not Started | BSL.1.1.2.1 | Allocation of Covered Storage Area | 2025-02-26 00:30 | 2025-06-25 23:30 |  |  | 118 | 0
A1240 | Not Started | BSL.1.1.2.6 | Dismantling of existing facilities (Major items- priority areas) | 2025-03-27 00:30 | 2025-07-26 11:30 |  |  | 120 | 0
A1450 | Not Started | BSL.1.1.2.2 | Commissioning of Secondary emission control system (Unit-1) | 2026-06-27 00:30 | 2026-06-29 23:30 |  |  | 3 | 0
A1460 | Not Started | BSL.1.1.2.2 | Completion of Secondary emission control system (Unit-1) | 2026-06-30 00:30 | 2026-06-30 00:30 |  |  | 0 | 0
A1000 | Completed | BSL.1.1 | Signing of Contract | 2025-02-26 00:30 |  | 2025-02-26 08:00 |  | 0 | 0
A1020 | Completed | BSL.1.1 | Kick Off Meeting (Flowsheet, Layout Approval, technical Specification of Fan & ESP, ECR building heat load, Construction | 2025-03-18 00:30 | 2025-03-21 23:30 | 2025-03-18 08:00 | 2025-03-18 17:00 | 4 | 0
A1030 | Not Started | BSL.1.1.1.2 | Basic Engineering - Mechanical & Electrical | 2025-02-26 00:30 | 2025-07-12 23:30 |  |  | 135 | 0
A1040 | Not Started | BSL.1.1.1.2 | Basic Engineering Approval - Mechanical & Electrical | 2025-02-26 00:30 | 2025-07-26 23:30 |  |  | 149 | 0
A1070 | Not Started | BSL.1.1.1.3 | Detail Engineering - Mechanical & Electrical | 2025-04-25 00:30 | 2026-02-12 23:30 |  |  | 289 | 0
A1080 | Not Started | BSL.1.1.1.3 | Detail Engineering Approval - Mechanical & Electrical | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A1140 | Not Started | BSL.1.1.3.1.1 | Dog House#2 | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1150 | Not Started | BSL.1.1.3.1.1 | ESP # 2 & Fan # 3 | 2025-03-26 00:30 | 2026-05-14 23:30 |  |  | 410 | 0
A1210 | Not Started | BSL.1.1.2.1 | Handover of project office building and associated facilities | 2025-04-27 00:30 | 2025-04-27 00:30 |  |  | 0 | 0
A1230 | Not Started | BSL.1.1.2 | Site mobilisation | 2025-02-26 00:30 | 2025-03-26 23:30 |  |  | 28 | 0
A1260 | Not Started | BSL.1.1.2 | Civil & structural Work | 2025-06-27 00:30 | 2026-07-26 23:30 |  |  | 391 | 0
A1050 | Not Started | BSL.1.1.1.2 | Basic Engineering - Civil | 2025-02-26 00:30 | 2025-07-12 23:30 |  |  | 135 | 0
A1060 | Not Started | BSL.1.1.1.2 | Basic Engineering - Approval Civil | 2025-02-26 00:30 | 2025-07-26 23:30 |  |  | 149 | 0
A1090 | Not Started | BSL.1.1.1.3 | Detail Engineering - Civil | 2025-05-27 00:30 | 2026-02-12 23:30 |  |  | 258 | 0
A1100 | Not Started | BSL.1.1.3.2.1 | Dog House#1 | 2025-04-30 00:30 | 2026-05-01 23:30 |  |  | 362 | 0
A1110 | Not Started | BSL.1.1.3.2.1 | ESP # 1, Fan # 1 & Fan # 2 | 2025-03-26 00:30 | 2026-03-01 23:30 |  |  | 336 | 0
A1120 | Not Started | BSL.1.1.3.2.1 | Secondary Ducts & Duct Support Structure | 2025-02-26 00:30 | 2026-04-26 23:30 |  |  | 419 | 0
A1130 | Not Started | BSL.1.1.3.2 | Electrical Items | 2025-05-26 00:30 | 2026-05-08 23:30 |  |  | 344 | 0
A1160 | Not Started | BSL.1.1.3.1.1 | Secondary Ducts & Duct Support Structure | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A1170 | Not Started | BSL.1.1.3 | Electrical Items | 2025-05-26 00:30 | 2026-05-08 23:30 |  |  | 344 | 0
A1270 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of ESP # 1 | 2025-10-30 00:30 | 2026-05-24 23:30 |  |  | 206 | 0
A1280 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Stack | 2025-09-28 00:30 | 2026-05-30 23:30 |  |  | 242 | 0
A1290 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Fan # 1 & Fan # 2 | 2025-10-29 00:30 | 2026-05-25 23:30 |  |  | 208 | 0
A1300 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Ducts & Support Structure (Inside & Outside Bldg.) | 2025-12-30 00:30 | 2026-05-30 23:30 |  |  | 152 | 0
A1310 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Electrical Items | 2026-01-14 00:30 | 2026-05-30 23:30 |  |  | 137 | 0
A1320 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Balance items | 2026-02-09 00:30 | 2026-05-22 23:30 |  |  | 103 | 0
A1400 | Not Started | BSL.1.1.2.3 | Converter#1 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-05-24 23:30 |  |  | 447 | 0
A1410 | Not Started | BSL.1.1.2.3 | Availability of EOT Crane | 2025-02-26 00:30 | 2026-05-24 23:30 |  |  | 447 | 0
A1420 | Not Started | BSL.1.1.2.3 | Converter#1 - Shutdown Work (Dismantling of existing dog house, installation of new dog house with hoods, refractory lin | 2026-05-25 00:30 | 2026-06-26 23:30 |  |  | 33 | 0
A1350 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Fan # 3 | 2025-11-28 00:30 | 2026-08-22 23:30 |  |  | 267 | 0
A1360 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Ducts & Support Structure (Inside & Outside Bldg.) | 2025-11-02 00:30 | 2026-08-26 23:30 |  |  | 297 | 0
A1370 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Electrical Items | 2026-06-01 00:30 | 2026-08-26 23:30 |  |  | 87 | 0
A1380 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Balance items | 2025-12-28 00:30 | 2026-08-26 23:30 |  |  | 242 | 0
A1470 | Not Started | BSL.1.1.2.4 | Converter#2 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-08-24 23:30 |  |  | 539 | 0
A1480 | Not Started | BSL.1.1.2.4 | Availability of EOT Crane | 2025-02-26 00:30 | 2026-08-24 23:30 |  |  | 539 | 0
A1490 | Not Started | BSL.1.1.2.4 | Converter#2 - Shutdown Work (Dismantling of existing dog house, installation of new dog house with hoods, refractory lin | 2026-08-25 00:30 | 2026-09-26 23:30 |  |  | 33 | 0
A1220 | Not Started | BSL.1.1.2.1 | Availability of permanent power & utilities | 2026-05-09 00:30 | 2026-05-09 00:30 |  |  | 0 | 0
A1540 | Completed | BSL.1.3 | Effective date of contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A1550 | Not Started | BSL.1.3.1.2.2 | Kick Off Meeting (Flowsheet, technical Specification of Fan & ESP, ECR building heat load, Construction vendor approval) | 2025-02-26 00:30 | 2025-03-21 23:30 |  |  | 23 | 0
A1580 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | BE.s: Dog house unit | 2025-04-16 00:30 | 2025-06-25 23:30 |  |  | 70 | 0
A1590 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | BE.a: Dog house unit | 2025-02-26 00:30 | 2025-07-09 23:30 |  |  | 132 | 0
A1600 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | DE.s: Dog house unit | 2025-07-10 00:30 | 2025-11-26 23:30 |  |  | 137 | 0
A1610 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | DE.a/i: Dog house unit | 2025-02-26 00:30 | 2025-12-10 23:30 |  |  | 283 | 0
A1620 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | MAN: Dog house unit (Converter-1) | 2025-09-23 00:30 | 2026-03-20 23:30 |  |  | 176 | 0
A1630 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | INSP: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A1640 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | DCC.a: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-06 23:30 |  |  | 399 | 0
A1650 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | DCC.r: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-10 23:30 |  |  | 403 | 0
A1660 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | LT: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-05-01 23:30 |  |  | 424 | 0
A1670 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5.1.2.2.4.1.5.6 | AoS: Dog house unit | 2025-02-26 00:30 | 2026-05-01 23:30 |  |  | 424 | 0
A1680 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5.1.2.2.4.1.5.6 | AoS: Dog house door front side/ back side rail | 2025-02-26 00:30 | 2026-05-01 23:30 |  |  | 424 | 0
A1920 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | BE.s: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-04-16 23:30 |  |  | 49 | 0
A1930 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | BE.a: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-04-30 23:30 |  |  | 63 | 0
A1940 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | DE.s: Square shape ESP unit (dry type) | 2025-05-02 00:30 | 2025-09-22 23:30 |  |  | 143 | 0
A1950 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | DE.a/i: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-10-10 23:30 |  |  | 223 | 0
A1960 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | MAN: Square shape ESP unit (dry type) (Unit-1) | 2025-07-03 00:30 | 2026-01-24 23:30 |  |  | 202 | 0
A1970 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | INSP: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-07 23:30 |  |  | 341 | 0
A1980 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | DCC.a: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-10 23:30 |  |  | 344 | 0
A1990 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | DCC.r: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-14 23:30 |  |  | 348 | 0
A2000 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | LT: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2010 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Access (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2020 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Support structure (for ESP) | 2025-03-07 00:30 | 2026-02-09 23:30 |  |  | 334 | 0
A2030 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Motorized Guillotine dampers (for inlet at each pass) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2040 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Motorized Guillotine dampers (for outlet at each pass) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2050 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Gas inlet and outlet cone (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2060 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Expansion joint (for duct of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2070 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Casing (for ESP) | 2025-03-28 00:30 | 2026-03-01 23:30 |  |  | 334 | 0
A2080 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Heating elements (for dust hoppers of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2090 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Manual slide gate (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2100 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Rotary valve (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2110 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Expansion joints (at dust hoppers of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2120 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Dust hoppers (of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2130 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: HV Insulator system (of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2140 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Heating elements (for HV insulators of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2150 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Transformer rectifier (HFTR - 1 field, advance controller - all field) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2160 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Technological internals (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2170 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Weather protection over TR Bay | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2180 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Structure (for Weather Protection) | 2025-02-26 00:30 | 2026-03-07 23:30 |  |  | 369 | 0
A2420 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | BE.s: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-04-26 23:30 |  |  | 59 | 0
A2430 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | BE.a: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-05-12 23:30 |  |  | 74 | 0
A2440 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DE.s: Steel part of clean gas stack | 2025-05-13 00:30 | 2025-10-07 23:30 |  |  | 146 | 0
A2450 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DE.a/i: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-10-26 23:30 |  |  | 238 | 0
A2460 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | MAN: Steel part of clean gas stack | 2025-07-11 00:30 | 2026-01-26 23:30 |  |  | 196 | 0
A2470 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | INSP: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-09 23:30 |  |  | 343 | 0
A2480 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DCC.a: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-12 23:30 |  |  | 346 | 0
A2490 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DCC.r: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-16 23:30 |  |  | 350 | 0
A2500 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | LT: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-03-09 23:30 |  |  | 371 | 0
A2510 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Shell for clean gas stack | 2025-02-26 00:30 | 2026-03-09 23:30 |  |  | 371 | 0
A2520 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Built in parts | 2025-04-14 00:30 | 2026-03-03 23:30 |  |  | 319 | 0
A2530 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Access platforms, stairs, ladders | 2025-04-14 00:30 | 2026-03-03 23:30 |  |  | 319 | 0
A2540 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | BE.s: Mechanical silo filling | 2025-02-26 00:30 | 2025-05-26 23:30 |  |  | 88 | 0
A2550 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | BE.a: Mechanical silo filling | 2025-02-26 00:30 | 2025-06-09 23:30 |  |  | 102 | 0
A2560 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DE.s: Mechanical silo filling | 2025-06-26 00:30 | 2025-09-21 23:30 |  |  | 87 | 0
A2570 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DE.a/i: Mechanical silo filling | 2025-02-26 00:30 | 2025-10-09 23:30 |  |  | 222 | 0
A2580 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | MAN: Mechanical silo filling | 2025-08-20 00:30 | 2026-01-19 23:30 |  |  | 150 | 0
A2590 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | INSP: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-02 23:30 |  |  | 336 | 0
A2600 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DCC.a: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-05 23:30 |  |  | 339 | 0
A2610 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DCC.r: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-09 23:30 |  |  | 343 | 0
A2620 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | LT: Mechanical silo filling | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2690 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2680 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2670 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Cross Chain Conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2720 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2710 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2700 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Bucket Elevator | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2730 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Screw conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2740 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2750 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 |  |  | 364 | 0
A2760 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | BE.s: Silo unit | 2025-04-28 00:30 | 2025-06-26 23:30 |  |  | 59 | 0
A2770 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | BE.a: Silo unit | 2025-02-26 00:30 | 2025-07-10 23:30 |  |  | 133 | 0
A2780 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DE.s: Silo unit | 2025-07-11 00:30 | 2025-10-08 23:30 |  |  | 88 | 0
A2790 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DE.a/i: Silo unit | 2025-02-26 00:30 | 2025-10-27 23:30 |  |  | 239 | 0
A2800 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | MAN: Silo unit | 2025-09-21 00:30 | 2026-02-05 23:30 |  |  | 135 | 0
A2810 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | INSP: Silo unit | 2025-02-26 00:30 | 2026-02-19 23:30 |  |  | 353 | 0
A2820 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DCC.a: Silo unit | 2025-02-26 00:30 | 2026-02-22 23:30 |  |  | 356 | 0
A2830 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DCC.r: Silo unit | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A2840 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | LT: Silo unit | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2850 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Shell for dust silo | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2860 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2870 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Access platforms, stairs, ladders | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2880 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.2 | AoS: Silo top filter unit | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2890 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.3 | AoS: Manual slide gate for main dust outlet | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2900 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS:Nozzles for fluidisation unit | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2910 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS: Equipment attached piping | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2920 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS: Solenoid valve for fluidisation unit | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A2930 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.5 | AoS: Rotary valve | 2025-02-26 00:30 | 2026-03-19 23:30 |  |  | 381 | 0
A3040 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | BE.s: Expansion joint | 2025-02-26 00:30 | 2025-05-28 23:30 |  |  | 90 | 0
A3050 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | BE.a: Expansion joint | 2025-02-26 00:30 | 2025-06-11 23:30 |  |  | 104 | 0
A3060 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DE.s: Expansion joint | 2025-07-13 00:30 | 2025-10-08 23:30 |  |  | 86 | 0
A3070 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DE.a/i: Expansion joint | 2025-02-26 00:30 | 2025-10-27 23:30 |  |  | 239 | 0
A3080 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | MAN: Expansion joint | 2025-09-11 00:30 | 2026-02-20 23:30 |  |  | 160 | 0
A3090 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | INSP: Expansion joint | 2025-02-26 00:30 | 2026-03-06 23:30 |  |  | 368 | 0
A3100 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DCC.a: Expansion joint | 2025-02-26 00:30 | 2026-03-09 23:30 |  |  | 371 | 0
A3110 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DCC.r: Expansion joint | 2025-02-26 00:30 | 2026-03-13 23:30 |  |  | 375 | 0
A3120 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | LT: Expansion joint | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3130 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3140 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3150 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of charging fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3160 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of tapping fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3170 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Raw gas collection duct | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3180 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Expansion joints for ID fan inlet (double inlet) | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3190 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Expansion joints for ID fan outlet | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3200 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | BE.s: Damper with actuator | 2025-02-26 00:30 | 2025-05-28 23:30 |  |  | 90 | 0
A3210 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | BE.a: Damper with actuator | 2025-02-26 00:30 | 2025-06-11 23:30 |  |  | 104 | 0
A3220 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DE.s: Damper with actuator | 2025-07-13 00:30 | 2025-10-08 23:30 |  |  | 86 | 0
A3230 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DE.a/i: Damper with actuator | 2025-02-26 00:30 | 2025-10-27 23:30 |  |  | 239 | 0
A3240 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | MAN: Damper with actuator | 2025-09-11 00:30 | 2026-02-20 23:30 |  |  | 160 | 0
A3250 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | INSP: Damper with actuator | 2025-02-26 00:30 | 2026-03-06 23:30 |  |  | 368 | 0
A3260 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DCC.a: Damper with actuator | 2025-02-26 00:30 | 2026-03-09 23:30 |  |  | 371 | 0
A3270 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DCC.r: Damper with actuator | 2025-02-26 00:30 | 2026-03-13 23:30 |  |  | 375 | 0
A3280 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | LT: Damper with actuator | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3290 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3300 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3310 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of charging fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3320 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of tapping fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 |  |  | 396 | 0
A3330 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | BE.s: ID fan station | 2025-02-26 00:30 | 2025-04-21 23:30 |  |  | 54 | 0
A3340 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | BE.a: ID fan station | 2025-02-26 00:30 | 2025-05-07 23:30 |  |  | 69 | 0
A3350 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | DE.s: ID fan station | 2025-06-03 00:30 | 2025-08-29 23:30 |  |  | 87 | 0
A3360 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | DE.a/i: ID fan station | 2025-02-26 00:30 | 2025-09-12 23:30 |  |  | 196 | 0
A3370 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | MAN: ID fan station (Fan-1) | 2025-08-17 00:30 | 2026-01-10 23:30 |  |  | 144 | 0
A3380 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | INSP: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-24 23:30 |  |  | 327 | 0
A3390 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.a: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-27 23:30 |  |  | 330 | 0
A3400 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.r: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-31 23:30 |  |  | 334 | 0
A3410 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | LT: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-02-21 23:30 |  |  | 355 | 0
A3420 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.6 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-02-21 23:30 |  |  | 237 | 0
A3430 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.6 | AoS: ID fan | 2025-06-26 00:30 | 2026-02-21 23:30 |  |  | 237 | 0
A3580 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | BE.s: MHS booster fan | 2025-02-26 00:30 | 2025-06-17 23:30 |  |  | 110 | 0
A3590 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | BE.a: MHS booster fan | 2025-02-26 00:30 | 2025-07-01 23:30 |  |  | 124 | 0
A3600 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DE.s: MHS booster fan | 2025-08-02 00:30 | 2025-09-28 23:30 |  |  | 57 | 0
A3610 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DE.a/i: MHS booster fan | 2025-02-26 00:30 | 2025-10-16 23:30 |  |  | 229 | 0
A3620 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | MAN: MHS booster fan | 2025-10-01 00:30 | 2026-02-19 23:30 |  |  | 139 | 0
A3630 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | INSP: MHS booster fan | 2025-02-26 00:30 | 2026-03-05 23:30 |  |  | 367 | 0
A3640 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DCC.a: MHS booster fan | 2025-02-26 00:30 | 2026-03-08 23:30 |  |  | 370 | 0
A3650 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DCC.r: MHS booster fan | 2025-02-26 00:30 | 2026-03-11 23:30 |  |  | 373 | 0
A3660 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | LT: MHS booster fan | 2025-02-26 00:30 | 2026-04-01 23:30 |  |  | 394 | 0
A3670 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Control damper for booster fan inlet | 2026-04-02 00:30 | 2026-04-02 00:30 |  |  | 0 | 0
A3680 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Raw gas booster fan | 2026-04-02 00:30 | 2026-04-02 00:30 |  |  | 0 | 0
A3690 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Damper for booster fan outlet | 2026-04-02 00:30 | 2026-04-02 00:30 |  |  | 0 | 0
A3700 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | BE.s: Secondary ducts | 2025-04-16 00:30 | 2025-06-08 23:30 |  |  | 53 | 0
A3710 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | BE.a: Secondary ducts | 2025-02-26 00:30 | 2025-06-22 23:30 |  |  | 115 | 0
A3720 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DE.s: Secondary ducts | 2025-06-23 00:30 | 2025-11-04 23:30 |  |  | 132 | 0
A3730 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DE.a/i: Secondary ducts | 2025-02-26 00:30 | 2025-11-18 23:30 |  |  | 261 | 0
A3740 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | MAN: Secondary ducts | 2025-08-23 00:30 | 2026-04-15 23:30 |  |  | 233 | 0
A3750 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | INSP: Secondary ducts | 2025-02-26 00:30 | 2026-04-29 23:30 |  |  | 422 | 0
A3760 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DCC.a: Secondary ducts | 2025-02-26 00:30 | 2026-05-02 23:30 |  |  | 425 | 0
A3770 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DCC.r: Secondary ducts | 2025-02-26 00:30 | 2026-05-06 23:30 |  |  | 429 | 0
A3780 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | LT: Secondary ducts | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3790 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of material handling fume suction | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3800 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of material handling suction for BOF | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3810 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3820 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3830 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of charging fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 |  |  | 375 | 0
A3840 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of charging fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 |  |  | 375 | 0
A3870 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of tapping fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 |  |  | 375 | 0
A3880 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of tapping fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 |  |  | 375 | 0
A3910 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Raw gas collection duct | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3920 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Clean gas duct assembly | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A3930 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | BE.s: Support structure of secondary ducts & Misc. structures | 2025-04-16 00:30 | 2025-05-21 23:30 |  |  | 35 | 0
A3940 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | BE.a: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2025-06-04 23:30 |  |  | 97 | 0
A3950 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DE.s: Support structure of secondary ducts & Misc. structures | 2025-06-05 00:30 | 2025-11-05 23:30 |  |  | 151 | 0
A3960 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DE.a/i: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2025-11-19 23:30 |  |  | 262 | 0
A3970 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | MAN: Support structure of secondary ducts & Misc. structures | 2025-08-03 00:30 | 2026-02-12 23:30 |  |  | 190 | 0
A3980 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | INSP: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-02-26 23:30 |  |  | 360 | 0
A3990 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DCC.a: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-01 23:30 |  |  | 363 | 0
A4000 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DCC.r: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-05 23:30 |  |  | 367 | 0
A4010 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | LT: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4020 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (material handling fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4030 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (material handling fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4040 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4050 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4060 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (hot metal mixer station fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4070 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (hot metal mixer station fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4080 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (hot metal mixer station fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4090 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4100 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (charging fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4110 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (charging fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4120 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (charging fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4130 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (charging fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4140 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (tapping fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4150 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (tapping fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4160 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (tapping fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4170 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Duct supporting structues (raw gas collection duct) | 2025-03-12 00:30 | 2026-03-26 23:30 |  |  | 374 | 0
A4180 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (raw gas collection duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4190 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Duct supporting structues (clean gas duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4200 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (clean gas duct) | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4210 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Structural shed for ID fan | 2025-02-26 00:30 | 2026-03-26 23:30 |  |  | 388 | 0
A4220 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | BE.s: Refractory lining | 2025-04-16 00:30 | 2025-07-12 23:30 |  |  | 87 | 0
A4230 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | BE.a: Refractory lining | 2025-02-26 00:30 | 2025-07-26 23:30 |  |  | 149 | 0
A4240 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DE.s: Refractory lining | 2025-10-19 00:30 | 2025-12-15 23:30 |  |  | 57 | 0
A4250 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DE.a/i: Refractory lining | 2025-02-26 00:30 | 2026-01-04 23:30 |  |  | 307 | 0
A4260 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | MAN: Refractory lining | 2026-01-05 00:30 | 2026-05-13 23:30 |  |  | 129 | 0
A4270 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | INSP: Refractory lining | 2025-02-26 00:30 | 2026-05-27 23:30 |  |  | 450 | 0
A4280 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DCC.a: Refractory lining | 2025-02-26 00:30 | 2026-05-30 23:30 |  |  | 453 | 0
A4290 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DCC.r: Refractory lining | 2025-02-26 00:30 | 2026-06-03 23:30 |  |  | 457 | 0
A4300 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | LT: Refractory lining | 2025-02-26 00:30 | 2026-06-24 23:30 |  |  | 478 | 0
A4310 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for dog house unit | 2025-06-26 00:30 | 2026-06-24 23:30 |  |  | 360 | 0
A4320 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for hood (charging fume suction) | 2025-06-26 00:30 | 2026-06-24 23:30 |  |  | 360 | 0
A4330 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for hood (tapping fume suction) | 2025-06-26 00:30 | 2026-06-24 23:30 |  |  | 360 | 0
A4340 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | BE.s: Insulation | 2025-04-16 00:30 | 2025-07-11 23:30 |  |  | 86 | 0
A4350 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | BE.a: Insulation | 2025-02-26 00:30 | 2025-07-25 23:30 |  |  | 148 | 0
A4360 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DE.s: Insulation | 2025-09-17 00:30 | 2025-11-14 23:30 |  |  | 57 | 0
A4370 | Not Started | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DE.a/i: Insulation | 2025-02-26 00:30 | 2025-11-28 23:30 |  |  | 271 | 0