## TASK
task_code | status_code | wbs_id | task_name | target_start_date | target_end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Planned Start | (*)Planned Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Delete This Row
A4380 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | MAN: Insulation | 2025-12-02 00:30 | 2026-04-27 23:30 | 2025-12-02 00:30 | 2026-04-26 23:30 | 146 | 146
A4390 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | INSP: Insulation | 2025-02-26 00:30 | 2026-05-11 23:30 | 2025-02-26 00:30 | 2026-05-09 23:30 | 434 | 434
A4400 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DCC.a: Insulation | 2025-02-26 00:30 | 2026-05-14 23:30 | 2025-02-26 00:30 | 2026-05-14 23:30 | 437 | 437
A4410 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DCC.r: Insulation | 2025-02-26 00:30 | 2026-05-18 23:30 | 2025-02-26 00:30 | 2026-05-13 23:30 | 441 | 441
A4420 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | LT: Insulation | 2025-02-26 00:30 | 2026-06-08 23:30 | 2025-02-26 00:30 | 2026-06-08 23:30 | 462 | 462
A4430 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Heat insulation material ( for dust hoppers of ESP) | 2026-06-09 00:30 | 2026-06-24 23:30 | 2026-06-09 00:30 | 2026-06-24 23:30 | 16 | 16
A4440 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Sound insulation (for secondary ID fan) | 2026-06-09 00:30 | 2026-06-24 23:30 | 2026-06-09 00:30 | 2026-06-24 23:30 | 16 | 16
A4450 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15.1.2.2.4.15.10 | AoS: Sound insulation (for MHS booster fan) | 2026-06-09 00:30 | 2026-06-24 23:30 | 2026-06-09 00:30 | 2026-06-24 23:30 | 16 | 16
A4460 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | BE.s: Misc. electric hoists | 2025-06-11 00:30 | 2025-07-09 23:30 | 2025-06-11 00:30 | 2025-07-08 23:30 | 29 | 29
A4470 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | BE.a: Misc. electric hoists | 2025-02-26 00:30 | 2025-07-23 23:30 | 2025-02-26 00:30 | 2025-07-18 23:30 | 146 | 146
A4480 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DE.s: Misc. electric hoists | 2025-09-30 00:30 | 2025-11-27 23:30 | 2025-09-30 00:30 | 2025-11-27 23:30 | 57 | 57
A4490 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DE.a/i: Misc. electric hoists | 2025-02-26 00:30 | 2025-12-11 23:30 | 2025-02-26 00:30 | 2025-12-11 23:30 | 284 | 284
A4500 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | MAN: Misc. electric hoists | 2025-11-14 00:30 | 2026-03-10 23:30 | 2025-11-14 00:30 | 2026-03-10 23:30 | 116 | 116
A4510 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | INSP: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-24 23:30 | 2025-03-02 00:30 | 2026-04-01 23:30 | 386 | 386
A4520 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DCC.a: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-27 23:30 | 2025-02-26 00:30 | 2026-03-27 23:30 | 389 | 389
A4530 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | DCC.r: Misc. electric hoists | 2025-02-26 00:30 | 2026-03-31 23:30 | 2025-02-26 00:30 | 2026-03-31 23:30 | 393 | 393
A4540 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16 | LT: Misc. electric hoists | 2025-02-26 00:30 | 2026-04-21 23:30 | 2025-02-27 00:30 | 2026-05-04 23:30 | 414 | 414
A4550 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric hoist (for transformer rectifier of ESP) | 2025-02-26 00:30 | 2026-04-21 23:30 | 2025-02-26 00:30 | 2026-04-21 23:30 | 414 | 414
A4560 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric hoist | 2025-02-26 00:30 | 2026-04-21 23:30 | 2025-02-26 00:30 | 2026-04-21 23:30 | 414 | 414
A4570 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.16.1.2.2.4.16.10 | AoS: Electric Hoist for Secondary Dedusting Electrical Room | 2025-02-26 00:30 | 2026-04-21 23:30 | 2025-02-27 00:30 | 2026-05-02 23:30 | 414 | 414
A1810 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | INSP: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-12 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 374 | 374
A1820 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | DCC.a: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-15 23:30 | 2025-02-26 00:30 | 2026-03-15 23:30 | 377 | 377
A1830 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | DCC.r: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-03-18 23:30 | 2025-03-03 00:30 | 2026-03-23 23:30 | 380 | 380
A1840 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | LT: Dog house unit drive (Converter-1) | 2025-02-26 00:30 | 2026-04-08 23:30 | 2025-02-26 00:30 | 2026-04-08 23:30 | 401 | 401
A1900 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.7 | AoS: Dog house unit drive | 2025-02-26 00:30 | 2026-04-08 23:30 | 2025-02-26 00:30 | 2026-04-05 23:30 | 401 | 401
A1760 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | BE.s: Dog house unit drive | 2025-04-16 00:30 | 2025-06-25 23:30 | 2025-04-16 00:30 | 2025-06-24 23:30 | 70 | 70
A1770 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | BE.a: Dog house unit drive | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-09 23:30 | 132 | 132
A1780 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | DE.s: Dog house unit drive | 2025-08-18 00:30 | 2025-11-14 23:30 | 2025-08-18 00:30 | 2025-11-14 23:30 | 87 | 87
A1790 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2 | DE.a/i: Dog house unit drive | 2025-02-26 00:30 | 2025-11-28 23:30 | 2025-02-26 00:30 | 2025-11-28 23:30 | 271 | 271
A1800 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.5 | MAN: Dog house unit drive (Converter-1) | 2025-10-23 00:30 | 2026-02-26 23:30 | 2025-10-23 00:30 | 2026-02-26 23:30 | 126 | 126
A4580 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | BE.s: Fluid and utility facilities | 2025-05-13 00:30 | 2025-07-10 23:30 | 2025-05-13 00:30 | 2025-07-10 23:30 | 59 | 59
A4590 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | BE.a: Fluid and utility facilities | 2025-02-26 00:30 | 2025-07-24 23:30 | 2025-02-26 00:30 | 2025-07-24 23:30 | 147 | 147
A4600 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DE.s: Fluid and utility facilities | 2025-07-25 00:30 | 2025-12-20 23:30 | 2025-07-25 00:30 | 2025-12-20 23:30 | 146 | 146
A4610 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DE.a/i: Fluid and utility facilities | 2025-02-26 00:30 | 2026-01-04 23:30 | 2025-02-26 00:30 | 2026-01-01 23:30 | 307 | 307
A4620 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | MAN: Fluid and utility facilities | 2025-11-02 00:30 | 2026-03-13 23:30 | 2025-11-02 00:30 | 2026-03-13 23:30 | 131 | 131
A4630 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | INSP: Fluid and utility facilities | 2025-02-26 00:30 | 2026-03-27 23:30 | 2025-02-26 00:30 | 2026-03-27 23:30 | 389 | 389
A4640 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DCC.a: Fluid and utility facilities | 2025-02-26 00:30 | 2026-03-30 23:30 | 2025-02-26 00:30 | 2026-03-29 23:30 | 392 | 392
A4650 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | DCC.r: Fluid and utility facilities | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-01 23:30 | 396 | 396
A4660 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17 | LT: Fluid and utility facilities | 2025-02-26 00:30 | 2026-04-24 23:30 | 2025-02-26 00:30 | 2026-04-22 23:30 | 417 | 417
A4670 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17.1.2.2.4.17.10 | AoS: Interconnecting piping - fire water | 2025-02-26 00:30 | 2026-04-24 23:30 | 2025-02-26 00:30 | 2026-04-24 23:30 | 417 | 417
A4680 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.17.1.2.2.4.17.10 | AoS: Interconnecting piping - nitrogen | 2025-02-26 00:30 | 2026-04-24 23:30 | 2025-02-26 00:30 | 2026-04-24 23:30 | 417 | 417
A4710 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | BE.s: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-06-27 23:30 | 2025-02-28 00:30 | 2025-07-17 23:30 | 120 | 120
A4720 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | BE.a: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-07-11 23:30 | 2025-02-26 00:30 | 2025-07-10 23:30 | 134 | 134
A4730 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DE.s: General scope for buildings and foundations | 2025-03-29 00:30 | 2025-11-21 23:30 | 2025-03-29 00:30 | 2025-11-21 23:30 | 234 | 234
A4740 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DE.a/i: General scope for buildings and foundations | 2025-02-26 00:30 | 2025-12-05 23:30 | 2025-02-26 00:30 | 2025-12-05 23:30 | 278 | 278
A4750 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | MAN: General scope for buildings and foundations | 2025-06-13 00:30 | 2026-04-20 23:30 | 2025-06-13 00:30 | 2026-04-20 23:30 | 308 | 308
A4760 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | INSP: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-04 23:30 | 2025-02-26 00:30 | 2026-05-04 23:30 | 427 | 427
A4770 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DCC.a: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-07 23:30 | 2025-02-26 00:30 | 2026-05-07 23:30 | 430 | 430
A4780 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | DCC.r: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-05-11 23:30 | 2025-02-28 00:30 | 2026-05-24 23:30 | 434 | 434
A4790 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1 | LT: General scope for buildings and foundations | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-05-28 23:30 | 455 | 455
A4800 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Anchor boxes/bolts for equipment directly placed in concrete | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-28 00:30 | 2026-06-18 23:30 | 455 | 455
A4810 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Equipment base frames incl. anchor bolts | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4820 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Anchors for steel structure | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4830 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Retaining bars, weld-on plates; edge protection as well as running rails for transformers; wall penetrations and pi | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-05-29 23:30 | 455 | 455
A4840 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Concrete covers for openings | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-05-28 23:30 | 455 | 455
A4850 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Steel covers for openings | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-03-01 00:30 | 2026-06-16 23:30 | 455 | 455
A4860 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Earthwork/ cable protection measures related to temporary site facilities | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4870 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Lightning protection and earthing | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-03-02 00:30 | 2026-06-20 23:30 | 455 | 455
A4880 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Conduits and conduit templates including all connections placed in concrete or ground, as well as conduit closures | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4890 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Doors and windows | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4900 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.1.1.2.2.5.1.10 | AoS: Temporary site fencing incl. gates, barriers, repair and disassembly | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-06-01 23:30 | 455 | 455
A4910 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | BE.s: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-04-30 23:30 | 2025-02-26 00:30 | 2025-04-26 23:30 | 63 | 63
A4920 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | BE.a: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-05-16 23:30 | 2025-02-26 00:30 | 2025-05-12 23:30 | 78 | 78
A4930 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | DE.s: Secondary dedusting E-building | 2025-07-16 00:30 | 2025-11-16 23:30 | 2025-07-16 00:30 | 2025-11-16 23:30 | 121 | 121
A4940 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.1 | DE.a/i: Secondary dedusting E-building | 2025-02-26 00:30 | 2025-11-30 23:30 | 2025-03-01 00:30 | 2025-12-19 23:30 | 273 | 273
A4950 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | BE.s: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-02-26 00:30 | 2025-07-13 23:30 | 2025-02-27 00:30 | 2025-07-16 23:30 | 136 | 136
A4960 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | BE.a: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-02-26 00:30 | 2025-07-27 23:30 | 2025-02-26 00:30 | 2025-07-22 23:30 | 150 | 150
A4970 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | DE.s: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Secondar | 2025-07-28 00:30 | 2025-12-22 23:30 | 2025-07-29 00:30 | 2026-01-04 23:30 | 144 | 144
A4980 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.2.1.2.2.5.2.2 | DE.a/i: Cable rack / trench / conduit banks for Secondary Dedusting systemCable rack / trench / conduit banks for Second | 2025-02-26 00:30 | 2026-01-05 23:30 | 2025-02-26 00:30 | 2026-01-05 23:30 | 308 | 308
A4990 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | BE.s: Secondary ID fan foundation | 2025-04-16 00:30 | 2025-05-30 23:30 | 2025-04-16 00:30 | 2025-05-30 23:30 | 44 | 44
A5000 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | BE.a: Secondary ID fan foundation | 2025-02-26 00:30 | 2025-06-13 23:30 | 2025-02-26 00:30 | 2025-06-13 23:30 | 106 | 106
A5010 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | DE.s: Secondary ID fan foundation | 2025-06-18 00:30 | 2025-08-20 23:30 | 2025-06-18 00:30 | 2025-08-17 23:30 | 63 | 63
A5020 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.1 | DE.a/i: Secondary ID fan foundation | 2025-02-26 00:30 | 2025-09-03 23:30 | 2025-03-03 00:30 | 2025-09-11 23:30 | 187 | 187
A5030 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | BE.s: Secondary ID fan rain protection foundation | 2025-04-16 00:30 | 2025-05-30 23:30 | 2025-04-21 00:30 | 2025-06-11 23:30 | 44 | 44
A5040 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | BE.a: Secondary ID fan rain protection foundation | 2025-02-26 00:30 | 2025-06-13 23:30 | 2025-02-26 00:30 | 2025-06-11 23:30 | 106 | 106
A5050 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | DE.s: Secondary ID fan rain protection foundation | 2025-06-14 00:30 | 2025-08-20 23:30 | 2025-06-14 00:30 | 2025-08-20 23:30 | 67 | 67
A5060 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.2 | DE.a/i: Secondary ID fan rain protection foundation | 2025-02-26 00:30 | 2025-09-03 23:30 | 2025-02-26 00:30 | 2025-09-03 23:30 | 187 | 187
A5070 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | BE.s: Secondary stack foundation | 2025-04-25 00:30 | 2025-06-08 23:30 | 2025-04-26 00:30 | 2025-06-27 23:30 | 44 | 44
A5080 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | BE.a: Secondary stack foundation | 2025-02-26 00:30 | 2025-06-22 23:30 | 2025-02-26 00:30 | 2025-06-18 23:30 | 115 | 115
A5090 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | DE.s: Secondary stack foundation | 2025-06-23 00:30 | 2025-09-20 23:30 | 2025-06-23 00:30 | 2025-09-20 23:30 | 89 | 89
A5100 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.3 | DE.a/i: Secondary stack foundation | 2025-02-26 00:30 | 2025-10-08 23:30 | 2025-02-28 00:30 | 2025-10-20 23:30 | 221 | 221
A5110 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | BE.s: Dry ESP support foundation | 2025-04-25 00:30 | 2025-06-08 23:30 | 2025-04-25 00:30 | 2025-06-08 23:30 | 44 | 44
A5120 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | BE.a: Dry ESP support foundation | 2025-02-26 00:30 | 2025-06-22 23:30 | 2025-02-27 00:30 | 2025-06-27 23:30 | 115 | 115
A5130 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | DE.s: Dry ESP support foundation | 2025-06-23 00:30 | 2025-09-20 23:30 | 2025-06-23 00:30 | 2025-09-19 23:30 | 89 | 89
A5140 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.4 | DE.a/i: Dry ESP support foundation | 2025-02-26 00:30 | 2025-10-08 23:30 | 2025-02-28 00:30 | 2025-10-28 23:30 | 221 | 221
A5150 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | BE.s: Foundation for dust disposal system | 2025-04-27 00:30 | 2025-06-10 23:30 | 2025-04-27 00:30 | 2025-06-10 23:30 | 44 | 44
A5160 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | BE.a: Foundation for dust disposal system | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-24 23:30 | 117 | 117
A5170 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | DE.s: Foundation for dust disposal system | 2025-07-11 00:30 | 2025-09-21 23:30 | 2025-07-11 00:30 | 2025-09-18 23:30 | 72 | 72
A5180 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.3.1.2.2.5.3.5 | DE.a/i: Foundation for dust disposal system | 2025-02-26 00:30 | 2025-10-09 23:30 | 2025-02-26 00:30 | 2025-10-04 23:30 | 222 | 222
A5190 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | BE.s: Duct support structure foundation | 2025-04-27 00:30 | 2025-06-25 23:30 | 2025-04-27 00:30 | 2025-06-25 23:30 | 59 | 59
A5200 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | BE.a: Duct support structure foundation | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-09 23:30 | 132 | 132
A5210 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | DE.s: Duct support structure foundation | 2025-07-10 00:30 | 2025-10-07 23:30 | 2025-07-10 00:30 | 2025-10-05 23:30 | 88 | 88
A5220 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.1 | DE.a/i: Duct support structure foundation | 2025-02-26 00:30 | 2025-10-26 23:30 | 2025-02-26 00:30 | 2025-10-22 23:30 | 238 | 238
A5230 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | BE.s: Cable rack foundations/trench/conduit banks | 2025-04-25 00:30 | 2025-06-23 23:30 | 2025-04-29 00:30 | 2025-07-07 23:30 | 59 | 59
A5240 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | BE.a: Cable rack foundations/trench/conduit banks | 2025-02-26 00:30 | 2025-07-07 23:30 | 2025-02-27 00:30 | 2025-07-24 23:30 | 130 | 130
A5250 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | DE.s: Cable rack foundations/trench/conduit banks | 2025-07-08 00:30 | 2026-01-03 23:30 | 2025-07-08 00:30 | 2026-01-03 23:30 | 176 | 176
A5260 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.4.1.2.2.5.4.2 | DE.a/i: Cable rack foundations/trench/conduit banks | 2025-02-26 00:30 | 2026-01-17 23:30 | 2025-02-26 00:30 | 2026-01-17 23:30 | 320 | 320
A5270 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | BE.s: Cable support structures | 2025-04-27 00:30 | 2025-06-25 23:30 | 2025-04-27 00:30 | 2025-06-25 23:30 | 59 | 59
A5280 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | BE.a: Cable support structures | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-04 23:30 | 132 | 132
A5290 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DE.s: Cable support structures | 2025-07-10 00:30 | 2025-10-07 23:30 | 2025-07-10 00:30 | 2025-10-07 23:30 | 88 | 88
A5300 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DE.a/i: Cable support structures | 2025-02-26 00:30 | 2025-10-26 23:30 | 2025-02-26 00:30 | 2025-10-26 23:30 | 238 | 238
A5310 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | MAN: Cable support structures | 2025-09-11 00:30 | 2026-03-04 23:30 | 2025-09-11 00:30 | 2026-03-02 23:30 | 172 | 172
A5320 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | INSP: Cable support structures | 2025-02-26 00:30 | 2026-03-18 23:30 | 2025-02-26 00:30 | 2026-03-18 23:30 | 380 | 380
A5330 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DCC.a: Cable support structures | 2025-02-26 00:30 | 2026-03-21 23:30 | 2025-02-26 00:30 | 2026-03-21 23:30 | 383 | 383
A5340 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | DCC.r: Cable support structures | 2025-02-26 00:30 | 2026-03-25 23:30 | 2025-02-26 00:30 | 2026-03-25 23:30 | 387 | 387
A5350 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | LT: Cable support structures | 2025-02-26 00:30 | 2026-04-15 23:30 | 2025-02-26 00:30 | 2026-04-12 23:30 | 408 | 408
A5360 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.5.1.2.2.5.5.1 | AoS: Cable support structures | 2025-02-26 00:30 | 2026-04-15 23:30 | 2025-02-26 00:30 | 2026-04-13 23:30 | 408 | 408
A5370 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | BE.s: HVAC | 2025-04-16 00:30 | 2025-06-15 23:30 | 2025-04-16 00:30 | 2025-06-10 23:30 | 60 | 60
A5380 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | BE.a: HVAC | 2025-02-26 00:30 | 2025-06-29 23:30 | 2025-02-26 00:30 | 2025-06-27 23:30 | 122 | 122
A5390 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DE.s: HVAC | 2025-08-29 00:30 | 2025-11-10 23:30 | 2025-08-31 00:30 | 2025-11-26 23:30 | 72 | 72
A5400 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DE.a/i: HVAC | 2025-02-26 00:30 | 2025-11-24 23:30 | 2025-02-26 00:30 | 2025-11-24 23:30 | 267 | 267
A5410 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | MAN: HVAC | 2025-11-01 00:30 | 2026-01-26 23:30 | 2025-11-01 00:30 | 2026-01-23 23:30 | 86 | 86
A5420 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | INSP: HVAC | 2025-02-26 00:30 | 2026-02-09 23:30 | 2025-02-26 00:30 | 2026-02-09 23:30 | 343 | 343
A5430 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DCC.a: HVAC | 2025-02-26 00:30 | 2026-02-12 23:30 | 2025-02-26 00:30 | 2026-02-12 23:30 | 346 | 346
A5440 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | DCC.r: HVAC | 2025-02-26 00:30 | 2026-02-16 23:30 | 2025-02-26 00:30 | 2026-02-15 23:30 | 350 | 350
A5450 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6 | LT: HVAC | 2025-02-26 00:30 | 2026-03-09 23:30 | 2025-02-26 00:30 | 2026-03-09 23:30 | 371 | 371
A5460 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: Equipment for HVAC system excl. natural ventilation | 2025-06-26 00:30 | 2026-03-09 23:30 | 2025-06-26 00:30 | 2026-03-08 23:30 | 253 | 253
A5470 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: Power supply, electrical distribution and cabling for HVAC system | 2025-06-26 00:30 | 2026-03-09 23:30 | 2025-06-26 00:30 | 2026-03-09 23:30 | 253 | 253
A5480 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: FRP cooling tower pumps (1W+1S) | 2025-06-26 00:30 | 2026-03-09 23:30 | 2025-06-26 00:30 | 2026-03-09 23:30 | 253 | 253
A5490 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.6.1.2.2.5.6.10 | AoS: FRP cooling tower (NW+NS) | 2025-06-26 00:30 | 2026-03-09 23:30 | 2025-06-26 00:30 | 2026-03-09 23:30 | 253 | 253
A5500 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | BE.s: Fire detection, fire fighting and fire protection systems | 2025-04-27 00:30 | 2025-06-10 23:30 | 2025-04-27 00:30 | 2025-06-10 23:30 | 44 | 44
A5510 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | BE.a: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-24 23:30 | 117 | 117
A5520 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DE.s: Fire detection, fire fighting and fire protection systems | 2025-08-02 00:30 | 2025-10-15 23:30 | 2025-08-02 00:30 | 2025-10-15 23:30 | 73 | 73
A5530 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DE.a/i: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2025-11-03 23:30 | 2025-03-03 00:30 | 2025-11-20 23:30 | 246 | 246
A5540 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | MAN: Fire detection, fire fighting and fire protection systems | 2025-10-14 00:30 | 2026-02-27 23:30 | 2025-10-14 00:30 | 2026-02-27 23:30 | 135 | 135
A5550 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | INSP: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-13 23:30 | 2025-02-26 00:30 | 2026-03-08 23:30 | 375 | 375
A5560 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DCC.a: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-16 23:30 | 2025-02-28 00:30 | 2026-03-21 23:30 | 378 | 378
A5570 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | DCC.r: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-03-20 23:30 | 2025-02-26 00:30 | 2026-03-20 23:30 | 382 | 382
A5580 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7 | LT: Fire detection, fire fighting and fire protection systems | 2025-02-26 00:30 | 2026-04-10 23:30 | 2025-02-26 00:30 | 2026-04-10 23:30 | 403 | 403
A5590 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire Protection System | 2025-06-28 00:30 | 2026-04-10 23:30 | 2025-06-28 00:30 | 2026-04-10 23:30 | 283 | 283
A5600 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire alarm systems | 2025-06-28 00:30 | 2026-04-10 23:30 | 2025-06-28 00:30 | 2026-04-10 23:30 | 283 | 283
A5610 | Completed | BSL.1.3.1.2.2.1.2.2.5.1.2.2.5.7.1.2.2.5.7.10 | AoS: Fire-extinguishing systems and devices | 2025-06-28 00:30 | 2026-04-10 23:30 | 2025-06-28 00:30 | 2026-04-10 23:30 | 283 | 283
A2630 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Chain Conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2640 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Motor for conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-03-02 00:30 | 2026-03-13 23:30 | 364 | 364
A2650 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.1 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2660 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.2 | AoS: Rotary valve | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-02-25 23:30 | 364 | 364
A3030 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | AoS: Pug mill assembly | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-15 23:30 | 381 | 381
A3020 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | LT: Pug mill assembly | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2980 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | MAN: Pug mill assembly | 2025-09-21 00:30 | 2026-02-05 23:30 | 2025-09-21 00:30 | 2026-02-05 23:30 | 135 | 135
A2990 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | INSP: Pug mill assembly | 2025-02-26 00:30 | 2026-02-19 23:30 | 2025-02-27 00:30 | 2026-03-11 23:30 | 353 | 353
A3000 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DCC.a: Pug mill assembly | 2025-02-26 00:30 | 2026-02-22 23:30 | 2025-02-26 00:30 | 2026-02-21 23:30 | 356 | 356
A3010 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DCC.r: Pug mill assembly | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-26 23:30 | 360 | 360
A2940 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | BE.s: Pug mill assembly | 2025-04-28 00:30 | 2025-06-26 23:30 | 2025-04-28 00:30 | 2025-06-26 23:30 | 59 | 59
A2950 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | BE.a: Pug mill assembly | 2025-02-26 00:30 | 2025-07-10 23:30 | 2025-02-28 00:30 | 2025-07-29 23:30 | 133 | 133
A2960 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DE.s: Pug mill assembly | 2025-07-11 00:30 | 2025-10-08 23:30 | 2025-07-11 00:30 | 2025-10-08 23:30 | 88 | 88
A2970 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.7 | DE.a/i: Pug mill assembly | 2025-02-26 00:30 | 2025-10-27 23:30 | 2025-02-26 00:30 | 2025-10-25 23:30 | 239 | 239
A5620 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | BE.s: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-05-13 23:30 | 2025-02-26 00:30 | 2025-05-13 23:30 | 75 | 75
A5630 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | BE.a: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-05-27 23:30 | 2025-02-26 00:30 | 2025-05-27 23:30 | 89 | 89
A5640 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DE.s: HMI Hardware and System Software | 2025-10-06 00:30 | 2025-11-30 23:30 | 2025-10-07 00:30 | 2025-12-15 23:30 | 55 | 55
A5650 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DE.a/i: HMI Hardware and System Software | 2025-02-26 00:30 | 2025-12-14 23:30 | 2025-03-03 00:30 | 2025-12-24 23:30 | 287 | 287
A5660 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | MAN: HMI Hardware and System Software | 2025-12-06 00:30 | 2026-02-13 23:30 | 2025-12-06 00:30 | 2026-02-08 23:30 | 69 | 69
A5670 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | INSP: HMI Hardware and System Software | 2026-02-14 00:30 | 2026-02-27 23:30 | 2026-02-14 00:30 | 2026-02-27 23:30 | 14 | 14
A5680 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DCC.a: HMI Hardware and System Software | 2026-02-28 00:30 | 2026-03-02 23:30 | 2026-02-28 00:30 | 2026-02-25 23:30 | 3 | 3
A5690 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | DCC.r: HMI Hardware and System Software | 2026-03-03 00:30 | 2026-03-06 23:30 | 2026-03-03 00:30 | 2026-03-03 23:30 | 4 | 4
A5700 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1 | LT: HMI Hardware and System Software | 2025-02-26 00:30 | 2026-03-27 23:30 | 2025-02-26 00:30 | 2026-03-27 23:30 | 389 | 389
A5710 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at New ECR room for ESP - Hardware | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-26 00:30 | 0 | 0
A5720 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at New ECR room for ESP - System Software | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 0 | 0
A5730 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at Converter Control room - Hardware | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 0 | 0
A5740 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: HMI Workstation station at Converter Control room - System Software | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-24 00:30 | 0 | 0
A5750 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: A4 B/W Laser Printer | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 0 | 0
A5760 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.1.1.2.2.6.1.10 | AoS: Computer furniture (3 Computer table, 3 chairs , 1 Printer Table, 2 steel almirah) | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-29 00:30 | 2026-04-02 00:30 | 0 | 0
A5770 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | BE.s: Control Desks and Control Boxes | 2025-05-28 00:30 | 2025-07-10 23:30 | 2025-05-28 00:30 | 2025-07-10 23:30 | 44 | 44
A5780 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | BE.a: Control Desks and Control Boxes | 2025-02-26 00:30 | 2025-07-24 23:30 | 2025-02-27 00:30 | 2025-07-30 23:30 | 147 | 147
A5790 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DE.s: Control Desks and Control Boxes | 2025-09-02 00:30 | 2025-10-30 23:30 | 2025-09-02 00:30 | 2025-10-25 23:30 | 57 | 57
A5800 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DE.a/i: Control Desks and Control Boxes | 2025-02-26 00:30 | 2025-11-13 23:30 | 2025-02-26 00:30 | 2025-11-13 23:30 | 256 | 256
A5810 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | MAN: Control Desks and Control Boxes | 2025-11-03 00:30 | 2026-02-12 23:30 | 2025-11-05 00:30 | 2026-02-17 23:30 | 101 | 101
A5820 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | INSP: Control Desks and Control Boxes | 2026-02-13 00:30 | 2026-02-26 23:30 | 2026-02-13 00:30 | 2026-02-26 23:30 | 14 | 14
A5830 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DCC.a: Control Desks and Control Boxes | 2026-02-27 00:30 | 2026-03-01 23:30 | 2026-02-27 00:30 | 2026-03-01 23:30 | 3 | 3
A5840 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | DCC.r: Control Desks and Control Boxes | 2026-03-02 00:30 | 2026-03-05 23:30 | 2026-03-07 00:30 | 2026-03-17 23:30 | 4 | 4
A5850 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2 | LT: Control Desks and Control Boxes | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-27 00:30 | 2026-04-14 23:30 | 388 | 388
A5860 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2.1.2.2.6.2.10 | AoS: Operator Desk at new ECR Building | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-22 00:30 | 0 | 0
A5870 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.2.1.2.2.6.2.10 | AoS: Local Control Boxes for ESP area | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A5880 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | BE.s: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-05-13 23:30 | 2025-02-26 00:30 | 2025-05-11 23:30 | 75 | 75
A5890 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | BE.a: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-05-27 23:30 | 2025-02-26 00:30 | 2025-05-27 23:30 | 89 | 89
A5900 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DE.s: PCS Hardware and System Software | 2025-07-05 00:30 | 2025-09-15 23:30 | 2025-07-07 00:30 | 2025-10-05 23:30 | 72 | 72
A5910 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DE.a/i: PCS Hardware and System Software | 2025-02-26 00:30 | 2025-09-29 23:30 | 2025-02-26 00:30 | 2025-09-29 23:30 | 213 | 213
A5920 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | MAN: PCS Hardware and System Software | 2025-09-04 00:30 | 2026-02-17 23:30 | 2025-09-04 00:30 | 2026-02-14 23:30 | 164 | 164
A5930 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | INSP: PCS Hardware and System Software | 2026-02-18 00:30 | 2026-03-03 23:30 | 2026-02-18 00:30 | 2026-03-03 23:30 | 14 | 14
A5940 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DCC.a: PCS Hardware and System Software | 2026-03-04 00:30 | 2026-03-06 23:30 | 2026-03-04 00:30 | 2026-03-03 23:30 | 3 | 3
A5950 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | DCC.r: PCS Hardware and System Software | 2026-03-07 00:30 | 2026-03-10 23:30 | 2026-03-07 00:30 | 2026-03-07 23:30 | 4 | 4
A5960 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3 | LT: PCS Hardware and System Software | 2025-02-26 00:30 | 2026-03-31 23:30 | 2025-02-27 00:30 | 2026-04-04 23:30 | 393 | 393
A5970 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: PLC (CPU) for ESP | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-03-29 00:30 | 0 | 0
A5980 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: RIOs for ESP & ID Fans | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 0 | 0
A5990 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Remote Ios for Doghouse & Dampers for Converters # 1 & 2 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 0 | 0
A6000 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: RIO (with Panel AC) for Suction Damper of Mixer-II | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 0 | 0
A6010 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Laptop based Programming Station - Hardware | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-05 00:30 | 2026-04-09 00:30 | 0 | 0
A6020 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: Laptop based Programming Station - System Software | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-03-28 00:30 | 0 | 0
A6030 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: HMI development cum Engineering station at New ECR room for ESP - Hardware | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-03-31 00:30 | 0 | 0
A6040 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.3.1.2.2.6.3.10 | AoS: HMI development cum Engineering station at New ECR room for ESP - System Software | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 2026-04-01 00:30 | 0 | 0
A6050 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | BE.s: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-03-03 00:30 | 2025-06-17 23:30 | 103 | 103
A6060 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | BE.a: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-24 23:30 | 117 | 117
A6070 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DE.s: Electrical Field Devices, Sensors | 2025-08-02 00:30 | 2025-09-30 23:30 | 2025-08-02 00:30 | 2025-09-30 23:30 | 59 | 59
A6080 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DE.a/i: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2025-10-18 23:30 | 2025-02-26 00:30 | 2025-10-14 23:30 | 231 | 231
A6090 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | MAN: Electrical Field Devices, Sensors | 2025-10-05 00:30 | 2026-02-18 23:30 | 2025-10-05 00:30 | 2026-02-18 23:30 | 135 | 135
A6100 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | INSP: Electrical Field Devices, Sensors | 2026-02-19 00:30 | 2026-02-26 23:30 | 2026-02-19 00:30 | 2026-02-26 23:30 | 8 | 8
A6110 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DCC.a: Electrical Field Devices, Sensors | 2026-02-27 00:30 | 2026-03-01 23:30 | 2026-03-02 00:30 | 2026-03-05 23:30 | 3 | 3
A6120 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | DCC.r: Electrical Field Devices, Sensors | 2026-03-02 00:30 | 2026-03-05 23:30 | 2026-03-02 00:30 | 2026-03-05 23:30 | 4 | 4
A6130 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4 | LT: Electrical Field Devices, Sensors | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A6140 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.4.1.2.2.6.4.10 | AoS: Electrical Field devices, Sensors for Seller supplied system | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6150 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | BE.s: Network | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-03-03 00:30 | 2025-06-26 23:30 | 103 | 103
A6160 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | BE.a: Network | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-22 23:30 | 117 | 117
A6170 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DE.s: Network | 2025-09-02 00:30 | 2025-10-30 23:30 | 2025-09-06 00:30 | 2025-11-07 23:30 | 57 | 57
A6180 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DE.a/i: Network | 2025-02-26 00:30 | 2025-11-13 23:30 | 2025-02-26 00:30 | 2025-11-13 23:30 | 256 | 256
A6190 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | MAN: Network | 2025-11-03 00:30 | 2026-02-12 23:30 | 2025-11-03 00:30 | 2026-02-09 23:30 | 101 | 101
A6200 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | INSP: Network | 2026-02-13 00:30 | 2026-02-26 23:30 | 2026-02-15 00:30 | 2026-03-14 23:30 | 14 | 14
A6210 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DCC.a: Network | 2026-02-27 00:30 | 2026-03-01 23:30 | 2026-02-27 00:30 | 2026-03-01 23:30 | 3 | 3
A6220 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | DCC.r: Network | 2026-03-02 00:30 | 2026-03-05 23:30 | 2026-03-06 00:30 | 2026-03-11 23:30 | 4 | 4
A6230 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5 | LT: Network | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-28 00:30 | 2026-04-13 23:30 | 388 | 388
A6240 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Switches (Layer 2) including accessories | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6250 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Switches (Layer 3) including accessories | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-30 00:30 | 2026-04-10 00:30 | 0 | 0
A6260 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Hardware Firewall | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-29 00:30 | 2026-04-06 00:30 | 0 | 0
A6270 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.5.1.2.2.6.5.10 | AoS: Network Components (Passive) | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6280 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | BE.s: HMI Functions | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-26 23:30 | 88 | 88
A6290 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | BE.a: HMI Functions | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-09 23:30 | 102 | 102
A6300 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DE.s: HMI Functions | 2025-08-18 00:30 | 2025-10-15 23:30 | 2025-08-21 00:30 | 2025-10-26 23:30 | 58 | 58
A6310 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DE.a/i: HMI Functions | 2025-02-26 00:30 | 2025-11-03 23:30 | 2025-02-26 00:30 | 2025-10-30 23:30 | 246 | 246
A6320 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | MAN: HMI Functions | 2025-10-19 00:30 | 2026-02-17 23:30 | 2025-10-19 00:30 | 2026-02-12 23:30 | 120 | 120
A6330 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | INSP: HMI Functions | 2026-02-18 00:30 | 2026-02-25 23:30 | 2026-02-18 00:30 | 2026-02-25 23:30 | 8 | 8
A6340 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DCC.a: HMI Functions | 2026-02-26 00:30 | 2026-02-28 23:30 | 2026-02-26 00:30 | 2026-02-28 23:30 | 3 | 3
A6350 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | DCC.r: HMI Functions | 2026-03-01 00:30 | 2026-03-04 23:30 | 2026-03-03 00:30 | 2026-03-15 23:30 | 4 | 4
A6360 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6 | LT: HMI Functions | 2025-02-26 00:30 | 2026-03-25 23:30 | 2025-02-26 00:30 | 2026-03-22 23:30 | 387 | 387
A6370 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.6.1.2.2.6.6.10 | AoS: HMI (Human Machine Interface) Application Software for Secondary Dedusting system | 2026-03-26 00:30 | 2026-03-26 00:30 | 2026-03-26 00:30 | 2026-03-26 00:30 | 0 | 0
A6380 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | BE.s: Process Control Functions | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-02-26 00:30 | 2025-06-07 23:30 | 103 | 103
A6390 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | BE.a: Process Control Functions | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-21 23:30 | 117 | 117
A6400 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DE.s: Process Control Functions | 2025-07-11 00:30 | 2025-11-07 23:30 | 2025-07-11 00:30 | 2025-11-07 23:30 | 117 | 117
A6410 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DE.a/i: Process Control Functions | 2025-02-26 00:30 | 2025-11-21 23:30 | 2025-03-02 00:30 | 2025-11-27 23:30 | 264 | 264
A6420 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | MAN: Process Control Functions | 2025-11-22 00:30 | 2026-02-23 23:30 | 2025-11-25 00:30 | 2026-03-04 23:30 | 93 | 93
A6430 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | INSP: Process Control Functions | 2026-02-24 00:30 | 2026-03-09 23:30 | 2026-02-24 00:30 | 2026-03-09 23:30 | 14 | 14
A6440 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DCC.a: Process Control Functions | 2026-03-10 00:30 | 2026-03-12 23:30 | 2026-03-10 00:30 | 2026-03-12 23:30 | 3 | 3
A6450 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | DCC.r: Process Control Functions | 2026-03-13 00:30 | 2026-03-16 23:30 | 2026-03-13 00:30 | 2026-03-11 23:30 | 4 | 4
A6460 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7 | LT: Process Control Functions | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-24 23:30 | 388 | 388
A6470 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.7.1.2.2.6.7.10 | AoS: Process Control Application Software for Secondary Dedusting system | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6480 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | BE.s: Instrumentation | 2025-02-26 00:30 | 2025-05-31 23:30 | 2025-02-26 00:30 | 2025-05-31 23:30 | 93 | 93
A6490 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | BE.a: Instrumentation | 2025-02-26 00:30 | 2025-06-14 23:30 | 2025-02-26 00:30 | 2025-06-11 23:30 | 107 | 107
A6500 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DE.s: Instrumentation | 2025-08-23 00:30 | 2025-10-20 23:30 | 2025-08-23 00:30 | 2025-10-19 23:30 | 58 | 58
A6510 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DE.a/i: Instrumentation | 2025-02-26 00:30 | 2025-11-08 23:30 | 2025-02-26 00:30 | 2025-11-05 23:30 | 251 | 251
A6520 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | MAN: Instrumentation | 2025-10-10 00:30 | 2026-02-08 23:30 | 2025-10-10 00:30 | 2026-02-04 23:30 | 120 | 120
A6530 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | INSP: Instrumentation | 2026-02-09 00:30 | 2026-02-16 23:30 | 2026-02-09 00:30 | 2026-02-16 23:30 | 8 | 8
A6540 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DCC.a: Instrumentation | 2026-02-17 00:30 | 2026-02-19 23:30 | 2026-02-17 00:30 | 2026-02-14 23:30 | 3 | 3
A6550 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | DCC.r: Instrumentation | 2026-02-20 00:30 | 2026-02-23 23:30 | 2026-02-20 00:30 | 2026-02-23 23:30 | 4 | 4
A6560 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8 | LT: Instrumentation | 2025-02-26 00:30 | 2026-03-16 23:30 | 2025-02-26 00:30 | 2026-03-16 23:30 | 378 | 378
A6570 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.8.1.2.2.6.8.10 | AoS: Instruments including accessories | 2026-03-17 00:30 | 2026-03-17 00:30 | 2026-03-22 00:30 | 2026-03-25 00:30 | 0 | 0
A6580 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | BE.s: Control Valves | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-02-26 00:30 | 2025-06-06 23:30 | 103 | 103
A6590 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | BE.a: Control Valves | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-23 23:30 | 117 | 117
A6600 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DE.s: Control Valves | 2025-07-19 00:30 | 2025-09-01 23:30 | 2025-07-19 00:30 | 2025-09-01 23:30 | 44 | 44
A6610 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DE.a/i: Control Valves | 2025-02-26 00:30 | 2025-09-15 23:30 | 2025-02-26 00:30 | 2025-09-15 23:30 | 199 | 199
A6620 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | MAN: Control Valves | 2025-09-17 00:30 | 2026-02-13 23:30 | 2025-09-21 00:30 | 2026-02-26 23:30 | 147 | 147
A6630 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | INSP: Control Valves | 2026-02-14 00:30 | 2026-02-27 23:30 | 2026-02-14 00:30 | 2026-02-27 23:30 | 14 | 14
A6640 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DCC.a: Control Valves | 2026-02-28 00:30 | 2026-03-02 23:30 | 2026-02-28 00:30 | 2026-02-25 23:30 | 3 | 3
A6650 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | DCC.r: Control Valves | 2026-03-03 00:30 | 2026-03-06 23:30 | 2026-03-03 00:30 | 2026-03-06 23:30 | 4 | 4
A6660 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9 | LT: Control Valves | 2025-02-26 00:30 | 2026-03-27 23:30 | 2025-02-27 00:30 | 2026-04-04 23:30 | 389 | 389
A6670 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.9.1.2.2.6.9.10 | AoS: Control Valves | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 2026-03-28 00:30 | 0 | 0
A6680 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | BE.s: Analysis System | 2025-02-26 00:30 | 2025-06-01 23:30 | 2025-02-26 00:30 | 2025-05-27 23:30 | 94 | 94
A6690 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | BE.a: Analysis System | 2025-02-26 00:30 | 2025-06-15 23:30 | 2025-02-26 00:30 | 2025-06-15 23:30 | 108 | 108
A6700 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DE.s: Analysis System | 2025-07-24 00:30 | 2025-09-21 23:30 | 2025-07-27 00:30 | 2025-10-01 23:30 | 59 | 59
A6710 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DE.a/i: Analysis System | 2025-02-26 00:30 | 2025-10-09 23:30 | 2025-02-26 00:30 | 2025-10-09 23:30 | 222 | 222
A6720 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | MAN: Analysis System | 2025-10-05 00:30 | 2026-02-18 23:30 | 2025-10-05 00:30 | 2026-02-18 23:30 | 135 | 135
A6730 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | INSP: Analysis System | 2026-02-19 00:30 | 2026-02-26 23:30 | 2026-02-19 00:30 | 2026-02-26 23:30 | 8 | 8
A6740 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DCC.a: Analysis System | 2026-02-27 00:30 | 2026-03-01 23:30 | 2026-02-27 00:30 | 2026-03-01 23:30 | 3 | 3
A6750 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | DCC.r: Analysis System | 2026-03-02 00:30 | 2026-03-05 23:30 | 2026-03-02 00:30 | 2026-03-05 23:30 | 4 | 4
A6760 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10 | LT: Analysis System | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-03-02 00:30 | 2026-03-31 23:30 | 388 | 388
A6770 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.10.1.2.2.6.10.10 | AoS: Dust concentration measurement in Secondary dedusting stack (common for all units) | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6780 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | BE.s: Vibration Monitoring System | 2025-02-26 00:30 | 2025-06-01 23:30 | 2025-02-26 00:30 | 2025-05-30 23:30 | 94 | 94
A6790 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | BE.a: Vibration Monitoring System | 2025-02-26 00:30 | 2025-06-15 23:30 | 2025-02-26 00:30 | 2025-06-11 23:30 | 108 | 108
A6800 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DE.s: Vibration Monitoring System | 2025-07-24 00:30 | 2025-09-21 23:30 | 2025-07-24 00:30 | 2025-09-21 23:30 | 59 | 59
A6810 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DE.a/i: Vibration Monitoring System | 2025-02-26 00:30 | 2025-10-09 23:30 | 2025-02-26 00:30 | 2025-10-09 23:30 | 222 | 222
A6820 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | MAN: Vibration Monitoring System | 2025-10-05 00:30 | 2026-02-18 23:30 | 2025-10-05 00:30 | 2026-02-17 23:30 | 135 | 135
A6830 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | INSP: Vibration Monitoring System | 2026-02-19 00:30 | 2026-02-26 23:30 | 2026-02-23 00:30 | 2026-03-04 23:30 | 8 | 8
A6840 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DCC.a: Vibration Monitoring System | 2026-02-27 00:30 | 2026-03-01 23:30 | 2026-02-27 00:30 | 2026-03-01 23:30 | 3 | 3
A6850 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | DCC.r: Vibration Monitoring System | 2026-03-02 00:30 | 2026-03-05 23:30 | 2026-03-06 00:30 | 2026-03-24 23:30 | 4 | 4
A6860 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11 | LT: Vibration Monitoring System | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A6870 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11.1.2.2.6.11.10 | AoS: Vibration Monitoring System for Secondary dedusting ID Fan | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-27 00:30 | 0 | 0
A6880 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.11.1.2.2.6.11.10 | AoS: Vibration Monitoring System for Secondary dedusting ID Fan Motor | 2026-03-27 00:30 | 2026-03-27 00:30 | 2026-03-29 00:30 | 2026-04-13 00:30 | 0 | 0
A6890 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | BE.s: MV drives | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-03-03 00:30 | 2025-06-14 23:30 | 88 | 88
A6900 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | BE.a: MV drives | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-05 23:30 | 102 | 102
A6910 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DE.s: MV drives | 2025-07-18 00:30 | 2025-09-15 23:30 | 2025-07-18 00:30 | 2025-09-10 23:30 | 59 | 59
A6920 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DE.a/i: MV drives | 2025-02-26 00:30 | 2025-09-29 23:30 | 2025-02-26 00:30 | 2025-09-29 23:30 | 213 | 213
A6930 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | MAN: MV drives | 2025-09-17 00:30 | 2026-02-14 23:30 | 2025-09-19 00:30 | 2026-03-03 23:30 | 148 | 148
A6940 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | INSP: MV drives | 2026-02-15 00:30 | 2026-02-28 23:30 | 2026-02-15 00:30 | 2026-02-24 23:30 | 14 | 14
A6950 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DCC.a: MV drives | 2026-03-01 00:30 | 2026-03-03 23:30 | 2026-03-01 00:30 | 2026-03-03 23:30 | 3 | 3
A6960 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | DCC.r: MV drives | 2026-03-04 00:30 | 2026-03-07 23:30 | 2026-03-09 00:30 | 2026-03-18 23:30 | 4 | 4
A6970 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1 | LT: MV drives | 2025-02-26 00:30 | 2026-03-28 23:30 | 2025-02-26 00:30 | 2026-03-28 23:30 | 390 | 390
A6980 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.1.1.2.2.6.12.1.10 | AoS: MV VVVF Drive for Secondary Deusting ID Fan | 2026-03-29 00:30 | 2026-03-29 00:30 | 2026-03-29 00:30 | 2026-03-29 00:30 | 0 | 0
A6990 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | BE.s: MV motors | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-26 23:30 | 88 | 88
A7000 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | BE.a: MV motors | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-07 23:30 | 102 | 102
A7010 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DE.s: MV motors | 2025-07-18 00:30 | 2025-09-15 23:30 | 2025-07-18 00:30 | 2025-09-15 23:30 | 59 | 59
A7020 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DE.a/i: MV motors | 2025-02-26 00:30 | 2025-09-29 23:30 | 2025-02-26 00:30 | 2025-09-29 23:30 | 213 | 213
A7030 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | MAN: MV motors | 2025-09-17 00:30 | 2026-02-14 23:30 | 2025-09-17 00:30 | 2026-02-12 23:30 | 148 | 148
A7040 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | INSP: MV motors | 2026-02-15 00:30 | 2026-02-28 23:30 | 2026-02-15 00:30 | 2026-02-28 23:30 | 14 | 14
A7050 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DCC.a: MV motors | 2026-03-01 00:30 | 2026-03-03 23:30 | 2026-03-01 00:30 | 2026-03-03 23:30 | 3 | 3
A7060 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | DCC.r: MV motors | 2026-03-04 00:30 | 2026-03-07 23:30 | 2026-03-04 00:30 | 2026-03-07 23:30 | 4 | 4
A7070 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2 | LT: MV motors | 2025-02-26 00:30 | 2026-03-28 23:30 | 2025-02-26 00:30 | 2026-03-28 23:30 | 390 | 390
A7080 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.12.1.2.2.6.12.2.1.2.2.6.12.2.10 | AoS: MV Motor for Secondary Deusting ID Fan | 2026-03-29 00:30 | 2026-03-29 00:30 | 2026-03-29 00:30 | 2026-03-29 00:30 | 0 | 0
A7090 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | BE.s: Variable speed motors | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-26 23:30 | 88 | 88
A7100 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | BE.a: Variable speed motors | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-09 23:30 | 102 | 102
A7110 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DE.s: Variable speed motors | 2025-07-18 00:30 | 2025-09-30 23:30 | 2025-07-18 00:30 | 2025-09-30 23:30 | 74 | 74
A7120 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DE.a/i: Variable speed motors | 2025-02-26 00:30 | 2025-10-18 23:30 | 2025-03-03 00:30 | 2025-11-02 23:30 | 231 | 231
A7130 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | MAN: Variable speed motors | 2025-09-18 00:30 | 2026-02-17 23:30 | 2025-09-23 00:30 | 2026-02-20 23:30 | 150 | 150
A7140 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | INSP: Variable speed motors | 2026-02-18 00:30 | 2026-02-25 23:30 | 2026-02-18 00:30 | 2026-02-25 23:30 | 8 | 8
A7150 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DCC.a: Variable speed motors | 2026-02-26 00:30 | 2026-02-28 23:30 | 2026-02-26 00:30 | 2026-02-28 23:30 | 3 | 3
A7160 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | DCC.r: Variable speed motors | 2026-03-01 00:30 | 2026-03-04 23:30 | 2026-03-01 00:30 | 2026-03-04 23:30 | 4 | 4
A7170 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1 | LT: Variable speed motors | 2025-02-26 00:30 | 2026-03-25 23:30 | 2025-03-03 00:30 | 2026-04-10 23:30 | 387 | 387
A7180 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.13.1.2.2.6.13.1.1.2.2.6.13.1.10 | AoS: Low Voltage Variable Speed Motors | 2026-03-26 00:30 | 2026-03-26 00:30 | 2026-03-26 00:30 | 2026-03-21 00:30 | 0 | 0
A7190 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | BE.s: Motor starter panels | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-03-02 00:30 | 2025-06-05 23:30 | 88 | 88
A7200 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | BE.a: Motor starter panels | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-09 23:30 | 102 | 102
A7210 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DE.s: Motor starter panels | 2025-07-18 00:30 | 2025-09-15 23:30 | 2025-07-18 00:30 | 2025-09-15 23:30 | 59 | 59
A7220 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DE.a/i: Motor starter panels | 2025-02-26 00:30 | 2025-09-29 23:30 | 2025-02-26 00:30 | 2025-09-29 23:30 | 213 | 213
A7230 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | MAN: Motor starter panels | 2025-09-12 00:30 | 2026-01-23 23:30 | 2025-09-12 00:30 | 2026-01-23 23:30 | 131 | 131
A7240 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | INSP: Motor starter panels | 2026-01-24 00:30 | 2026-02-06 23:30 | 2026-01-24 00:30 | 2026-02-02 23:30 | 14 | 14
A7250 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DCC.a: Motor starter panels | 2026-02-07 00:30 | 2026-02-09 23:30 | 2026-02-07 00:30 | 2026-02-05 23:30 | 3 | 3
A7260 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | DCC.r: Motor starter panels | 2026-02-10 00:30 | 2026-02-13 23:30 | 2026-02-11 00:30 | 2026-03-05 23:30 | 4 | 4
A7270 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14 | LT: Motor starter panels | 2025-02-26 00:30 | 2026-03-06 23:30 | 2025-02-27 00:30 | 2026-03-09 23:30 | 368 | 368
A7280 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: Motor Control Center (MCC) for ESP | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-05 00:30 | 0 | 0
A7290 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: MCC for Doghouse & Dampers for Converters # 1 | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-08 00:30 | 2026-03-15 00:30 | 0 | 0
A7300 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: MCC for Doghouse & Dampers for Converters # 2 | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-07 00:30 | 0 | 0
A7310 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.14.1.2.2.6.14.10 | AoS: Standalone Soft-starter panel for MHS Booster Fan | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-07 00:30 | 2026-03-07 00:30 | 0 | 0
A7320 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | BE.s: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-05-11 23:30 | 2025-02-26 00:30 | 2025-05-11 23:30 | 73 | 73
A7330 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | BE.a: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-05-25 23:30 | 2025-02-26 00:30 | 2025-05-25 23:30 | 87 | 87
A7340 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DE.s: Medium Voltage Distribution Board | 2025-07-10 00:30 | 2025-09-07 23:30 | 2025-07-14 00:30 | 2025-09-18 23:30 | 59 | 59
A7350 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DE.a/i: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2025-09-21 23:30 | 2025-02-26 00:30 | 2025-09-21 23:30 | 205 | 205
A7360 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | MAN: Medium Voltage Distribution Board | 2025-09-03 00:30 | 2026-01-14 23:30 | 2025-09-03 00:30 | 2026-01-14 23:30 | 131 | 131
A7370 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | INSP: Medium Voltage Distribution Board | 2026-01-15 00:30 | 2026-01-28 23:30 | 2026-01-15 00:30 | 2026-01-28 23:30 | 14 | 14
A7380 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DCC.a: Medium Voltage Distribution Board | 2026-01-29 00:30 | 2026-01-31 23:30 | 2026-01-29 00:30 | 2026-01-28 23:30 | 3 | 3
A7390 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | DCC.r: Medium Voltage Distribution Board | 2026-02-01 00:30 | 2026-02-04 23:30 | 2026-02-01 00:30 | 2026-02-04 23:30 | 4 | 4
A7400 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15 | LT: Medium Voltage Distribution Board | 2025-02-26 00:30 | 2026-02-25 23:30 | 2025-02-26 00:30 | 2026-02-25 23:30 | 359 | 359
A7410 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: 11kV Isolator (VCB without protection), | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-27 00:30 | 2026-03-02 00:30 | 0 | 0
A7420 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: Retrofitting job in existing 11 kV HT Boards at 15 RP | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-27 00:30 | 2026-03-07 00:30 | 0 | 0
A7430 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: Retrofitting job in existing 11 kV HT Boards at MSDS-VI | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-24 00:30 | 0 | 0
A7440 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.15.1.2.2.6.15.10 | AoS: One Laptop, licensed software along with communication cable for programming and testing the numerical relay. | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 0 | 0
A7450 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | BE.s: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-05-11 23:30 | 2025-02-26 00:30 | 2025-05-06 23:30 | 73 | 73
A7460 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | BE.a: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-05-25 23:30 | 2025-03-01 00:30 | 2025-06-11 23:30 | 87 | 87
A7470 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DE.s: Low Voltage Distribution (Load center) | 2025-07-10 00:30 | 2025-09-07 23:30 | 2025-07-15 00:30 | 2025-09-15 23:30 | 59 | 59
A7480 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DE.a/i: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2025-09-21 23:30 | 2025-02-26 00:30 | 2025-09-20 23:30 | 205 | 205
A7490 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | MAN: Low Voltage Distribution (Load center) | 2025-09-03 00:30 | 2026-01-14 23:30 | 2025-09-06 00:30 | 2026-01-22 23:30 | 131 | 131
A7500 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | INSP: Low Voltage Distribution (Load center) | 2026-01-15 00:30 | 2026-01-28 23:30 | 2026-01-15 00:30 | 2026-01-28 23:30 | 14 | 14
A7510 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DCC.a: Low Voltage Distribution (Load center) | 2026-01-29 00:30 | 2026-01-31 23:30 | 2026-01-29 00:30 | 2026-01-31 23:30 | 3 | 3
A7520 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | DCC.r: Low Voltage Distribution (Load center) | 2026-02-01 00:30 | 2026-02-04 23:30 | 2026-02-01 00:30 | 2026-02-04 23:30 | 4 | 4
A7530 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16 | LT: Low Voltage Distribution (Load center) | 2025-02-26 00:30 | 2026-02-25 23:30 | 2025-02-26 00:30 | 2026-02-21 23:30 | 359 | 359
A7540 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16.1.2.2.6.16.10 | AoS: Modification in existing 3x800A and 6x 630A feeders of LT Substation-1, if any | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 0 | 0
A7550 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.16.1.2.2.6.16.10 | AoS: Power Distribution Board (PDB: Aux) | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-26 00:30 | 2026-02-25 00:30 | 0 | 0
A7560 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | BE.s: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-24 23:30 | 88 | 88
A7570 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | BE.a: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-09 23:30 | 102 | 102
A7580 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DE.s: Automation Power Supply Systems | 2025-08-02 00:30 | 2025-09-30 23:30 | 2025-08-07 00:30 | 2025-10-06 23:30 | 59 | 59
A7590 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DE.a/i: Automation Power Supply Systems | 2025-02-26 00:30 | 2025-10-18 23:30 | 2025-03-03 00:30 | 2025-11-01 23:30 | 231 | 231
A7600 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | MAN: Automation Power Supply Systems | 2025-10-04 00:30 | 2026-02-02 23:30 | 2025-10-04 00:30 | 2026-02-02 23:30 | 120 | 120
A7610 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | INSP: Automation Power Supply Systems | 2026-02-03 00:30 | 2026-02-11 23:30 | 2026-02-03 00:30 | 2026-02-11 23:30 | 9 | 9
A7620 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DCC.a: Automation Power Supply Systems | 2026-02-12 00:30 | 2026-02-14 23:30 | 2026-02-12 00:30 | 2026-02-11 23:30 | 3 | 3
A7630 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | DCC.r: Automation Power Supply Systems | 2026-02-15 00:30 | 2026-02-18 23:30 | 2026-02-15 00:30 | 2026-02-18 23:30 | 4 | 4
A7640 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17 | LT: Automation Power Supply Systems | 2025-02-26 00:30 | 2026-03-11 23:30 | 2025-02-26 00:30 | 2026-03-11 23:30 | 373 | 373
A7650 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17.1.2.2.6.17.10 | AoS: Uninterruptable Power Supply (UPS) & Main Distribution Board | 2026-03-12 00:30 | 2026-03-12 00:30 | 2026-03-12 00:30 | 2026-03-12 00:30 | 0 | 0
A7660 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.17.1.2.2.6.17.10 | AoS: UPS Sub Distribution Board | 2026-03-12 00:30 | 2026-03-12 00:30 | 2026-03-12 00:30 | 2026-03-12 00:30 | 0 | 0
A7670 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | BE.s: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-05-24 23:30 | 2025-02-26 00:30 | 2025-05-24 23:30 | 86 | 86
A7680 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | BE.a: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-06-07 23:30 | 2025-02-28 00:30 | 2025-06-24 23:30 | 100 | 100
A7690 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DE.s: Power cables (HT&LT) | 2025-06-08 00:30 | 2025-10-10 23:30 | 2025-06-08 00:30 | 2025-10-10 23:30 | 123 | 123
A7700 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DE.a/i: Power cables (HT&LT) | 2025-02-26 00:30 | 2025-10-29 23:30 | 2025-02-26 00:30 | 2025-10-26 23:30 | 241 | 241
A7710 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | MAN: Power cables (HT&LT) | 2025-08-09 00:30 | 2026-01-28 23:30 | 2025-08-09 00:30 | 2026-01-23 23:30 | 169 | 169
A7720 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | INSP: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-11 23:30 | 2025-03-02 00:30 | 2026-02-28 23:30 | 345 | 345
A7730 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DCC.a: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-14 23:30 | 2025-03-01 00:30 | 2026-02-25 23:30 | 348 | 348
A7740 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | DCC.r: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-02-18 23:30 | 2025-03-01 00:30 | 2026-02-23 23:30 | 352 | 352
A7750 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1 | LT: Power cables (HT&LT) | 2025-02-26 00:30 | 2026-03-11 23:30 | 2025-03-02 00:30 | 2026-03-21 23:30 | 373 | 373
A7760 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1.1.2.2.6.18.1.10 | AoS: Power cables (HT) | 2025-06-28 00:30 | 2026-03-11 23:30 | 2025-06-28 00:30 | 2026-03-07 23:30 | 253 | 253
A7770 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.1.1.2.2.6.18.1.10 | AoS: Power cables (LT) | 2025-06-28 00:30 | 2026-03-11 23:30 | 2025-06-28 00:30 | 2026-03-11 23:30 | 253 | 253
A7780 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | BE.s: Other misc. cables | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-26 23:30 | 88 | 88
A7790 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | BE.a: Other misc. cables | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-09 23:30 | 102 | 102
A7800 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DE.s: Other misc. cables | 2025-07-30 00:30 | 2025-10-27 23:30 | 2025-07-30 00:30 | 2025-10-27 23:30 | 87 | 87
A7810 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DE.a/i: Other misc. cables | 2025-02-26 00:30 | 2025-11-10 23:30 | 2025-02-26 00:30 | 2025-11-10 23:30 | 253 | 253
A7820 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | MAN: Other misc. cables | 2025-09-29 00:30 | 2026-02-09 23:30 | 2025-09-29 00:30 | 2026-02-09 23:30 | 131 | 131
A7830 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | INSP: Other misc. cables | 2025-02-26 00:30 | 2026-02-23 23:30 | 2025-02-26 00:30 | 2026-02-23 23:30 | 357 | 357
A7840 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DCC.a: Other misc. cables | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-23 23:30 | 360 | 360
A7850 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | DCC.r: Other misc. cables | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-02-25 23:30 | 364 | 364
A7860 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2 | LT: Other misc. cables | 2025-02-26 00:30 | 2026-03-23 23:30 | 2025-02-28 00:30 | 2026-03-28 23:30 | 385 | 385
A7870 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Control and Signal Cables | 2025-06-26 00:30 | 2026-03-23 23:30 | 2025-06-26 00:30 | 2026-03-19 23:30 | 267 | 267
A7880 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Automation & Networking Cable | 2025-06-26 00:30 | 2026-03-23 23:30 | 2025-06-26 00:30 | 2026-03-21 23:30 | 267 | 267
A7890 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.18.1.2.2.6.18.2.1.2.2.6.18.2.10 | AoS: Cables for ACVS, Illumination etc. | 2025-06-26 00:30 | 2026-03-23 23:30 | 2025-06-26 00:30 | 2026-03-19 23:30 | 267 | 267
A1750 | In Progress | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6.1.2.2.4.1.6.6 | AoS: Dog house door front side/ back side rail | 2025-02-26 00:30 | 2026-06-26 23:30 | 2025-02-28 00:30 |  | 480 | 481
A1690 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | MAN: Dog house unit (Converter-2) | 2025-11-20 00:30 | 2026-05-15 23:30 | 2025-11-20 00:30 | 2026-05-15 23:30 | 176 | 176
A1700 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | INSP: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-05-29 23:30 | 2025-02-26 00:30 | 2026-05-29 23:30 | 452 | 452
A1710 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | DCC.a: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-01 23:30 | 2025-02-26 00:30 | 2026-05-29 23:30 | 455 | 455
A1720 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | DCC.r: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-05 23:30 | 2025-02-26 00:30 | 2026-06-02 23:30 | 459 | 459
A1730 | In Progress | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6 | LT: Dog house unit (Converter-2) | 2025-02-26 00:30 | 2026-06-26 23:30 | 2025-03-08 00:30 |  | 480 | 473
A1740 | In Progress | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.6.1.2.2.4.1.6.6 | AoS: Dog house unit | 2025-02-26 00:30 | 2026-06-26 23:30 | 2025-03-11 00:30 |  | 480 | 470
A1850 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | MAN: Dog house unit drive (Converter-2) | 2025-12-07 00:30 | 2026-04-12 23:30 | 2025-12-07 00:30 | 2026-04-09 23:30 | 126 | 126
A1860 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | INSP: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-23 23:30 | 419 | 419
A1870 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | DCC.a: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-04-29 23:30 | 2025-02-26 00:30 | 2026-04-29 23:30 | 422 | 422
A1880 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | DCC.r: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-05-02 23:30 | 2025-02-26 00:30 | 2026-05-02 23:30 | 425 | 425
A1890 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.6 | LT: Dog house unit drive (Converter-2) | 2025-02-26 00:30 | 2026-05-23 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 446 | 446
A1910 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.2.1.2.2.4.2.8 | AoS: Dog house unit drive | 2026-05-24 00:30 | 2026-05-24 00:30 | 2026-05-24 00:30 | 2026-05-24 00:30 | 0 | 0
A2410 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Structure (for Weather Protection) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-18 23:30 | 443 | 443
A2330 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Rotary valve (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2340 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Expansion joints (at dust hoppers of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-17 23:30 | 443 | 443
A2350 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Dust hoppers (of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-15 23:30 | 443 | 443
A2360 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: HV Insulator system (of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-19 23:30 | 443 | 443
A2370 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Heating elements (for HV insulators of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-28 00:30 | 2026-06-01 23:30 | 443 | 443
A2380 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Transformer rectifier (HFTR - 1 field, advance controller - all field) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2390 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Technological internals (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2400 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Weather protection over TR Bay | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-18 23:30 | 443 | 443
A2190 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | MAN: Square shape ESP unit (dry type) (Unit-2) | 2025-09-16 00:30 | 2026-04-08 23:30 | 2025-09-16 00:30 | 2026-04-08 23:30 | 202 | 202
A2200 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | INSP: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-22 23:30 | 2025-03-01 00:30 | 2026-05-12 23:30 | 415 | 415
A2210 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | DCC.a: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-25 23:30 | 2025-02-26 00:30 | 2026-04-23 23:30 | 418 | 418
A2220 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | DCC.r: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-04-29 23:30 | 2025-02-26 00:30 | 2026-04-25 23:30 | 422 | 422
A2230 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6 | LT: Square shape ESP unit (dry type) (Unit-2) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2240 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Access (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2250 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Support structure (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2260 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Motorized Guillotine dampers (for inlet at each pass) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2270 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Motorized Guillotine dampers (for outlet at each pass) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2280 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Gas inlet and outlet cone (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-03-02 00:30 | 2026-05-31 23:30 | 443 | 443
A2290 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Expansion joint (for duct of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2300 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Casing (for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2310 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Heating elements (for dust hoppers of ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-20 23:30 | 443 | 443
A2320 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.6.1.2.2.4.3.6.6 | AoS: Manual slide gate (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-05-20 23:30 | 2025-02-26 00:30 | 2026-05-19 23:30 | 443 | 443
A3560 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6.1.2.2.4.10.6.6 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-05-22 23:30 | 2025-06-26 00:30 | 2026-05-22 23:30 | 327 | 327
A3570 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6.1.2.2.4.10.6.6 | AoS: ID fan | 2025-06-26 00:30 | 2026-05-22 23:30 | 2025-06-27 00:30 | 2026-06-03 23:30 | 327 | 327
A3440 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | MAN: ID fan station (Fan-2) | 2025-09-16 00:30 | 2026-02-09 23:30 | 2025-09-21 00:30 | 2026-02-15 23:30 | 144 | 144
A3450 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | INSP: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-02-23 23:30 | 2025-03-03 00:30 | 2026-03-05 23:30 | 357 | 357
A3460 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.a: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-26 23:30 | 360 | 360
A3470 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.r: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-03-03 00:30 | 2026-03-14 23:30 | 364 | 364
A3480 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | LT: ID fan station (Fan-2) | 2025-02-26 00:30 | 2026-03-23 23:30 | 2025-03-03 00:30 | 2026-04-04 23:30 | 385 | 385
A3490 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.12 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-03-23 23:30 | 2025-06-26 00:30 | 2026-03-18 23:30 | 267 | 267
A3500 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.12 | AoS: ID fan | 2025-06-26 00:30 | 2026-03-23 23:30 | 2025-06-28 00:30 | 2026-03-29 23:30 | 267 | 267
A3510 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | MAN: ID fan station (Fan-3) | 2025-10-17 00:30 | 2026-04-10 23:30 | 2025-10-17 00:30 | 2026-04-07 23:30 | 174 | 174
A3520 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | INSP: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-04-24 23:30 | 2025-02-26 00:30 | 2026-04-22 23:30 | 417 | 417
A3530 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | DCC.a: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-04-27 23:30 | 2025-02-26 00:30 | 2026-04-27 23:30 | 420 | 420
A3540 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | DCC.r: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-05-01 23:30 | 2025-02-26 00:30 | 2026-04-29 23:30 | 424 | 424
A3550 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.6 | LT: ID fan station (Fan-3) | 2025-02-26 00:30 | 2026-05-22 23:30 | 2025-02-26 00:30 | 2026-05-22 23:30 | 445 | 445
A3860 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of charging fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A3850 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of charging fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-24 23:30 | 450 | 450
A3900 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of tapping fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A3890 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of tapping fume suction (Converter-2) | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A7900 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | BE.s: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-05-13 23:30 | 2025-02-26 00:30 | 2025-05-13 23:30 | 75 | 75
A7910 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | BE.a: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-05-27 23:30 | 2025-02-28 00:30 | 2025-06-01 23:30 | 89 | 89
A7920 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DE.s: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-08-11 00:30 | 2025-11-06 23:30 | 2025-08-15 00:30 | 2025-11-15 23:30 | 85 | 85
A7930 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DE.a/i: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2025-11-20 23:30 | 2025-02-26 00:30 | 2025-11-20 23:30 | 263 | 263
A7940 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | MAN: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-09-26 00:30 | 2026-01-20 23:30 | 2025-09-26 00:30 | 2026-01-20 23:30 | 114 | 114
A7950 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | INSP: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-03 23:30 | 2025-02-26 00:30 | 2026-02-03 23:30 | 337 | 337
A7960 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DCC.a: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-06 23:30 | 2025-02-26 00:30 | 2026-02-06 23:30 | 340 | 340
A7970 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | DCC.r: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-02-10 23:30 | 2025-02-26 00:30 | 2026-02-10 23:30 | 344 | 344
A7980 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | LT: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-02-26 00:30 | 2026-03-03 23:30 | 2025-02-26 00:30 | 2026-03-03 23:30 | 365 | 365
A7990 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.1 | AoS: Cable Trays/Supports/Angles/ Channels/ Pipe /Conduits | 2025-06-26 00:30 | 2026-03-03 23:30 | 2025-06-30 00:30 | 2026-03-15 23:30 | 247 | 247
A8000 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | BE.s: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-02-26 00:30 | 2025-06-10 23:30 | 103 | 103
A8010 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | BE.a: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-20 23:30 | 117 | 117
A8020 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DE.s: Impulse tubes & fittings for Instruments | 2025-06-25 00:30 | 2025-08-23 23:30 | 2025-06-30 00:30 | 2025-09-11 23:30 | 59 | 59
A8030 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DE.a/i: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2025-09-06 23:30 | 2025-02-26 00:30 | 2025-09-06 23:30 | 190 | 190
A8040 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | MAN: Impulse tubes & fittings for Instruments | 2025-09-08 00:30 | 2026-01-04 23:30 | 2025-09-08 00:30 | 2026-01-04 23:30 | 116 | 116
A8050 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | INSP: Impulse tubes & fittings for Instruments | 2026-01-05 00:30 | 2026-01-18 23:30 | 2026-01-05 00:30 | 2026-01-18 23:30 | 14 | 14
A8060 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DCC.a: Impulse tubes & fittings for Instruments | 2026-01-19 00:30 | 2026-01-21 23:30 | 2026-01-19 00:30 | 2026-01-21 23:30 | 3 | 3
A8070 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | DCC.r: Impulse tubes & fittings for Instruments | 2026-01-22 00:30 | 2026-01-25 23:30 | 2026-01-22 00:30 | 2026-01-25 23:30 | 4 | 4
A8080 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | LT: Impulse tubes & fittings for Instruments | 2025-02-26 00:30 | 2026-02-11 23:30 | 2025-02-26 00:30 | 2026-02-11 23:30 | 345 | 345
A8090 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.2 | AoS: Impulse tubes & fittings for Instruments | 2026-02-12 00:30 | 2026-02-12 00:30 | 2026-02-12 00:30 | 2026-02-12 00:30 | 0 | 0
A8100 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | BE.s: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-05-11 23:30 | 2025-03-01 00:30 | 2025-05-14 23:30 | 73 | 73
A8110 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | BE.a: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-05-25 23:30 | 2025-02-26 00:30 | 2025-05-23 23:30 | 87 | 87
A8120 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DE.s: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-05-26 00:30 | 2025-10-23 23:30 | 2025-05-26 00:30 | 2025-10-23 23:30 | 148 | 148
A8130 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DE.a/i: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2025-11-06 23:30 | 2025-02-26 00:30 | 2025-11-03 23:30 | 249 | 249
A8140 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | MAN: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-07-10 00:30 | 2026-02-05 23:30 | 2025-07-10 00:30 | 2026-02-05 23:30 | 207 | 207
A8150 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | INSP: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-19 23:30 | 2025-02-26 00:30 | 2026-02-15 23:30 | 353 | 353
A8160 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DCC.a: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-22 23:30 | 2025-03-01 00:30 | 2026-03-12 23:30 | 356 | 356
A8170 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | DCC.r: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-26 23:30 | 360 | 360
A8180 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | LT: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A8190 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.19.1.2.2.6.19.3 | AoS: Junction Boxes (CJB, PJB), Terminal Boxes, Transmitter Protection Boxes | 2025-06-26 00:30 | 2026-03-19 23:30 | 2025-06-26 00:30 | 2026-03-19 23:30 | 263 | 263
A8200 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | BE.s: Special tools | 2025-02-26 00:30 | 2025-07-10 23:30 | 2025-02-26 00:30 | 2025-07-10 23:30 | 133 | 133
A8210 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | BE.a: Special tools | 2025-02-26 00:30 | 2025-07-24 23:30 | 2025-02-26 00:30 | 2025-07-24 23:30 | 147 | 147
A8220 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DE.s: Special tools | 2025-10-19 00:30 | 2025-12-13 23:30 | 2025-10-19 00:30 | 2025-12-13 23:30 | 55 | 55
A8230 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DE.a/i: Special tools | 2025-02-26 00:30 | 2026-01-02 23:30 | 2025-02-26 00:30 | 2025-12-29 23:30 | 305 | 305
A8240 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | MAN: Special tools | 2026-01-03 00:30 | 2026-03-27 23:30 | 2026-01-04 00:30 | 2026-04-16 23:30 | 84 | 84
A8250 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | INSP: Special tools | 2026-03-28 00:30 | 2026-04-10 23:30 | 2026-03-28 00:30 | 2026-04-10 23:30 | 14 | 14
A8260 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DCC.a: Special tools | 2026-04-11 00:30 | 2026-04-13 23:30 | 2026-04-11 00:30 | 2026-04-13 23:30 | 3 | 3
A8270 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | DCC.r: Special tools | 2026-04-14 00:30 | 2026-04-17 23:30 | 2026-04-14 00:30 | 2026-04-17 23:30 | 4 | 4
A8280 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20 | LT: Special tools | 2025-02-26 00:30 | 2026-05-08 23:30 | 2025-03-03 00:30 | 2026-05-23 23:30 | 431 | 431
A8290 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.20.1.2.2.6.20.10 | AoS: Universal HART calibrator | 2026-05-09 00:30 | 2026-05-09 00:30 | 2026-05-14 00:30 | 2026-05-12 00:30 | 0 | 0
A8300 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | BE.s: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-06-10 23:30 | 2025-02-26 00:30 | 2025-06-10 23:30 | 103 | 103
A8310 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | BE.a: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-06-24 23:30 | 2025-02-26 00:30 | 2025-06-24 23:30 | 117 | 117
A8320 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DE.s: Lighting And Socket Systems incl. Cables | 2025-08-03 00:30 | 2025-10-01 23:30 | 2025-08-03 00:30 | 2025-09-26 23:30 | 59 | 59
A8330 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DE.a/i: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2025-10-19 23:30 | 2025-02-27 00:30 | 2025-11-05 23:30 | 232 | 232
A8340 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | MAN: Lighting And Socket Systems incl. Cables | 2025-09-19 00:30 | 2026-01-19 23:30 | 2025-09-19 00:30 | 2026-01-19 23:30 | 120 | 120
A8350 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | INSP: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-03 23:30 | 2025-02-26 00:30 | 2026-01-31 23:30 | 337 | 337
A8360 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DCC.a: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-06 23:30 | 2025-02-26 00:30 | 2026-02-06 23:30 | 340 | 340
A8370 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | DCC.r: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-02-10 23:30 | 2025-02-26 00:30 | 2026-02-09 23:30 | 344 | 344
A8380 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21 | LT: Lighting And Socket Systems incl. Cables | 2025-02-26 00:30 | 2026-03-03 23:30 | 2025-02-26 00:30 | 2026-03-03 23:30 | 365 | 365
A8390 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Room Lighting System | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-03-01 23:30 | 245 | 245
A8400 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Machine Lighting System | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-02-28 23:30 | 245 | 245
A8410 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Emergency Lighting Systems | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-02-26 23:30 | 245 | 245
A8420 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Outdoor/ Area Lighting Systems | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-03-03 23:30 | 245 | 245
A8430 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Standard Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-03-03 23:30 | 245 | 245
A8440 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Safety Extra-Low Voltage Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-07-02 00:30 | 2026-03-09 23:30 | 245 | 245
A8450 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Welding Socket Outlets | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-07-02 00:30 | 2026-03-10 23:30 | 245 | 245
A8460 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Lighting Transformer | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-07-03 00:30 | 2026-03-15 23:30 | 245 | 245
A8470 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: MLDB & SLDBs | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-02-27 23:30 | 245 | 245
A8480 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Welding Distribution Board (WDB) | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-30 00:30 | 2026-03-21 23:30 | 245 | 245
A8490 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.21.1.2.2.6.21.10 | AoS: Aviation Lighting for Secondary Dedusting Stack | 2025-06-28 00:30 | 2026-03-03 23:30 | 2025-06-28 00:30 | 2026-03-03 23:30 | 245 | 245
A8500 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | BE.s: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2025-06-25 23:30 | 2025-02-26 00:30 | 2025-06-25 23:30 | 118 | 118
A8510 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | BE.a: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-09 23:30 | 132 | 132
A8520 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DE.s: Industrial TV Systems (CCTV system) including cable | 2025-10-19 00:30 | 2025-12-15 23:30 | 2025-10-19 00:30 | 2025-12-13 23:30 | 57 | 57
A8530 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DE.a/i: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2026-01-04 23:30 | 2025-03-02 00:30 | 2026-01-15 23:30 | 307 | 307
A8540 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | MAN: Industrial TV Systems (CCTV system) including cable | 2025-12-06 00:30 | 2026-03-05 23:30 | 2025-12-06 00:30 | 2026-03-05 23:30 | 89 | 89
A8550 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | INSP: Industrial TV Systems (CCTV system) including cable | 2026-03-06 00:30 | 2026-03-13 23:30 | 2026-03-07 00:30 | 2026-03-24 23:30 | 8 | 8
A8560 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DCC.a: Industrial TV Systems (CCTV system) including cable | 2026-03-14 00:30 | 2026-03-16 23:30 | 2026-03-14 00:30 | 2026-03-16 23:30 | 3 | 3
A8570 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | DCC.r: Industrial TV Systems (CCTV system) including cable | 2026-03-17 00:30 | 2026-03-20 23:30 | 2026-03-17 00:30 | 2026-03-20 23:30 | 4 | 4
A8580 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | LT: Industrial TV Systems (CCTV system) including cable | 2025-02-26 00:30 | 2026-04-10 23:30 | 2025-02-26 00:30 | 2026-04-06 23:30 | 403 | 403
A8590 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.1 | AoS: Industrial TV Systems (CCTV system) including cable | 2026-04-11 00:30 | 2026-04-11 00:30 | 2026-04-16 00:30 | 2026-04-28 00:30 | 0 | 0
A8600 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | BE.s: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2025-06-25 23:30 | 2025-02-26 00:30 | 2025-06-25 23:30 | 118 | 118
A8610 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | BE.a: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-09 23:30 | 132 | 132
A8620 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DE.s: Plant Telephone Systems including cable | 2025-10-19 00:30 | 2025-12-15 23:30 | 2025-10-23 00:30 | 2025-12-30 23:30 | 57 | 57
A8630 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DE.a/i: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2026-01-04 23:30 | 2025-02-28 00:30 | 2026-01-13 23:30 | 307 | 307
A8640 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | MAN: Plant Telephone Systems including cable | 2025-12-06 00:30 | 2026-03-05 23:30 | 2025-12-06 00:30 | 2026-03-03 23:30 | 89 | 89
A8650 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | INSP: Plant Telephone Systems including cable | 2026-03-06 00:30 | 2026-03-13 23:30 | 2026-03-07 00:30 | 2026-03-29 23:30 | 8 | 8
A8660 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DCC.a: Plant Telephone Systems including cable | 2026-03-14 00:30 | 2026-03-16 23:30 | 2026-03-14 00:30 | 2026-03-16 23:30 | 3 | 3
A8670 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | DCC.r: Plant Telephone Systems including cable | 2026-03-17 00:30 | 2026-03-20 23:30 | 2026-03-17 00:30 | 2026-03-20 23:30 | 4 | 4
A8680 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | LT: Plant Telephone Systems including cable | 2025-02-26 00:30 | 2026-04-10 23:30 | 2025-03-02 00:30 | 2026-04-25 23:30 | 403 | 403
A8690 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.22.1.2.2.6.22.2 | AoS: Plant Telephone Systems including cable | 2026-04-11 00:30 | 2026-04-11 00:30 | 2026-04-15 00:30 | 2026-04-18 00:30 | 0 | 0
A8700 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | BE.s: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-06-25 23:30 | 2025-03-03 00:30 | 2025-07-02 23:30 | 118 | 118
A8710 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | BE.a: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-27 00:30 | 2025-07-22 23:30 | 132 | 132
A8720 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DE.s: Power feeding of Heating-, Ventilation, Aircondition | 2025-08-30 00:30 | 2025-10-27 23:30 | 2025-08-31 00:30 | 2025-11-13 23:30 | 57 | 57
A8730 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DE.a/i: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2025-11-10 23:30 | 2025-02-26 00:30 | 2025-11-06 23:30 | 253 | 253
A8740 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | MAN: Power feeding of Heating-, Ventilation, Aircondition | 2025-10-15 00:30 | 2026-02-08 23:30 | 2025-10-15 00:30 | 2026-02-08 23:30 | 115 | 115
A8750 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | INSP: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-09 00:30 | 2026-02-22 23:30 | 2026-02-09 00:30 | 2026-02-22 23:30 | 14 | 14
A8760 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DCC.a: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-23 00:30 | 2026-02-25 23:30 | 2026-02-24 00:30 | 2026-03-04 23:30 | 3 | 3
A8770 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | DCC.r: Power feeding of Heating-, Ventilation, Aircondition | 2026-02-26 00:30 | 2026-03-01 23:30 | 2026-02-26 00:30 | 2026-03-01 23:30 | 4 | 4
A8780 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | LT: Power feeding of Heating-, Ventilation, Aircondition | 2025-02-26 00:30 | 2026-03-22 23:30 | 2025-03-03 00:30 | 2026-04-04 23:30 | 384 | 384
A8790 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.23.1.2.2.6.23.1 | AoS: Power feeding of Heating-, Ventilation, Aircondition | 2026-03-23 00:30 | 2026-03-23 00:30 | 2026-03-23 00:30 | 2026-03-22 00:30 | 0 | 0
A8820 | Completed | BSL.1.3.1.2.2.1.2.2.7 | Completion of Basic Engineering Submission | 2025-07-14 00:30 | 2025-07-14 00:30 | 2025-07-18 00:30 | 2025-08-03 00:30 | 0 | 0
A8830 | Completed | BSL.1.3.1.2.2.1.2.2.7 | Completion of Basic Engineering Approval | 2025-07-28 00:30 | 2025-07-28 00:30 | 2025-08-02 00:30 | 2025-08-15 00:30 | 0 | 0
A8840 | Completed | BSL.1.3.1.2.2.1.2.2.7 | Completion of Detailed Engineering Submission | 2026-02-13 00:30 | 2026-02-13 00:30 | 2026-02-13 00:30 | 2026-02-13 00:30 | 0 | 0
A8850 | Completed | BSL.1.3.1.2.2.1.2.2.7 | Completion of Detailed Engineering Approval | 2026-03-04 00:30 | 2026-03-04 00:30 | 2026-03-04 00:30 | 2026-03-04 00:30 | 0 | 0
A8860 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Supply (Indigenous) | 2026-07-01 00:30 | 2026-07-01 00:30 |  |  | 0 | 0
A8870 | Not Started | BSL.1.3.1.2.2.1.2.2.7 | Completion of Supply (Perishable) | 2026-06-25 00:30 | 2026-06-25 00:30 |  |  | 0 | 0
A8880 | Completed | BSL.1.3.1.2.3.1.2.3.1 | Construction power available | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-02-26 00:30 | 2025-03-23 23:30 | 28 | 28
A8890 | Completed | BSL.1.3.1.2.3.1.2.3.1 | Construction water available | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-03-02 00:30 | 2025-03-31 23:30 | 28 | 28
A8900 | Completed | BSL.1.3.1.2.3.1.2.3.1 | Drinking water available | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-03-02 00:30 | 2025-04-01 23:30 | 28 | 28
A8910 | Completed | BSL.1.3.1.2.3.1.2.3.1 | Allocation of covered storage area | 2025-02-26 00:30 | 2025-06-25 23:30 | 2025-02-26 00:30 | 2025-06-25 23:30 | 118 | 118
A8920 | Completed | BSL.1.3.1.2.3.1.2.3.1 | Space for Site office available | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-02-26 00:30 | 2025-03-26 23:30 | 28 | 28
A8930 | Completed | BSL.1.3.1.2.3.1.2.3.2 | Permanent Power from Substation available | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-26 23:30 | 419 | 419
A8940 | Completed | BSL.1.3.1.2.3.1.2.3.2 | Make Up Water available at TOP (Flushing and Pressure Testing) | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-26 23:30 | 419 | 419
A8950 | Completed | BSL.1.3.1.2.3.1.2.3.2 | Availability of fire water for fire-fighting | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-26 23:30 | 419 | 419
A8960 | Completed | BSL.1.3.1.2.3.1.2.3.2 | Nitrogen available at TOP (For purging and instrumentation) | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-26 23:30 | 419 | 419
A9010 | Completed | BSL.1.3.1.2.3.1.2.3.4 | CW: Civil Works - Site mobilisation | 2025-02-26 00:30 | 2025-07-25 23:30 | 2025-02-26 00:30 | 2025-07-25 23:30 | 148 | 148
A9020 | Completed | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Dry ESP, ID fan & clean gas stack foundations | 2025-07-26 00:30 | 2026-01-25 23:30 | 2025-07-26 00:30 | 2026-01-25 23:30 | 180 | 180
A9030 | Completed | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Duct support structure foundation and other misc. foundations | 2025-03-29 00:30 | 2026-03-05 23:30 | 2025-03-29 00:30 | 2026-03-05 23:30 | 337 | 337
A9040 | Completed | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Secondary ECR Building | 2025-08-31 00:30 | 2026-04-29 23:30 | 2025-08-31 00:30 | 2026-04-27 23:30 | 239 | 239
A9060 | Completed | BSL.1.3.1.2.3.1.2.3.5 | ERE: Erection Works - Site mobilisation | 2025-02-26 00:30 | 2025-11-15 23:30 | 2025-02-26 00:30 | 2025-11-15 23:30 | 258 | 258
A9070 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Dry ESP (Pass # A) | 2025-11-16 00:30 | 2026-04-24 23:30 | 2025-11-16 00:30 | 2026-04-24 23:30 | 159 | 159
A9090 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary ID fan (Unit # 1) | 2026-03-24 00:30 | 2026-04-25 23:30 | 2026-03-28 00:30 | 2026-05-05 23:30 | 33 | 33
A9110 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Clean gas stack | 2025-11-16 00:30 | 2026-04-30 23:30 | 2025-11-18 00:30 | 2026-05-07 23:30 | 165 | 165
A9120 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Silo unit (incl. conveying) | 2025-11-21 00:30 | 2026-05-03 23:30 | 2025-11-21 00:30 | 2026-05-03 23:30 | 163 | 163
A9130 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary duct with support structure (Unit # 1) | 2025-11-18 00:30 | 2026-05-03 23:30 | 2025-11-18 00:30 | 2026-05-03 23:30 | 166 | 166
A9080 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Dry ESP (Pass # B) | 2025-11-21 00:30 | 2026-07-31 23:30 | 2025-11-21 00:30 |  | 252 | 215
A9160 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Piping works (Unit # 1) | 2025-11-16 00:30 | 2026-05-26 23:30 | 2025-11-16 00:30 | 2026-05-26 23:30 | 191 | 191
A9180 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Pre-assembly works of dog house (Converter # 1) | 2025-11-16 00:30 | 2026-05-21 23:30 | 2025-11-21 00:30 | 2026-06-02 23:30 | 186 | 186
A9190 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Pre-assembly works of dog house (Converter # 2) | 2025-11-16 00:30 | 2026-08-22 23:30 | 2025-11-16 00:30 |  | 279 | 220
A9150 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Other misc. works | 2025-11-19 00:30 | 2026-05-10 23:30 | 2025-11-19 00:30 | 2026-05-10 23:30 | 172 | 172
A9310 | Completed | BSL.1.3.1.2.3.1.2.3.6 | ERE: Erection Works - Site mobilisation | 2025-02-26 00:30 | 2026-01-06 23:30 | 2025-02-26 00:30 | 2026-01-06 23:30 | 309 | 309
A9320 | Completed | BSL.1.3.1.2.3.1.2.3.6 | ERE: Electrical and automation works of Unit # 1 | 2026-01-15 00:30 | 2026-04-30 23:30 | 2026-01-15 00:30 | 2026-04-26 23:30 | 106 | 106
A9340 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ERE: Electrical and automation works of Unit # 2 | 2026-01-07 00:30 | 2026-07-27 23:30 |  |  | 202 | 0
A9380 | In Progress | BSL.1.3.1.2.3.1.2.3.7 | Shutdown of converter # 1 for doghouse, charging and tapping duct erection (incl. mechanical, electrical and refractory | 2026-05-25 00:30 | 2026-06-26 23:30 | 2026-05-31 00:30 |  | 33 | 24
A9440 | Not Started | BSL.1.3.1.2.3.1.2.3.9 | Shutdown of converter # 2 for doghouse, charging and tapping duct erection (incl. mechanical, electrical and refractory | 2026-08-31 00:30 | 2026-09-26 23:30 |  |  | 27 | 0
A9450 | In Progress | BSL.1.3.1.2.3.1.2.3.10 | Testing of equipment | 2026-05-03 00:30 | 2026-09-16 23:30 | 2026-05-03 00:30 |  | 137 | 52
A9460 | Not Started | BSL.1.3.1.2.3.1.2.3.10 | Trial run of equipment | 2026-08-31 00:30 | 2026-10-02 23:30 |  |  | 33 | 0
A9470 | Not Started | BSL.1.3.1.2.3.1.2.3.10 | Hot commissioning (Unit-2) | 2026-10-03 00:30 | 2026-10-26 23:30 |  |  | 24 | 0
A9370 | Completed | BSL.1.3.1.2.3.1.2.3.7 | Availiability of EOT crane for converter # 1 misc. shutdown activity | 2025-02-26 00:30 | 2026-05-24 23:30 | 2025-02-26 00:30 | 2026-05-24 23:30 | 447 | 447
A9430 | In Progress | BSL.1.3.1.2.3.1.2.3.9 | Availiability of EOT crane for converter # 2 misc. shutdown activity | 2025-02-26 00:30 | 2026-08-24 23:30 | 2025-03-03 00:30 |  | 539 | 478
A8990 | Completed | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Existing facilities (Major items- priority areas) | 2025-03-27 00:30 | 2025-05-28 17:01 | 2025-03-27 00:30 | 2025-05-28 17:01 | 62 | 62
A8970 | Completed | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Site mobilisation | 2025-03-27 00:30 | 2025-03-27 00:30 | 2025-03-27 00:30 | 2025-03-27 00:30 | 0 | 0
A8980 | Completed | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works: Clearance for dismantling & relocation of existing facilities | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-02-26 00:30 | 2025-03-26 23:30 | 28 | 28
A1430 | Completed | BSL.1.1.2.2 | Testing of Equipment | 2025-02-26 00:30 | 2026-06-13 23:30 | 2025-02-26 00:30 | 2026-06-12 23:30 | 467 | 467
A9360 | Completed | BSL.1.3.1.2.3.1.2.3.7 | Converter#1 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-05-24 23:30 | 2025-03-01 00:30 | 2026-06-08 23:30 | 447 | 447
A9420 | In Progress | BSL.1.3.1.2.3.1.2.3.9 | Converter#2 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-08-24 23:30 | 2025-02-26 00:30 |  | 539 | 483
A1330 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Pre-assembly of Dog house before shutdown | 2025-02-26 00:30 | 2026-05-21 23:30 | 2025-03-03 00:30 | 2026-05-25 23:30 | 444 | 444
A1390 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Pre-assembly of Dog house before shutdown | 2025-02-26 00:30 | 2026-08-22 23:30 |  |  | 537 | 0
A9000 | Not Started | BSL.1.3.1.2.3.1.2.3.3 | DW: Dismantling Works - Existing facilities (Non-priority areas & Doghouse) | 2025-05-28 17:01 | 2026-08-27 23:30 |  |  | 452 | 0
A9050 | Not Started | BSL.1.3.1.2.3.1.2.3.4.1.2.3.4.2 | CW: Civil Works - Road & drain works | 2025-02-26 00:30 | 2026-07-26 23:30 |  |  | 510 | 0
A9490 | Completed | BSL.1.2 | Effective Date of Contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A9510 | Completed | BSL.1.2 | Kick off Meeting | 2025-03-18 00:30 | 2025-03-18 00:30 | 2025-03-18 08:00 | 2025-03-18 17:00 | 0 | 0
A9500 | Completed | BSL.1.2 | Signing of Contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A9520 | Completed | BSL.1.2 | PBG | 2025-03-28 00:30 | 2025-03-28 00:30 | 2025-03-13 08:00 | 2025-03-13 17:00 | 0 | 0
A9530 | Completed | BSL.1.2 | Procurement Start | 2025-03-06 00:30 | 2025-03-25 23:30 | 2025-03-11 00:30 | 2025-04-04 23:30 | 19 | 19
A9540 | Not Started | BSL.1.2 | Completion of Procurement | 2026-06-29 06:30 | 2026-07-01 00:30 |  |  | 2 | 0
A9550 | Completed | BSL.1.2 | Site Handover | 2025-03-27 00:30 | 2025-03-27 00:30 | 2025-03-29 00:30 | 2025-04-06 00:30 | 0 | 0
A9560 | Completed | BSL.1.2 | Supply Start | 2025-10-18 00:30 | 2025-11-02 23:30 | 2025-10-18 00:30 | 2025-10-31 23:30 | 15 | 15
A9590 | Not Started | BSL.1.2 | Erection Completion | 2026-09-01 00:30 | 2026-09-01 00:30 |  |  | 0 | 0
A9600 | Not Started | BSL.1.2 | PAC | 2026-10-03 00:30 | 2026-10-03 00:30 |  |  | 0 | 0
A9610 | Not Started | BSL.1.2 | Commissioning |  | 2026-11-01 23:30 |  |  | 0 | 0
A9570 | Completed | BSL.1.2 | Erection Start | 2025-11-22 00:30 | 2025-11-22 00:30 | 2025-11-22 00:30 | 2025-11-21 00:30 | 0 | 0
A9390 | Completed | BSL.1.3.1.2.3.1.2.3.8 | Testing of equipment | 2026-05-03 00:30 | 2026-06-19 23:30 | 2026-05-03 00:30 | 2026-06-19 23:30 | 48 | 48
A9400 | In Progress | BSL.1.3.1.2.3.1.2.3.8 | Trial run of equipment | 2025-02-26 00:30 | 2026-07-02 23:30 | 2025-03-09 00:30 |  | 486 | 472
A9410 | Not Started | BSL.1.3.1.2.3.1.2.3.8 | Hot commissioning (unit-1) | 2026-07-03 00:30 | 2026-07-03 00:30 |  |  | 0 | 0
A9100 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary ID fan (Unit # 2) | 2026-05-23 00:30 | 2026-07-23 23:30 | 2026-05-27 00:30 |  | 62 | 28
A9140 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Secondary duct with support structure (Unit # 2) | 2025-11-16 00:30 | 2026-07-27 23:30 | 2025-11-16 00:30 |  | 253 | 220
A1500 | In Progress | BSL.1.1.2.5 | Testing of Equipment | 2025-02-26 00:30 | 2026-09-10 23:30 | 2025-02-26 00:30 |  | 556 | 483
A1520 | Not Started | BSL.1.1.2.5 | Commissioning of Secondary emission control system (Unit-2) | 2026-09-27 00:30 | 2026-10-26 23:30 |  |  | 30 | 0
A1530 | Not Started | BSL.1.1.2.5 | Completion of Secondary emission control system (Unit-2) | 2026-10-27 00:30 | 2026-10-27 00:30 |  |  | 0 | 0
A1440 | Not Started | BSL.1.1.2.2 | Trial Run of Equipment | 2025-02-26 00:30 | 2026-06-26 23:30 |  |  | 480 | 0
A1510 | In Progress | BSL.1.1.2.5 | Trial Run of Equipment | 2025-02-26 00:30 | 2026-09-26 23:30 | 2025-02-26 00:30 |  | 572 | 483
A1250 | In Progress | BSL.1.1.2.6 | Dismantling of existing facilities (Non-priority areas & Doghouse) | 2025-07-26 11:30 | 2026-07-26 23:30 | 2025-07-26 11:30 |  | 362 | 333
A1340 | In Progress | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of ESP # 2 | 2026-01-28 00:30 | 2026-08-24 23:30 | 2026-02-04 00:30 |  | 209 | 140
A9170 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.2 | ERE: Piping works (Unit # 2) | 2025-11-21 00:30 | 2026-07-31 23:30 | 2025-11-27 00:30 |  | 252 | 209
A9200 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Dry ESP (Pass # A) | 2025-02-26 00:30 | 2026-05-24 23:30 | 2025-03-02 00:30 | 2026-06-04 23:30 | 447 | 447
A9210 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Dry ESP (Pass # B) | 2025-02-26 00:30 | 2026-08-30 23:30 |  |  | 545 | 0
A9220 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary ID fan (Unit # 1) | 2025-02-26 00:30 | 2026-05-25 23:30 | 2025-02-26 00:30 | 2026-05-25 23:30 | 448 | 448
A9230 | Not Started | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary ID fan (Unit # 2) | 2025-02-26 00:30 | 2026-08-22 23:30 |  |  | 537 | 0
A9240 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Clean gas stack | 2025-02-26 00:30 | 2026-05-30 23:30 | 2025-02-27 00:30 | 2026-06-16 23:30 | 453 | 453
A9250 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Silo unit (incl. conveying) | 2025-02-26 00:30 | 2026-06-02 23:30 | 2025-02-26 00:30 | 2026-06-02 23:30 | 456 | 456
A9260 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary duct with support structure (Unit # 1) | 2025-02-26 00:30 | 2026-06-05 23:30 | 2025-03-03 00:30 | 2026-06-20 23:30 | 459 | 459
A9270 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Secondary duct with support structure (Unit # 2) | 2025-02-26 00:30 | 2026-08-26 23:30 | 2025-03-12 00:30 |  | 541 | 469
A9280 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Other misc. works | 2025-02-26 00:30 | 2026-06-11 23:30 | 2025-02-26 00:30 | 2026-06-11 23:30 | 465 | 465
A9290 | Completed | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Piping works (Unit # 1) | 2025-02-26 00:30 | 2026-06-16 23:30 | 2025-02-26 00:30 | 2026-06-16 23:30 | 470 | 470
A9300 | In Progress | BSL.1.3.1.2.3.1.2.3.5.1.2.3.5.3 | ALN: Piping works (Unit # 2) | 2025-02-26 00:30 | 2026-08-30 23:30 | 2025-02-26 00:30 |  | 545 | 483
A9330 | Completed | BSL.1.3.1.2.3.1.2.3.6 | ALN: Electrical and automation works of Unit # 1 | 2025-02-26 00:30 | 2026-05-30 23:30 | 2025-02-26 00:30 | 2026-05-30 23:30 | 453 | 453
A9350 | Not Started | BSL.1.3.1.2.3.1.2.3.6 | ALN: Electrical and automation works of Unit # 2 | 2025-02-26 00:30 | 2026-08-26 23:30 |  |  | 541 | 0
A1560 | Completed | BSL.1.3.1.2.2 | Layout submission | 2025-03-22 00:30 | 2025-04-01 23:30 | 2025-03-22 00:30 | 2025-04-01 23:30 | 11 | 11
A1570 | Completed | BSL.1.3.1.2.2 | Approval of Layout | 2025-04-02 00:30 | 2025-04-15 23:30 | 2025-04-02 00:30 | 2025-04-15 23:30 | 14 | 14
A9580 | Not Started | BSL.1.2 | Supply Finish | 2026-06-29 06:30 | 2026-07-01 00:30 |  |  | 2 | 0
A8800 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.24 | DE.s: Functional Description - Secondary dedusting | 2025-02-26 00:30 | 2026-01-31 23:30 | 2025-02-26 00:30 | 2026-01-28 23:30 | 334 | 334
A8810 | Completed | BSL.1.3.1.2.2.1.2.2.6.1.2.2.6.24 | DE.a/i: Functional Description - Secondary dedusting | 2025-02-26 00:30 | 2026-02-14 23:30 | 2025-02-26 00:30 | 2026-02-14 23:30 | 348 | 348
A4690 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.18 | DE.s: Operation & Maintenance manual | 2025-02-26 00:30 | 2026-02-12 23:30 | 2025-02-26 00:30 | 2026-02-12 23:30 | 346 | 346
A4700 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.18 | DE.a/i: Operation & Maintenance manual | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-26 23:30 | 360 | 360
A1010 | Completed | BSL.1.1 | Effective date of contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A1200 | Completed | BSL.1.1.2.1 | Work Front Handover including Construction power & water | 2025-03-27 00:30 | 2025-03-27 00:30 | 2025-03-30 00:30 | 2025-04-16 00:30 | 0 | 0
A1180 | Completed | BSL.1.1.2.1 | Allocation of Work Front Office Area | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-02-27 00:30 | 2025-04-05 23:30 | 28 | 28
A1190 | Completed | BSL.1.1.2.1 | Allocation of Covered Storage Area | 2025-02-26 00:30 | 2025-06-25 23:30 | 2025-02-26 00:30 | 2025-06-21 23:30 | 118 | 118
A1240 | Completed | BSL.1.1.2.6 | Dismantling of existing facilities (Major items- priority areas) | 2025-03-27 00:30 | 2025-07-26 11:30 | 2025-03-31 00:30 | 2025-08-07 11:30 | 120 | 120
A1450 | Not Started | BSL.1.1.2.2 | Commissioning of Secondary emission control system (Unit-1) | 2026-06-27 00:30 | 2026-06-29 23:30 |  |  | 3 | 0
A1460 | Not Started | BSL.1.1.2.2 | Completion of Secondary emission control system (Unit-1) | 2026-06-30 00:30 | 2026-06-30 00:30 |  |  | 0 | 0
A1000 | Completed | BSL.1.1 | Signing of Contract | 2025-02-26 00:30 |  | 2025-02-26 08:00 |  | 0 | 0
A1020 | Completed | BSL.1.1 | Kick Off Meeting (Flowsheet, Layout Approval, technical Specification of Fan & ESP, ECR building heat load, Construction | 2025-03-18 00:30 | 2025-03-21 23:30 | 2025-03-18 08:00 | 2025-03-18 17:00 | 4 | 0
A1030 | Completed | BSL.1.1.1.2 | Basic Engineering - Mechanical & Electrical | 2025-02-26 00:30 | 2025-07-12 23:30 | 2025-02-26 00:30 | 2025-07-12 23:30 | 135 | 135
A1040 | Completed | BSL.1.1.1.2 | Basic Engineering Approval - Mechanical & Electrical | 2025-02-26 00:30 | 2025-07-26 23:30 | 2025-02-26 00:30 | 2025-07-26 23:30 | 149 | 149
A1070 | Completed | BSL.1.1.1.3 | Detail Engineering - Mechanical & Electrical | 2025-04-25 00:30 | 2026-02-12 23:30 | 2025-04-25 00:30 | 2026-02-12 23:30 | 289 | 289
A1080 | Completed | BSL.1.1.1.3 | Detail Engineering Approval - Mechanical & Electrical | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-27 00:30 | 2026-03-04 23:30 | 360 | 360
A1140 | In Progress | BSL.1.1.3.1.1 | Dog House#2 | 2025-02-26 00:30 | 2026-06-26 23:30 | 2025-02-26 00:30 |  | 480 | 483
A1150 | Completed | BSL.1.1.3.1.1 | ESP # 2 & Fan # 3 | 2025-03-26 00:30 | 2026-05-14 23:30 | 2025-03-26 00:30 | 2026-05-10 23:30 | 410 | 410
A1210 | Completed | BSL.1.1.2.1 | Handover of project office building and associated facilities | 2025-04-27 00:30 | 2025-04-27 00:30 | 2025-04-27 00:30 | 2025-04-27 00:30 | 0 | 0
A1230 | Completed | BSL.1.1.2 | Site mobilisation | 2025-02-26 00:30 | 2025-03-26 23:30 | 2025-02-26 00:30 | 2025-03-21 23:30 | 28 | 28
A1260 | In Progress | BSL.1.1.2 | Civil & structural Work | 2025-06-27 00:30 | 2026-07-26 23:30 | 2025-07-10 00:30 |  | 391 | 349
A1050 | Completed | BSL.1.1.1.2 | Basic Engineering - Civil | 2025-02-26 00:30 | 2025-07-12 23:30 | 2025-02-26 00:30 | 2025-07-08 23:30 | 135 | 135
A1060 | Completed | BSL.1.1.1.2 | Basic Engineering - Approval Civil | 2025-02-26 00:30 | 2025-07-26 23:30 | 2025-02-26 00:30 | 2025-07-22 23:30 | 149 | 149
A1090 | Completed | BSL.1.1.1.3 | Detail Engineering - Civil | 2025-05-27 00:30 | 2026-02-12 23:30 | 2025-05-27 00:30 | 2026-02-09 23:30 | 258 | 258
A1100 | Completed | BSL.1.1.3.2.1 | Dog House#1 | 2025-04-30 00:30 | 2026-05-01 23:30 | 2025-04-30 00:30 | 2026-05-01 23:30 | 362 | 362
A1110 | Completed | BSL.1.1.3.2.1 | ESP # 1, Fan # 1 & Fan # 2 | 2025-03-26 00:30 | 2026-03-01 23:30 | 2025-03-26 00:30 | 2026-03-01 23:30 | 336 | 336
A1120 | Completed | BSL.1.1.3.2.1 | Secondary Ducts & Duct Support Structure | 2025-02-26 00:30 | 2026-04-26 23:30 | 2025-02-26 00:30 | 2026-04-26 23:30 | 419 | 419
A1130 | Completed | BSL.1.1.3.2 | Electrical Items | 2025-05-26 00:30 | 2026-05-08 23:30 | 2025-05-27 00:30 | 2026-05-22 23:30 | 344 | 344
A1160 | Completed | BSL.1.1.3.1.1 | Secondary Ducts & Duct Support Structure | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-03-03 00:30 | 2026-06-10 23:30 | 450 | 450
A1170 | Completed | BSL.1.1.3 | Electrical Items | 2025-05-26 00:30 | 2026-05-08 23:30 | 2025-05-27 00:30 | 2026-05-22 23:30 | 344 | 344
A1270 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of ESP # 1 | 2025-10-30 00:30 | 2026-05-24 23:30 | 2025-10-30 00:30 | 2026-05-24 23:30 | 206 | 206
A1280 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Stack | 2025-09-28 00:30 | 2026-05-30 23:30 | 2025-09-28 00:30 | 2026-05-30 23:30 | 242 | 242
A1290 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Fan # 1 & Fan # 2 | 2025-10-29 00:30 | 2026-05-25 23:30 | 2025-10-29 00:30 | 2026-05-25 23:30 | 208 | 208
A1300 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Ducts & Support Structure (Inside & Outside Bldg.) | 2025-12-30 00:30 | 2026-05-30 23:30 | 2025-12-31 00:30 | 2026-06-16 23:30 | 152 | 152
A1310 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Electrical Items | 2026-01-14 00:30 | 2026-05-30 23:30 | 2026-01-14 00:30 | 2026-05-25 23:30 | 137 | 137
A1320 | Completed | BSL.1.1.2.1.1.6.5.1.1.6.5.1 | Erection of Balance items | 2026-02-09 00:30 | 2026-05-22 23:30 | 2026-02-12 00:30 | 2026-05-26 23:30 | 103 | 103
A1400 | Completed | BSL.1.1.2.3 | Converter#1 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-05-24 23:30 | 2025-02-26 00:30 | 2026-05-24 23:30 | 447 | 447
A1410 | Completed | BSL.1.1.2.3 | Availability of EOT Crane | 2025-02-26 00:30 | 2026-05-24 23:30 | 2025-02-26 00:30 | 2026-05-24 23:30 | 447 | 447
A1420 | In Progress | BSL.1.1.2.3 | Converter#1 - Shutdown Work (Dismantling of existing dog house, installation of new dog house with hoods, refractory lin | 2026-05-25 00:30 | 2026-06-26 23:30 | 2026-05-28 00:30 |  | 33 | 27
A1350 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Fan # 3 | 2025-11-28 00:30 | 2026-08-22 23:30 |  |  | 267 | 0
A1360 | In Progress | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Ducts & Support Structure (Inside & Outside Bldg.) | 2025-11-02 00:30 | 2026-08-26 23:30 | 2025-11-13 00:30 |  | 297 | 223
A1370 | In Progress | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Electrical Items | 2026-06-01 00:30 | 2026-08-26 23:30 | 2026-06-01 00:30 |  | 87 | 23
A1380 | Not Started | BSL.1.1.2.1.1.6.5.1.1.6.5.2 | Erection of Balance items | 2025-12-28 00:30 | 2026-08-26 23:30 |  |  | 242 | 0
A1470 | In Progress | BSL.1.1.2.4 | Converter#2 - Shutdown, Converter cooling & Front Handover | 2025-02-26 00:30 | 2026-08-24 23:30 | 2025-03-02 00:30 |  | 539 | 479
A1480 | Not Started | BSL.1.1.2.4 | Availability of EOT Crane | 2025-02-26 00:30 | 2026-08-24 23:30 |  |  | 539 | 0
A1490 | Not Started | BSL.1.1.2.4 | Converter#2 - Shutdown Work (Dismantling of existing dog house, installation of new dog house with hoods, refractory lin | 2026-08-25 00:30 | 2026-09-26 23:30 |  |  | 33 | 0
A1220 | Completed | BSL.1.1.2.1 | Availability of permanent power & utilities | 2026-05-09 00:30 | 2026-05-09 00:30 | 2026-05-09 00:30 | 2026-05-06 00:30 | 0 | 0
A1540 | Completed | BSL.1.3 | Effective date of contract | 2025-02-26 00:30 | 2025-02-26 00:30 | 2025-02-26 08:00 | 2025-02-26 17:00 | 0 | 0
A1550 | Completed | BSL.1.3.1.2.2 | Kick Off Meeting (Flowsheet, technical Specification of Fan & ESP, ECR building heat load, Construction vendor approval) | 2025-02-26 00:30 | 2025-03-21 23:30 | 2025-02-28 00:30 | 2025-03-28 23:30 | 23 | 23
A1580 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | BE.s: Dog house unit | 2025-04-16 00:30 | 2025-06-25 23:30 | 2025-04-16 00:30 | 2025-06-23 23:30 | 70 | 70
A1590 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | BE.a: Dog house unit | 2025-02-26 00:30 | 2025-07-09 23:30 | 2025-02-26 00:30 | 2025-07-09 23:30 | 132 | 132
A1600 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | DE.s: Dog house unit | 2025-07-10 00:30 | 2025-11-26 23:30 | 2025-07-11 00:30 | 2025-12-03 23:30 | 137 | 137
A1610 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1 | DE.a/i: Dog house unit | 2025-02-26 00:30 | 2025-12-10 23:30 | 2025-02-26 00:30 | 2025-12-10 23:30 | 283 | 283
A1620 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | MAN: Dog house unit (Converter-1) | 2025-09-23 00:30 | 2026-03-20 23:30 | 2025-09-24 00:30 | 2026-04-02 23:30 | 176 | 176
A1630 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | INSP: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A1640 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | DCC.a: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-06 23:30 | 2025-02-26 00:30 | 2026-04-06 23:30 | 399 | 399
A1650 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | DCC.r: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-04-10 23:30 | 2025-02-26 00:30 | 2026-04-05 23:30 | 403 | 403
A1660 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5 | LT: Dog house unit (Converter-1) | 2025-02-26 00:30 | 2026-05-01 23:30 | 2025-02-26 00:30 | 2026-05-01 23:30 | 424 | 424
A1670 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5.1.2.2.4.1.5.6 | AoS: Dog house unit | 2025-02-26 00:30 | 2026-05-01 23:30 | 2025-02-26 00:30 | 2026-05-01 23:30 | 424 | 424
A1680 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.1.1.2.2.4.1.5.1.2.2.4.1.5.6 | AoS: Dog house door front side/ back side rail | 2025-02-26 00:30 | 2026-05-01 23:30 | 2025-02-26 00:30 | 2026-05-01 23:30 | 424 | 424
A1920 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | BE.s: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-04-16 23:30 | 2025-02-26 00:30 | 2025-04-16 23:30 | 49 | 49
A1930 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | BE.a: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-04-30 23:30 | 2025-02-26 00:30 | 2025-04-26 23:30 | 63 | 63
A1940 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | DE.s: Square shape ESP unit (dry type) | 2025-05-02 00:30 | 2025-09-22 23:30 | 2025-05-02 00:30 | 2025-09-17 23:30 | 143 | 143
A1950 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3 | DE.a/i: Square shape ESP unit (dry type) | 2025-02-26 00:30 | 2025-10-10 23:30 | 2025-02-26 00:30 | 2025-10-10 23:30 | 223 | 223
A1960 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | MAN: Square shape ESP unit (dry type) (Unit-1) | 2025-07-03 00:30 | 2026-01-24 23:30 | 2025-07-06 00:30 | 2026-02-12 23:30 | 202 | 202
A1970 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | INSP: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-07 23:30 | 2025-02-26 00:30 | 2026-02-07 23:30 | 341 | 341
A1980 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | DCC.a: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-10 23:30 | 2025-03-02 00:30 | 2026-02-14 23:30 | 344 | 344
A1990 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | DCC.r: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-02-14 23:30 | 2025-02-27 00:30 | 2026-03-02 23:30 | 348 | 348
A2000 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5 | LT: Square shape ESP unit (dry type) (Unit-1) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2010 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Access (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-27 00:30 | 2026-03-12 23:30 | 369 | 369
A2020 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Support structure (for ESP) | 2025-03-07 00:30 | 2026-02-09 23:30 | 2025-03-07 00:30 | 2026-02-09 23:30 | 334 | 334
A2030 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Motorized Guillotine dampers (for inlet at each pass) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2040 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Motorized Guillotine dampers (for outlet at each pass) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2050 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Gas inlet and outlet cone (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 369 | 369
A2060 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Expansion joint (for duct of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-04 23:30 | 369 | 369
A2070 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Casing (for ESP) | 2025-03-28 00:30 | 2026-03-01 23:30 | 2025-03-28 00:30 | 2026-03-01 23:30 | 334 | 334
A2080 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Heating elements (for dust hoppers of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-04 23:30 | 369 | 369
A2090 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Manual slide gate (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2100 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Rotary valve (of dust hopper for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-06 23:30 | 369 | 369
A2110 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Expansion joints (at dust hoppers of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-03-03 00:30 | 2026-03-13 23:30 | 369 | 369
A2120 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Dust hoppers (of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-05 23:30 | 369 | 369
A2130 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: HV Insulator system (of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2140 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Heating elements (for HV insulators of ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-03-01 00:30 | 2026-03-23 23:30 | 369 | 369
A2150 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Transformer rectifier (HFTR - 1 field, advance controller - all field) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-03-02 00:30 | 2026-03-22 23:30 | 369 | 369
A2160 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Technological internals (for ESP) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-04 23:30 | 369 | 369
A2170 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Weather protection over TR Bay | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 369 | 369
A2180 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.3.1.2.2.4.3.5.1.2.2.4.3.5.6 | AoS: Structure (for Weather Protection) | 2025-02-26 00:30 | 2026-03-07 23:30 | 2025-02-26 00:30 | 2026-03-04 23:30 | 369 | 369
A2420 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | BE.s: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-04-26 23:30 | 2025-02-27 00:30 | 2025-05-14 23:30 | 59 | 59
A2430 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | BE.a: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-05-12 23:30 | 2025-02-26 00:30 | 2025-05-12 23:30 | 74 | 74
A2440 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DE.s: Steel part of clean gas stack | 2025-05-13 00:30 | 2025-10-07 23:30 | 2025-05-13 00:30 | 2025-10-07 23:30 | 146 | 146
A2450 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DE.a/i: Steel part of clean gas stack | 2025-02-26 00:30 | 2025-10-26 23:30 | 2025-02-26 00:30 | 2025-10-26 23:30 | 238 | 238
A2460 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | MAN: Steel part of clean gas stack | 2025-07-11 00:30 | 2026-01-26 23:30 | 2025-07-11 00:30 | 2026-01-23 23:30 | 196 | 196
A2470 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | INSP: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-09 23:30 | 2025-02-27 00:30 | 2026-03-01 23:30 | 343 | 343
A2480 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DCC.a: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-12 23:30 | 2025-02-26 00:30 | 2026-02-07 23:30 | 346 | 346
A2490 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | DCC.r: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-02-16 23:30 | 2025-02-26 00:30 | 2026-02-15 23:30 | 350 | 350
A2500 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4 | LT: Steel part of clean gas stack | 2025-02-26 00:30 | 2026-03-09 23:30 | 2025-02-26 00:30 | 2026-03-09 23:30 | 371 | 371
A2510 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Shell for clean gas stack | 2025-02-26 00:30 | 2026-03-09 23:30 | 2025-02-27 00:30 | 2026-03-25 23:30 | 371 | 371
A2520 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Built in parts | 2025-04-14 00:30 | 2026-03-03 23:30 | 2025-04-17 00:30 | 2026-03-15 23:30 | 319 | 319
A2530 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.4.1.2.2.4.4.10 | AoS: Access platforms, stairs, ladders | 2025-04-14 00:30 | 2026-03-03 23:30 | 2025-04-14 00:30 | 2026-03-03 23:30 | 319 | 319
A2540 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | BE.s: Mechanical silo filling | 2025-02-26 00:30 | 2025-05-26 23:30 | 2025-02-26 00:30 | 2025-05-24 23:30 | 88 | 88
A2550 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | BE.a: Mechanical silo filling | 2025-02-26 00:30 | 2025-06-09 23:30 | 2025-02-26 00:30 | 2025-06-07 23:30 | 102 | 102
A2560 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DE.s: Mechanical silo filling | 2025-06-26 00:30 | 2025-09-21 23:30 | 2025-07-01 00:30 | 2025-10-05 23:30 | 87 | 87
A2570 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DE.a/i: Mechanical silo filling | 2025-02-26 00:30 | 2025-10-09 23:30 | 2025-02-26 00:30 | 2025-10-09 23:30 | 222 | 222
A2580 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | MAN: Mechanical silo filling | 2025-08-20 00:30 | 2026-01-19 23:30 | 2025-08-24 00:30 | 2026-01-29 23:30 | 150 | 150
A2590 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | INSP: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-02 23:30 | 2025-02-27 00:30 | 2026-02-22 23:30 | 336 | 336
A2600 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DCC.a: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-05 23:30 | 2025-02-26 00:30 | 2026-02-02 23:30 | 339 | 339
A2610 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | DCC.r: Mechanical silo filling | 2025-02-26 00:30 | 2026-02-09 23:30 | 2025-02-26 00:30 | 2026-02-09 23:30 | 343 | 343
A2620 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5 | LT: Mechanical silo filling | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2690 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-03-01 00:30 | 2026-03-15 23:30 | 364 | 364
A2680 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2670 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.3 | AoS: Cross Chain Conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-27 00:30 | 2026-03-17 23:30 | 364 | 364
A2720 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2710 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-01 23:30 | 364 | 364
A2700 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.4 | AoS: Bucket Elevator | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2730 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Screw conveyor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-02-26 23:30 | 364 | 364
A2740 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Motor | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2750 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.5.1.2.2.4.5.10.1.2.2.4.5.10.5 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-02 23:30 | 2025-02-26 00:30 | 2026-03-02 23:30 | 364 | 364
A2760 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | BE.s: Silo unit | 2025-04-28 00:30 | 2025-06-26 23:30 | 2025-04-28 00:30 | 2025-06-26 23:30 | 59 | 59
A2770 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | BE.a: Silo unit | 2025-02-26 00:30 | 2025-07-10 23:30 | 2025-02-26 00:30 | 2025-07-05 23:30 | 133 | 133
A2780 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DE.s: Silo unit | 2025-07-11 00:30 | 2025-10-08 23:30 | 2025-07-11 00:30 | 2025-10-07 23:30 | 88 | 88
A2790 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DE.a/i: Silo unit | 2025-02-26 00:30 | 2025-10-27 23:30 | 2025-02-26 00:30 | 2025-10-27 23:30 | 239 | 239
A2800 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | MAN: Silo unit | 2025-09-21 00:30 | 2026-02-05 23:30 | 2025-09-22 00:30 | 2026-02-09 23:30 | 135 | 135
A2810 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | INSP: Silo unit | 2025-02-26 00:30 | 2026-02-19 23:30 | 2025-02-26 00:30 | 2026-02-19 23:30 | 353 | 353
A2820 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DCC.a: Silo unit | 2025-02-26 00:30 | 2026-02-22 23:30 | 2025-02-26 00:30 | 2026-02-18 23:30 | 356 | 356
A2830 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | DCC.r: Silo unit | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-22 23:30 | 360 | 360
A2840 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6 | LT: Silo unit | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2850 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Shell for dust silo | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-03-01 00:30 | 2026-03-25 23:30 | 381 | 381
A2860 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Supporting structure | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2870 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.1 | AoS: Access platforms, stairs, ladders | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2880 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.2 | AoS: Silo top filter unit | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-15 23:30 | 381 | 381
A2890 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.3 | AoS: Manual slide gate for main dust outlet | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-16 23:30 | 381 | 381
A2900 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS:Nozzles for fluidisation unit | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2910 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS: Equipment attached piping | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A2920 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.4 | AoS: Solenoid valve for fluidisation unit | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-18 23:30 | 381 | 381
A2930 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.6.1.2.2.4.6.10.1.2.2.4.6.10.5 | AoS: Rotary valve | 2025-02-26 00:30 | 2026-03-19 23:30 | 2025-02-26 00:30 | 2026-03-19 23:30 | 381 | 381
A3040 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | BE.s: Expansion joint | 2025-02-26 00:30 | 2025-05-28 23:30 | 2025-03-01 00:30 | 2025-06-04 23:30 | 90 | 90
A3050 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | BE.a: Expansion joint | 2025-02-26 00:30 | 2025-06-11 23:30 | 2025-02-26 00:30 | 2025-06-11 23:30 | 104 | 104
A3060 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DE.s: Expansion joint | 2025-07-13 00:30 | 2025-10-08 23:30 | 2025-07-13 00:30 | 2025-10-08 23:30 | 86 | 86
A3070 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DE.a/i: Expansion joint | 2025-02-26 00:30 | 2025-10-27 23:30 | 2025-02-26 00:30 | 2025-10-27 23:30 | 239 | 239
A3080 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | MAN: Expansion joint | 2025-09-11 00:30 | 2026-02-20 23:30 | 2025-09-11 00:30 | 2026-02-20 23:30 | 160 | 160
A3090 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | INSP: Expansion joint | 2025-02-26 00:30 | 2026-03-06 23:30 | 2025-02-26 00:30 | 2026-03-06 23:30 | 368 | 368
A3100 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DCC.a: Expansion joint | 2025-02-26 00:30 | 2026-03-09 23:30 | 2025-02-26 00:30 | 2026-03-07 23:30 | 371 | 371
A3110 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | DCC.r: Expansion joint | 2025-02-26 00:30 | 2026-03-13 23:30 | 2025-02-26 00:30 | 2026-03-10 23:30 | 375 | 375
A3120 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8 | LT: Expansion joint | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3130 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-03-02 00:30 | 2026-04-07 23:30 | 396 | 396
A3140 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3150 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of charging fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-03-03 00:30 | 2026-04-16 23:30 | 396 | 396
A3160 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Duct of tapping fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3170 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Raw gas collection duct | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3180 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Expansion joints for ID fan inlet (double inlet) | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-03-31 23:30 | 396 | 396
A3190 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.8.1.2.2.4.8.10 | AoS: Expansion joints for ID fan outlet | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3200 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | BE.s: Damper with actuator | 2025-02-26 00:30 | 2025-05-28 23:30 | 2025-02-26 00:30 | 2025-05-28 23:30 | 90 | 90
A3210 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | BE.a: Damper with actuator | 2025-02-26 00:30 | 2025-06-11 23:30 | 2025-02-26 00:30 | 2025-06-11 23:30 | 104 | 104
A3220 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DE.s: Damper with actuator | 2025-07-13 00:30 | 2025-10-08 23:30 | 2025-07-16 00:30 | 2025-10-25 23:30 | 86 | 86
A3230 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DE.a/i: Damper with actuator | 2025-02-26 00:30 | 2025-10-27 23:30 | 2025-02-26 00:30 | 2025-10-27 23:30 | 239 | 239
A3240 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | MAN: Damper with actuator | 2025-09-11 00:30 | 2026-02-20 23:30 | 2025-09-15 00:30 | 2026-03-02 23:30 | 160 | 160
A3250 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | INSP: Damper with actuator | 2025-02-26 00:30 | 2026-03-06 23:30 | 2025-02-26 00:30 | 2026-03-01 23:30 | 368 | 368
A3260 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DCC.a: Damper with actuator | 2025-02-26 00:30 | 2026-03-09 23:30 | 2025-02-26 00:30 | 2026-03-09 23:30 | 371 | 371
A3270 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | DCC.r: Damper with actuator | 2025-02-26 00:30 | 2026-03-13 23:30 | 2025-02-28 00:30 | 2026-03-26 23:30 | 375 | 375
A3280 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9 | LT: Damper with actuator | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3290 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-03 23:30 | 396 | 396
A3300 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of material handling fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-02 23:30 | 396 | 396
A3310 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of charging fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-02-26 00:30 | 2026-04-01 23:30 | 396 | 396
A3320 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.9.1.2.2.4.9.10 | AoS: Damper of tapping fume suction | 2025-02-26 00:30 | 2026-04-03 23:30 | 2025-03-01 00:30 | 2026-04-17 23:30 | 396 | 396
A3330 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | BE.s: ID fan station | 2025-02-26 00:30 | 2025-04-21 23:30 | 2025-02-26 00:30 | 2025-04-19 23:30 | 54 | 54
A3340 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | BE.a: ID fan station | 2025-02-26 00:30 | 2025-05-07 23:30 | 2025-02-26 00:30 | 2025-05-07 23:30 | 69 | 69
A3350 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | DE.s: ID fan station | 2025-06-03 00:30 | 2025-08-29 23:30 | 2025-06-03 00:30 | 2025-08-29 23:30 | 87 | 87
A3360 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10 | DE.a/i: ID fan station | 2025-02-26 00:30 | 2025-09-12 23:30 | 2025-02-26 00:30 | 2025-09-12 23:30 | 196 | 196
A3370 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | MAN: ID fan station (Fan-1) | 2025-08-17 00:30 | 2026-01-10 23:30 | 2025-08-17 00:30 | 2026-01-09 23:30 | 144 | 144
A3380 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | INSP: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-24 23:30 | 2025-02-26 00:30 | 2026-01-24 23:30 | 327 | 327
A3390 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.a: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-27 23:30 | 2025-03-02 00:30 | 2026-02-14 23:30 | 330 | 330
A3400 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | DCC.r: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-01-31 23:30 | 2025-03-03 00:30 | 2026-02-17 23:30 | 334 | 334
A3410 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5 | LT: ID fan station (Fan-1) | 2025-02-26 00:30 | 2026-02-21 23:30 | 2025-02-26 00:30 | 2026-02-16 23:30 | 355 | 355
A3420 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.6 | AoS: Motorised Multi Louvre Damper with Manual override at ID fan Intlet | 2025-06-26 00:30 | 2026-02-21 23:30 | 2025-06-26 00:30 | 2026-02-21 23:30 | 237 | 237
A3430 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.10.1.2.2.4.10.5.1.2.2.4.10.5.6 | AoS: ID fan | 2025-06-26 00:30 | 2026-02-21 23:30 | 2025-06-28 00:30 | 2026-03-06 23:30 | 237 | 237
A3580 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | BE.s: MHS booster fan | 2025-02-26 00:30 | 2025-06-17 23:30 | 2025-02-26 00:30 | 2025-06-17 23:30 | 110 | 110
A3590 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | BE.a: MHS booster fan | 2025-02-26 00:30 | 2025-07-01 23:30 | 2025-02-26 00:30 | 2025-07-01 23:30 | 124 | 124
A3600 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DE.s: MHS booster fan | 2025-08-02 00:30 | 2025-09-28 23:30 | 2025-08-02 00:30 | 2025-09-25 23:30 | 57 | 57
A3610 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DE.a/i: MHS booster fan | 2025-02-26 00:30 | 2025-10-16 23:30 | 2025-02-26 00:30 | 2025-10-13 23:30 | 229 | 229
A3620 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | MAN: MHS booster fan | 2025-10-01 00:30 | 2026-02-19 23:30 | 2025-10-01 00:30 | 2026-02-16 23:30 | 139 | 139
A3630 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | INSP: MHS booster fan | 2025-02-26 00:30 | 2026-03-05 23:30 | 2025-02-26 00:30 | 2026-03-05 23:30 | 367 | 367
A3640 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DCC.a: MHS booster fan | 2025-02-26 00:30 | 2026-03-08 23:30 | 2025-02-26 00:30 | 2026-03-08 23:30 | 370 | 370
A3650 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | DCC.r: MHS booster fan | 2025-02-26 00:30 | 2026-03-11 23:30 | 2025-02-26 00:30 | 2026-03-11 23:30 | 373 | 373
A3660 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11 | LT: MHS booster fan | 2025-02-26 00:30 | 2026-04-01 23:30 | 2025-02-26 00:30 | 2026-04-01 23:30 | 394 | 394
A3670 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Control damper for booster fan inlet | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-04-01 00:30 | 0 | 0
A3680 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Raw gas booster fan | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-03-28 00:30 | 0 | 0
A3690 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.11.1.2.2.4.11.10 | AoS: Damper for booster fan outlet | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-04-02 00:30 | 2026-04-02 00:30 | 0 | 0
A3700 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | BE.s: Secondary ducts | 2025-04-16 00:30 | 2025-06-08 23:30 | 2025-04-16 00:30 | 2025-06-07 23:30 | 53 | 53
A3710 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | BE.a: Secondary ducts | 2025-02-26 00:30 | 2025-06-22 23:30 | 2025-02-26 00:30 | 2025-06-22 23:30 | 115 | 115
A3720 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DE.s: Secondary ducts | 2025-06-23 00:30 | 2025-11-04 23:30 | 2025-06-26 00:30 | 2025-11-13 23:30 | 132 | 132
A3730 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DE.a/i: Secondary ducts | 2025-02-26 00:30 | 2025-11-18 23:30 | 2025-02-26 00:30 | 2025-11-13 23:30 | 261 | 261
A3740 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | MAN: Secondary ducts | 2025-08-23 00:30 | 2026-04-15 23:30 | 2025-08-23 00:30 | 2026-04-15 23:30 | 233 | 233
A3750 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | INSP: Secondary ducts | 2025-02-26 00:30 | 2026-04-29 23:30 | 2025-02-26 00:30 | 2026-04-29 23:30 | 422 | 422
A3760 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DCC.a: Secondary ducts | 2025-02-26 00:30 | 2026-05-02 23:30 | 2025-02-26 00:30 | 2026-05-02 23:30 | 425 | 425
A3770 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | DCC.r: Secondary ducts | 2025-02-26 00:30 | 2026-05-06 23:30 | 2025-02-27 00:30 | 2026-05-19 23:30 | 429 | 429
A3780 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12 | LT: Secondary ducts | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-25 23:30 | 450 | 450
A3790 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of material handling fume suction | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A3800 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of material handling suction for BOF | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-23 23:30 | 450 | 450
A3810 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-22 23:30 | 450 | 450
A3820 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of hot metal mixer station fume suction Unit | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A3830 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of charging fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 | 2025-03-12 00:30 | 2026-03-27 23:30 | 375 | 375
A3840 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of charging fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 | 2025-03-12 00:30 | 2026-03-27 23:30 | 375 | 375
A3870 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Hood of tapping fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 | 2025-03-12 00:30 | 2026-03-27 23:30 | 375 | 375
A3880 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Duct of tapping fume suction (Converter-1) | 2025-03-12 00:30 | 2026-03-27 23:30 | 2025-03-12 00:30 | 2026-03-27 23:30 | 375 | 375
A3910 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Raw gas collection duct | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-24 23:30 | 450 | 450
A3920 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.12.1.2.2.4.12.10 | AoS: Clean gas duct assembly | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A3930 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | BE.s: Support structure of secondary ducts & Misc. structures | 2025-04-16 00:30 | 2025-05-21 23:30 | 2025-04-16 00:30 | 2025-05-21 23:30 | 35 | 35
A3940 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | BE.a: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2025-06-04 23:30 | 2025-02-26 00:30 | 2025-06-01 23:30 | 97 | 97
A3950 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DE.s: Support structure of secondary ducts & Misc. structures | 2025-06-05 00:30 | 2025-11-05 23:30 | 2025-06-05 00:30 | 2025-11-05 23:30 | 151 | 151
A3960 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DE.a/i: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2025-11-19 23:30 | 2025-03-01 00:30 | 2025-11-26 23:30 | 262 | 262
A3970 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | MAN: Support structure of secondary ducts & Misc. structures | 2025-08-03 00:30 | 2026-02-12 23:30 | 2025-08-03 00:30 | 2026-02-12 23:30 | 190 | 190
A3980 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | INSP: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-02-26 23:30 | 2025-02-26 00:30 | 2026-02-23 23:30 | 360 | 360
A3990 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DCC.a: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-01 23:30 | 2025-02-26 00:30 | 2026-03-01 23:30 | 363 | 363
A4000 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | DCC.r: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-05 23:30 | 2025-02-26 00:30 | 2026-03-01 23:30 | 367 | 367
A4010 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13 | LT: Support structure of secondary ducts & Misc. structures | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4020 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (material handling fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-25 23:30 | 388 | 388
A4030 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (material handling fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4040 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4050 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-03-03 00:30 | 2026-04-02 23:30 | 388 | 388
A4060 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (hot metal mixer station fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4070 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (hot metal mixer station fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-21 23:30 | 388 | 388
A4080 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (hot metal mixer station fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4090 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (material handling fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4100 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (charging fume suction hood) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4110 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (charging fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4120 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (charging fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-28 00:30 | 2026-04-13 23:30 | 388 | 388
A4130 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (charging fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4140 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Supporting structure (tapping fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4150 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (tapping fume suction duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4160 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (tapping fume suction damper) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-03-03 00:30 | 2026-04-01 23:30 | 388 | 388
A4170 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Duct supporting structues (raw gas collection duct) | 2025-03-12 00:30 | 2026-03-26 23:30 | 2025-03-13 00:30 | 2026-04-14 23:30 | 374 | 374
A4180 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (raw gas collection duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-21 23:30 | 388 | 388
A4190 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Duct supporting structues (clean gas duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4200 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Access platforms, stairs, ladders (clean gas duct) | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4210 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.13.1.2.2.4.13.10 | AoS: Structural shed for ID fan | 2025-02-26 00:30 | 2026-03-26 23:30 | 2025-02-26 00:30 | 2026-03-26 23:30 | 388 | 388
A4220 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | BE.s: Refractory lining | 2025-04-16 00:30 | 2025-07-12 23:30 | 2025-04-20 00:30 | 2025-07-20 23:30 | 87 | 87
A4230 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | BE.a: Refractory lining | 2025-02-26 00:30 | 2025-07-26 23:30 | 2025-02-26 00:30 | 2025-07-26 23:30 | 149 | 149
A4240 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DE.s: Refractory lining | 2025-10-19 00:30 | 2025-12-15 23:30 | 2025-10-19 00:30 | 2025-12-15 23:30 | 57 | 57
A4250 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DE.a/i: Refractory lining | 2025-02-26 00:30 | 2026-01-04 23:30 | 2025-02-26 00:30 | 2025-12-31 23:30 | 307 | 307
A4260 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | MAN: Refractory lining | 2026-01-05 00:30 | 2026-05-13 23:30 | 2026-01-05 00:30 | 2026-05-09 23:30 | 129 | 129
A4270 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | INSP: Refractory lining | 2025-02-26 00:30 | 2026-05-27 23:30 | 2025-02-26 00:30 | 2026-05-27 23:30 | 450 | 450
A4280 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DCC.a: Refractory lining | 2025-02-26 00:30 | 2026-05-30 23:30 | 2025-02-26 00:30 | 2026-05-30 23:30 | 453 | 453
A4290 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | DCC.r: Refractory lining | 2025-02-26 00:30 | 2026-06-03 23:30 | 2025-02-28 00:30 | 2026-06-21 23:30 | 457 | 457
A4300 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14 | LT: Refractory lining | 2025-02-26 00:30 | 2026-06-24 23:30 | 2025-02-26 00:30 | 2026-06-24 23:30 | 478 | 478
A4310 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for dog house unit | 2025-06-26 00:30 | 2026-06-24 23:30 | 2025-06-30 00:30 | 2026-07-11 23:30 | 360 | 360
A4320 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for hood (charging fume suction) | 2025-06-26 00:30 | 2026-06-24 23:30 | 2025-07-01 00:30 | 2026-07-09 23:30 | 360 | 360
A4330 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.14.1.2.2.4.14.10 | AoS: Lining for hood (tapping fume suction) | 2025-06-26 00:30 | 2026-06-24 23:30 | 2025-06-26 00:30 | 2026-06-22 23:30 | 360 | 360
A4340 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | BE.s: Insulation | 2025-04-16 00:30 | 2025-07-11 23:30 | 2025-04-19 00:30 | 2025-07-18 23:30 | 86 | 86
A4350 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | BE.a: Insulation | 2025-02-26 00:30 | 2025-07-25 23:30 | 2025-02-26 00:30 | 2025-07-25 23:30 | 148 | 148
A4360 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DE.s: Insulation | 2025-09-17 00:30 | 2025-11-14 23:30 | 2025-09-17 00:30 | 2025-11-14 23:30 | 57 | 57
A4370 | Completed | BSL.1.3.1.2.2.1.2.2.4.1.2.2.4.15 | DE.a/i: Insulation | 2025-02-26 00:30 | 2025-11-28 23:30 | 2025-02-26 00:30 | 2025-11-28 23:30 | 271 | 271