## Sheet1
task_code | status_code | wbs_id | task_name | target_start_date | target_end_date | act_start_date | act_end_date | target_drtn_hr_cnt | act_drtn_hr_cnt | delete_record_flag
Activity ID | Activity Status | WBS Code | Activity Name | (*)Planned Start | (*)Planned Finish | Actual Start | Actual Finish | Original Duration(d) | (*)Actual Duration(d) | Delete This Row
A-1001 | Completed | WTP.02.CIV.01 | Site Clearance & Grubbing | 2025-04-01 00:30 | 2025-04-10 00:30 | 45748 | 45758 | 6 | 6
A-1002 | Completed | WTP.02.CIV.02 | Bulk Excavation — Aeration Basin | 45762 | 45782 | 2025-04-16 00:30 | 2025-05-07 00:30 | 14 | 15
A-1003 | In Progress | WTP.02.STR.01 | Rebar Fixing — Basin Base Slab | 2025-06-01 00:30 | 2026-05-01 00:30 | 45813 |  | 11 | 300
A-1004 | In Progress | WTP.02.STR.02 | Formwork — Basin Walls (North) | 46174 | 46213 | 2026-06-03 00:30 |  | 12 | 25
A-1005 | Completed | WTP.02.STR.02 | Concrete Pour — Basin Walls (North) | 2026-07-01 00:30 | 2026-07-14 00:30 | 46204 | 46216 | 7 | 6
A-1006 | Not Started | WTP.02.STR.03 | Waterproof Membrane — Basin | 46209 | 46216 |  |  | 5 | 0
A-1007 | Not Started | WTP.02.CIV.03 | Backfill Around Basin | 2026-07-20 00:30 | 2026-08-03 00:30 |  |  | 7 | 0
A-1008 | Completed | WTP.02.STR.05 | Handrails & Access Platforms — Basin | 45809 | 45818 | 2025-06-02 00:30 | 2025-06-09 00:30 | 8 | 7
A-1009 | In Progress | WTP.02.MEC.01 | Install Inlet Works Pipework | 2026-05-01 00:30 | 2026-06-20 00:30 | 46145 |  | 11 | 45
A-1010 | Not Started | WTP.02.MEP.02 | MEP First Fix — Pump House | 45778 | 46235 |  |  | 12 | 0
A-1011 | Completed | WTP.02.STR.04 | Structural Steel Erection — Pump House | 2025-03-01 00:30 | 2025-04-01 00:30 | 45718 | 45749 | 15 | 16
A-1012 | Not Started | WTP.02.ARC.01 | Cladding to Pump House | 46211 | 46223 |  |  | 9 | 0
A-1013 | Not Started | WTP.02.MEC.02 | Install Duty / Standby Pumps | 2026-08-05 00:30 | 2026-08-19 00:30 |  |  | 10 | 0
A-1014 | Completed | WTP.02.ARC.02 | Painting & Protective Coatings | 45992 | 46037 | 2025-12-01 00:30 | 2026-01-14 00:30 | 4 | 4
A-1015 | Completed |  | Temporary Site Fencing | 2025-01-01 00:30 | 2025-01-10 00:30 | 45658 | 45666 | 5 | 5
A-1016 | In Progress | WTP.02.ELE.01 | Ductbank & Cable Containment (Phase-1/Rev.C) | 46193 | 46214 | 2026-06-21 00:30 |  | 7 | 11
A-1017 | Completed | WTP.02.CIV.05 | Access Road Sub-base & Kerbing — Northgate Perimeter Boundary Works, Package 2 (Civil/Drainage), incl. all associated ancillary structures and appurtenances required for completion of the northern site boundary interface zone | 2025-02-01 00:30 | 2025-03-01 00:30 | 45689 | 45719 | 20 | 20
A-1018 | In Progress | WTP.02.CIV.06 | Chlorination Building Foundations | 46113 | 46174 | 2026-04-05 00:30 |  | 11 | 55
A-1019 | Not Started | WTP.02.MEC.03 | Install Chemical Dosing Skids | 2026-07-08 00:30 | 2026-07-16 00:30 |  |  | 8 | 0
A-1020 | Not Started | WTP.02.ELE.02 | Commissioning & Testing — SCADA | 46254 | 46270 |  |  | 13 | 0
A-1021 | Completed | WTP.02 | Contract Award |  | 2025-01-15 00:30 |  | 45672 | 0 | 0
A-1022 | Completed | WTP.02 | Site Mobilization Complete | 45689 |  | 2025-02-01 00:30 |  | 0 | 0
A-1023 | Not Started | WTP.02 | Hot Commissioning Milestone |  | 2026-07-12 00:30 |  |  | 0 | 0
A-1024 | Completed | WTP.02.CIV.04 | Underground Drainage Runs | 46023 | 46082 | 2026-01-02 00:30 | 2026-02-28 00:30 | 14 | 13
A-1025 | In Progress | WTP.02.STR.06 | Erection of Balance Items | 2026-07-09 00:30 | 2026-07-15 00:30 | 46212 |  | 5 | 4
A-1027 | Not Started | WTP.02.CIV.08 | Miscellaneous Works With No Duration Recorded | 46143 | 46157
A-1028 | On Hold | WTP.02.ELE.03 | on hold pending client decision | 2026-06-01 00:30 | 2026-07-09 00:30 |  |  | 10 | 5
A-1029 | completed | WTP.02.ELE.04 | Spare Parts Procurement | 46113 | 46132 | 2026-04-01 00:30 | 2026-04-18 00:30 | 12 | 12
A-1026 | Completed | WTP.02.CIV.07 | Miscellaneous Punch-list Closeout | 2026-05-01 00:30 | 2026-05-10 00:30 | 46143 | 46151 | 6 | 6